CONSTRUCTION OF 110 KV SUBSTATION AT VALLARPADAM- HIGH LIGHTS

(Assume that CoPT will fund the capital cost)

| 1 | Total Estimated cost | Rs 40 Crores |  |
| --- | --- | --- | --- |
| 2 | Amount receivable through grant under ASIDE | Rs 15 Crores |  |
| 3 | Balance amount to be sourced | Rs 25 Crores |  |
| 4 | Expected date of commencement of work | 01.07.2014 |  |
| 5 | Time period | 18 Months |  |
| 6 | Expected date of completion of work | 31.12.2015 |  |
| 7 | Lead time for according statutory clearance from CEA/KSEB for commissioning | 6 months |  |
| 8 | Date of commissioning & taking over | 01.06.2016 |  |
| 9 | Rate of interest as per CERC norms | 12 % of loan amount as per PLR for Rs 25 Crores. | No interest is allowed for asset created out of grant |
| 10 | Rate of depreciation as per CERC norms | 3.6% of capital asset. (40 Crores) | Depreciation is computed for Rs 40 Crores. |
| 11 | Anticipated yearly consumption by IGTPL | 100 Lakhs unit during 2016 and 3% increase thereafter. |  |
| 12 | Anticipated BST during 2016 | Rs 5.60/unit with 5% hike | Rs 350/KVA/ month |
| 13 | Anticipated RST on general tariff during 2016 for the consumption>30000/month | Rs 8/unit with 5% hike | Rs 400/KVA/month |
| 14 | Anticipated RST during 2016 for the consumption <30000/month | Rs 7.25/unit with 5% hike | Rs 400/KVA/month |

Existing tariff.

| Bulk Supply Tariff (BST) | Retail supply tariff (RST) applicable to HT-IV |
| --- | --- |
| Demand Charge- Rs 300/KVA/month | Demand charge – Rs 400/KVA/Month |  |
| Energy charge - Rs 5.05/unit | Energy charge- Rs 7.2 /unit (For consumption>30000 |  |
|  | - Rs 6.10/unit (For cons: up to 30000 |  |