MID TERM PERFORMANCE REVIEW OF SBU-T FOR 2019-20 & REVISED ESTIMATE FOR 2020-21 & 2021-22

CHAPTER 8 MID TERM PERFORMANCE REVIEW OF SBU-T FOR THE YEAR 2019-20

8.1	INTRODUCTION

8.1.1	The Strategic Business Unit – Transmission of KSEBL performs functions of the State Transmission Utility, to ensure development of an efficient, coordinated and economical system of intra-state transmission lines for smooth flow of electricity from generating station to the load centers. The second transfer scheme entrusts the responsibility on the STU to develop and execute long term plans for evacuation and supply of power at voltages of and above 33KV, in consultation and co-ordination with the other SBUs and under the policy framework developed by KSEBL. SBU-T is also carrying out the functions of State Load Despatch Centre, as provided in Part-II of Schedule-A1 of the second Transfer scheme. The SBU-T handles the total energy sold to consumers and licensees within the state, power drawn by open access consumers and the small quantum of energy sold outside the state.

8.1.2	As per the second Transfer Scheme, all assets of voltage level of 66KV and above is assigned to SBU-Transmission. At the same time, SBU-T is entrusted with the construction of 33KV and above system.

8.1.3	SBU-T had submitted before Hon’ble Commission a detailed CIP and MYT ARR petition before Hon’ble Commission ion October 30th, 2018. As per Regulation 10(2) of the KSERC(Terms and Conditions for determination of Tariff) Regulations, 2018 issued by Hon’ble Commission, every generating business/company or transmission business/licensee or distribution business/licensee or State Load Despatch Centre shall file, on or before the Thirtieth day of November 2019, the Mid-term Performance Review (MPR) which shall comprise the truing up for the financial year upto 2018-19 and midyear performance review for the year 2019-20 and the revised forecast for the year 2020-21 and 2021-22 on account of unexpected variations if any on controllable and uncontrollable parameters.

8.1.4	Accordingly the mid year performance review for the year 2019-20 and the revised forecast for the years 2020-21 and 2021-22 of SBU-T are furnished in this chapter.

8.2.		Transmission System Statistics

8.2.1	The voltage level wise capacity of Transmission system and number of substations and transmission lines as on 31st March, 2019 and the addition to transmission system during the half year period i.e. as on 30-9-2019in the State is summarized below:

| Table 8.1 Transmission System statistics |  |  |  |  |
| --- | --- | --- | --- | --- |
| No | Item | Unit | As on 31-3-2019 | As on 30-9-2019 |
| 1 | 400 kV Lines | Ckt-km | 855.96* | 947.96** |
| 2 | 220 kV Lines | Ckt-km | 2855.98 | 2910.98 |
| 3 | 110 kV Lines | Ckt-km | 4662.28 | 4803.28 |
| 4 | 66 kV Lines | Ckt-km | 2134.44 | 2100.64 |
| 5 | 33KV lines | Ckt-km | 2006.54 | 2082.69 |
| 6 | 400 kV Substations | Nos | 5* + 1 | 5* + 1 |
| 7 | 220 kV Substations | Nos | 22 | 22 |
| 8 | 110 kV Substations | Nos | 157 | 162 |
| 9 | 66KV Substations | Nos | 74 | 70 |
| 10 | 33 KV Substations | Nos | 153 | 158 |
| 11 | Total transmission capacity (MVA) | MVA | 20820.90 | 20933.40 |
|  | *PGCIL owned **Madakkathara-Malaparambu 400KV line addition |  |  |  |

8.3	Details of Transmission assets added up to September 2019

8.3.1	The details of transmission assets added during the half year of 2019-20 are tabulated below:

| Table 8.2 Substations and Lines Commissioned up to 30-9-2019 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Sl. No |  | Name of Substation | Voltage level (kV) | New / Upgn. |
| 1 |  | Olavakkode | 33 | New |
| 2 |  | Eramallur | 110 | New |
| 3 |  | Enathu | 66 | New |
| 4 |  | Cherai | 110 | New |
| 5 |  | Vydyuthi Bhavan | 33 | New |
| 6 |  | Sreekantapuram | 110 | upgn |
| 7 |  | Kelakom | 33 | New |
| 8 |  | Kodungallur | 110 | upgn |
| 9 |  | Vandanmedu | 33 | New |
| 10 |  | Mala | 110 | upgn |
| Lines commissioned |  |  |  |  |  |
| Sl. No | Name of Line |  | Voltage level (kV) |  |  |  |
| 1 | Tap line to Cherai |  | 110 |  |  |  |
| 2 | Medicall College-Vydyuthi Bhavanam UG cable |  | 33 |  |  |  |
| 3 | Madakkathara -Malaparamba |  | 400 (92 km) |  |  |  |
| 4 | Madakkathara – Malaparamba |  | 220KV (46km) |  |  |  |
| 5 | Karukadam-Kothamangalam |  | 220KV (9 km) |  |  |  |
| 6 | LILO Kanhirode- Sreekandapuram |  | 110KV (12.5 km) |  |  |  |
| 7 | LILO Aroor- Eramallur |  | 110KV (0.5 km) |  |  |  |
| 8 | Chalakudy-Kodungallur |  | 110KV (43 km) |  |  |  |
| 9 | Parassala-Neyattinkara |  | 110KV (11 km) |  |  |  |
| 10 | Kaniambetta – Kuthumunda |  | 110KV (12.8 km) |  |  |  |
| 11 | Adoor-Enathu |  | 66KV (11.4 km) |  |  |  |
| 12 | Venakkara-Olavakode |  | 33KV (8 km) |  |  |  |
| 13 | Nedumkandan – Vadunedu |  | 33KV (21 km) |  |  |  |
| 14 | Santhinagar - Pookothumpadam |  | 33KV (10 km) |  |  |  |
|  | Capacity Addition |  |  |  |  |  |
| Sl. No | Name of Substation |  | Voltage level (kV) |  |  |  |
| 1 | 110 kV Substation, Panoor |  | 110/33 |  |  |  |
| 2 | 33 kV Substation, Melady |  | 33/11 |  |  |  |
| 3 | 33 kV Substation, Venjarammoodu |  | 33/11 |  |  |  |
| 4 | 33 kV Substation, Kadakkavoor |  | 33/11 |  |  |  |
| 5 | 33 kV Substation, Kadakkavoor |  | 33/11 |  |  |  |
| 6 | 33 kV Substation, Kacheri, Attingal |  | 33/11 |  |  |  |
| 7 | 33 kV Substation, Poovar |  | 33/11 |  |  |  |
| 8 | 110 kV Substation, Medical College |  | 110/33 |  |  |  |

8.4.	Capital expenditure and Capitalization

8.4.1	SBU-T had submitted before Hon’ble Commission a detailed Capital Investment Plan for the control period along with the MYT petition filed on 30th October 2018. The capital addition provisionally approved for the years 2019-20, 2020-21 and 2021-22 vide the order dated 8-7-2019 is submitted below:

| Table 8.3 Total GFA addition provisionally approved of SBU-T for 2019-20, 2020-21 & 2021-22 (Rs Cr) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019-20 |  | 2020-21 |  | 2021-22 |  |
| Name of Work |  | Claimed | Approved | Claimed | Approved | Claimed | Approved |
| 1 | Ongoing projects plus new small works | 568.73 | 312.80 | 196.28 | 20.00 | 254.26 | 0.00 |
| 2 | New Capital Works above 10Cr | 662.59 | 353.74 | 421.83 | 150.92 | 41.65 | 141.80 |
| 3 | Transgrid Works | 362.57 | 362.57 | 2073.84 | 1244.84 | 260.96 | 260.96 |
|  | Total | 1593.89 | 1029.11 | 2691.95 | 1415.76 | 556.87 | 402.76 |

The status of the above works as on 30-9-2019 along with the physical progress is submitted below.

8.5 Status of Ongoing projects & new projects (w/o DPR)

8.5.1	KSEBL in the MYT petition had submitted a list of capital works having project cost less than Rs.10Cr and some new projects for which DPR were under preparation under various Transmission Circles of KSEBL. The status of these works as on 30-9-2019 is enclosed as Appendix 1.

8.5.2	Many projects planned in 2018-19 could not be completed in 2018-19 due to flood that affected the State during 2018-19. The commissioning of these projects extended to 2019-20 and is expected that these projects will be commissioned in 2019-20. The GFA addition in the year 2018-19 was less compared to that estimated in the ARR. The revised GFA addition for the year 2019-20 is more than that estimated in the ARR due to carry over of commissioning of assets originally planned for 2018-19. The details of works planned under various transmission circles as above for the year 2019-20  and their status as on 30-9-2019 is detailed under Appendix 1.The revised GFA addition on account of ongoing and new small works for the years 2019-20, 2020-21 and 2021-22 are given below.

| Table 8.4 GFA addition – Ongoing and New projects less than 10Cr |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2019-20 |  |  | 2020-21 |  |  | 2021-22 |  |  |
| In Area under | Estimated in ARR (Rs.Cr.) | Provisionally approved (Rs.Cr.) | Revised estimate (Rs.Cr.) | Estimated in ARR (Rs.Cr.) | Provisionally approved (Rs.Cr.) | Revised estimate (Rs.Cr.) | Estiamted in ARR (Rs.Cr.) | Provisionally approved (Rs.Cr.) | Revised estimate (Rs.Cr.) |
| Total Ongoing + New works | 568.73 | 312.80 | 724.09 | 196.28 | 20.00 | 201.44 | 254.26 | 0 | 77.47 |

8.6 Status of Normal works (above 10Cr) planned in the control period

8.6.1	About 40 new capital works were proposed for the control period exceeding Rs.10 Crore, for which DPR were prepared and submitted before Hon’ble Commission. The project ‘Reliable Communication & Data acquisition’ submitted in the original CIP under ‘SLDC Works’ is shifted to works under ‘SBU-T’ as the asset addition through this project comes under various transmission substations. The status of normal works as on 30-9-2019 is submitted below.

| Table 8.5 NORMAL WORKS (STATUS AS ON 30-9-2019) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Name of Work | Target CoD | Physical (%) | Revised CoD | Remarks |
| 1 | 110 KV DC 220 KV S/S, Palakkad- Malampuzha | 2019-20 | 0% | 2020-21 | Work awarded and agreement executed |
| 2 | New 220kV Substation at Kottayi | 2021-22 |  |  | Project dropped due to land availability issues |
| 3 | 110kV GIS in 110kV Substation, Vennakkara | 2019-20 | 80% | 2020-21 | 80% completed |
| 4 | New 110KV S/S Pattambi | 2019-20 | 0% | 2020-21 | Land purchased and registration done on 21-3-2019. Site levelling and construciton of retaining wall progressing. Line work will be tendered soon. |
|  | 110 kV Shornur- Malapparamba D/c feeder |  |  |  |  |
| 5 | 66 kV S/S Chandranagar in 110 kV | 2019-20 | 0% | 2020-21 | Scheme modified as LILO arrangement from PVKN feeder. (The work is only Rs.4 Cr now and therefore is included in the list of small works less than Rs.10Cr) |
|  | 110 kV Kanjikode - Chandranagar D/c |  |  |  |  |
|  | 110 kV Chandranagar - Vennakkara D/c |  |  |  |  |
| 6 | 110 kV Substation, Mannuthy | 2019-20 | 0% | 2020-21 | Alterations in the scheme with 2 numbers of 12.5MVA T/F replaced with 1 no. 12.5MVA T/F. Also GIS Substation is replaced with AIS. Revised DPR enclosed. |
|  | LILO 110 kV Madakkathara - Ollur D/c |  |  |  |  |
| 7 | Upgradation 66kV Pudukkad – Kattoor SC & construction 2 Nos. 110kV bays at Pudukkad S/S | 2020-21 | 0% | 2020-21 | Work tendered. Delay in tendering occured due to litigation and court cases. |
| 8 | Upgradation of Viyyur -Ollur 66kV line | 2020-21 | 0% | 2020-21 | Pre construction works progressing. |
| 9 | Upgradation Pallom - Ettumanoor 66 kV S/c | 2020-21 | 0% | 2021-22 | Preconstruction works progressing. |
|  | Upgradation 66 kV S/S Gandhinagar to 110 kV |  | 0% |  |  |
|  | Upgradation of 66 kV S/S Kottayam to 110 kV |  | 0% |  |  |
| 10 | Upgradation 66 kV Koothattukulam - Kuravilangadu & 66kV Kuravilangad S/S | 2019-20 | 0% | 2021-22 | Preconstruction works progressing. |
| 11 | Upgradation 66 kV Kothamangalam - Koothattukulam S/c to 110 kV D/c. | 2019-20 | 54% | 2020-21 | 54% work completed. Stub setting at 56 locations completed, line survey and tower schedule approval completed, 12 numbers of towers erected. |
| 12 | Up-gradation of 66kV S/S Koothattukulam to 110kV-vaikom | 2019-20 | 32% | 2020-21 | Construction of control room 50% completed, site levelling and construction of retaining wall – 99% completed. |
|  |  |  |  |  | Overall 32% work completed. |
| 13 | 66 kV SC Pala-Ettumanoor to 110 kV DC and construction of feeder bays at 110 kV S/S, Pala | 2019-20 | 12% | 2020-21 | Overall 12% completed. |
| 14 | Upgradation of 66kV S/S Ettumanoor to 110kV | 2019-20 | 6% | 2020-21 | S/S design changed to GIS and will be executed by TRANSGRID. Scope of this work is limited to installation of Transformers. Work in progress. |
| 15 | 110 kV S/S, Vazhoor | 2020-21 | 0% | 2021-22 | Land identified. In contact with Revenue authorities for getting land. |
| 16 | 110 kV GIS substation, Kowdiar | 2019-20 | 0% | 2021-22 | Land to be identified. |
| 17 | Upgradation of 66 kV S/S Palode to 110 kV | 2019-20 | 0% | 2021-22 | Pre-construction work in progress |
| 18 | Upgradation of TVT No: 1 and 2 feeders. | 2020-21 | 40% | 2021-22 | First phase Parassala – Neyattinkara portion work completed. |
|  |  |  |  |  | Second phase: Thirumala-Neyyatinkara portion work in progress. |
|  |  |  |  |  | Third phase: Paruthippara-Thirumala portion : Pre-construction work in progress. |
| 19 | 110 kV switching cum S/S at Panthalacode with 8 feeder bays &2T/F bays and erecting 2 x 12.5 MVA, 110/11 kV T/F | 2020-21 | 0% | 2021-22 | Land finalized. |
| 20 | 110 kV S/S, Chithara LILO of 110 kV Edamon -Paruthippara to 110 kV S/S Chithara | 2019-20 | 0% | 2021-22 | Land acquisition procedures in progress. |
| 21 | 110 kV GIS Kollam - Kottiyam (SC, UG cable) | 2019-20 | 0% | 2021-22 | Pre construction work in progress. |
| 22 | 66kV S/S Anchal to 110kV with 2 nos, 110/11kV, 12.5MVA T/F and upgradation of 66kV SC Edamon- Ayoor to 110kV DC line | 2019-20 | 60% | 2019-20 | Work in progress. 60% completed. |
| 23 | 66kV S/S, Karunagappally to 110kV and upgradation of line from 110kV S/S, Sasthamcotta to 66kV S/S, Karunagapally | 2019-20 | 35% | 2020-21 | Work in progress. 35% completed. |
| 24 | 110 kV Kayamkulam -Karunagapally D/c | 2021-22 | 0% | 2021-22 | Pre-construction work in progress |
| 25 | 66 kV S/S Kuttanad to 110 Kv, Poopally- Kuttanad portion of 66kV Kuttanad - Alappuzha S/c feeder to 110 kV D/c | 2020-21 | 0% | 2021-22 | Tendering stage |
| 26 | 66 kV Punnapra -Alappuzha DC to 110 kV DC | 2020-21 | 0% | 2021-22 | Pre-construction work in progress |
| 27 | 110 kV Substation, Seethangoli | 2019-20 | S/S: 0% | 2021-22 | Land to be obtained. |
|  | LILO of 110 kV Vidyanagar - Kubanoor to 110 kV S/s Seethangoli |  | Line : 0% |  |  |
| 28 | 110 kV GIS Substation, Malappuram | 2020-21 |  |  | Project not to be included in this control period |
| 29 | 110 kV Chemberi | 2019-20 | S/S: 30% | 2019-20 | Substation work 30% completed. |
|  |  |  | Line : 43% |  | Line work : 43% completed |
| 30 | Ambalathara Solarpark | 2019-20 | S/s: 93% | 2020-21 | Substation work 93% completed. |
|  |  |  | Line: 57% |  | Line work : 57% completed |
| 31 | 33 kV S/S Thambalamanna to 110 kV | 2019-20 | 65% | 2019-20 | 65% work completed. |
|  | 110 kV Agasthiamuzhy -Thambalamanna |  |  |  |  |
| 32 | 66 kV Substation Kuthumunda to 110 kV | 2019-20 | 70% | 2019-20 | Line upgradation completed. |
| 33 | 66 kV Substation Mankada to 110 kV | 2019-20 | 10% | 2020-21 | Work started |
|  | 110 kV D/c line Valambur -Elachola, 66 kV Malappuram - Mankada S/c feeder to 110 kV D/c |  |  |  |  |
| 34 | 66 kV Kaniyampetta-Sulthanbattery feeder to 110 kV LILO-ing to 110 kV S/s Ambalavayal | 2019-20 | 63% | 2019-20 | 63% of work completed |
| 35 | LILO of 110 kV Nallalam - Kizhissery feeder to proposed 110 kV S/s Pulikkal | 2019-20 | 0% | 2021-22 | Land identified. |
| 36 | 110 kV Tirur - Parappanangadi D/c feeder | 2020-21 | 5% | 2020-21 | Preliminary profile survey 75% completed. |
| 37 | 110 kV Mylatty -Vidyanagar S/c line to 110/220 kV MCMV line | 2019-20 | S/S: 0%, Line : 2% | 2020-21 | Work awarded and in progress |
| 38 | Doubling 66 kV Kunnamangalam - Thamarassery in 110 kV parameters | 2019-20 | 0% | 2021-22 | Alternate scheme evolved with substation also included. Revised DPR included. |
| 39 | Methottuthazham - Mankavu portion of 66 kV Nallalam - Kuttikkattoor S/c line to 110 kV D/c | 2019-20 | 30% | 2019-20 | Work in progress. 30% completed. |
| 40 | LILO of 110 kV Tirur- Kuttipuram, Edappal -Kuttipuram & Tirur- Ponnani to 110 kV S/S Vengaloor | 2020-21 | 0% | 2020-21 | Sanction received from KIIFB. Land acquisition in progress. Line work tendered. Tender evaluation progressing. |
| 41 | Reliable Communication & Data Acquisition | 2021-22 | 10% | 2021-22 | Work under process. Revised DPR attached. |

8.6.2	It is humbly submitted that for many works, the progress was not upto the target due to land availability issues and floods that affected the State during 2018-19.   Following revisions in the already submitted plan are made:

8.7 Charging of 66 kV Substation Chandranagar in 110 kV, 110 kV Kanjikode - Chandranagar D/c feeder, 110 kV Chandranagar - Vennakkara D/c Feeder

8.7.1	DPR submitted was for the upgradation of Sub Station by constructing 14.5KMS 110 KV DC line from Kanjikode to Vennakkara via Palakkad Medical College 66 KV Sub Station using the ROW of existing decommissioned Palakkad-Madukkara 66kv Single circuit line and Vennakkara -Kozhinjampara decommissioned line. But with the proposed 110KV GIS at Vennakkara, there is no need for this proposal. Hence the DPR is revised with 110KV GIS at Vennakkara with LILO arrangement in PVKN feeder. The estimated cost of the project is Rs 4 Cr and is expected to be commissioned by 2020-21.  A comparison of the original proposal and revised proposal is submitted below.

| Table 8.6 comparison of the original and revised proposal (Rs.Cr.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| As per ARR |  |  | Revised proposal |  |  |
| Description of work | CoD | Cost | Description of work | CoD | Cost |
| Upgrading 66 kV S/S Chandranagar to 110 kV | 2019-20 | 23.10 | 110KV GIS S/S, Vennakkara | 2020-21 | 4 |
| 110 kV Kanjikode - Chandranagar D/c line |  |  |  |  |  |
| 110 kV Chandranagar - Vennakkara D/c line |  |  |  |  |  |

8.8 Construction of 110 kV Substation, Mannuthy and LILO of one circuit of 110 kV Madakkathara - Ollur D/c feeder to 110 kV Substation Mannuthy

8.8.1	This proposal is for construction of 110kV AIS substation at Kerala Veterinary and Animal Science  University Campus, Mannuthy,Thrissur  by installing one No. 110/11kV, 12.5MVA transformers and drawing 0.06km new 110kV DC line from Madakkathara- Kodakara feeder as LILO arrangements. This proposal is a revision of the earlier proposal of providing GIS substation at Mannuthy. GIS substation was proposed earlier anticipating land availability issues. Since sufficient land is obtained for the project, the proposal is revised with AIS.  The estimated cost of the AIS project is Rs 11.60 Cr and is expected to be commissioned by 2020-21.

| Table 8.7 Comparison of ARR and revised proposal (Rs.Cr.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| As per ARR |  |  | Revised proposal |  |  |
| Description of work | CoD | Cost | Description of work | CoD | Cost |
| 110KV GIS Substation at Mannuthy | 2019-20 | 26.30 | 110KV AIS S/S, Mannuthy | 2020-21 | 11.60 |

8.9 Upgradation of 66KV S/S, Thamarassery and 66 kV Kunnamangalam - Thamarassery line

8.9.1	The original project was only for doubling of 66KV Kunnumangalam-Thamarassery line in 110KV parameters. The project is revised by including upgradation of 66kV Substation, Thamarassery to 110kV.

8.9.2	The present installed capacity of Thamarassery substation is 20MVA (Two 66/11kV transformers of capacity 10MVA each). Now the peak load demand of this station comes to nearly 15MVA and hence the upgradation to 110kV substation is proposed. Also this feeder extends another 19.278 km to Kuthumunda 66kV(KU-TM) substation for interconnection. The peak load of this feeder  when it feeds Thamarassery Substation alone is 110A , when it extends up to  Kuthumunda substation the load will increase to a range of 120-180A . Existing line capacity will not be adequate as far as present load condition and future load growth is considered. Also the replacement of existing conductor with ACSR Wolf will improve the tensile strength of the feeder as well as reduce transmission loss. Moreover, the line passes through residential and hilly areas of Thamarassery, Koduvally and Kunnamangalam villages. Lot of land development / construction works are being carried out in these areas and statutory clearance has been seriously violated in many sites due to earth filling activities. Hence the line has to be raised for obtaining sufficient ground clearance which is very urgent as far as safety aspect is considered.

8.9.3	With the commissioning  of the  upgraded  66 kV Kunnamangalam –Thamarassery feeder , another 110kV connectivity can be materialized for  meeting  the increased power evacuation requirement  and load  demand of  Thamarassery Substation. 	The proposed project envisages

1.  Constructing new Substation in 110kV standard near the existing 66kV yard in Thamarassery  substation and installing 2nos of 12.5MVA transformers and associated equipments and then dismantling the existing 66kV substation and equipments.

2. Conversion of Existing 66KV SC Kunnamangalam- Thamarassery Feeder (17.7km) to 110KV DC Feeder.

8.9.4	The estimated cost of the project is Rs 38.15 Cr and is expected to be commissioned by 2021-22.

| Table 8.8 Comparison of ARR and revised proposal (Rs.Cr.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| As per ARR |  |  | Revised proposal |  |  |
| Description of work | CoD | Cost | Description of work | CoD | Cost |
| Doubling of 66KV Kunnumangalam-Thamarassery line in 110KV parameters. | 2019-20 | 18.06 | Upgradation of 66KV S/S, Thamarassery and 66 kV Kunnamangalam - Thamarassery line | 2021-22 | 38.15 |

8.10 Reliable Communication and Data Acquisition System.

8.10.1	The proposal was submitted before Hon’ble Commission along with the original CIP submitted on October 30, 2018 along with the DPR. The original estimate was Rs. 212.45 Crore. Now the estimate is revised limiting the expenditure to present requirement and giving price escalation considering present market price of various equipments and for accommodating additional cost for supporting KFON project of Government of Kerala by providing 48 cores instead of 24 core OPGW. AS per the revised estimate the total project cost will be Rs.175.20 Crore of which, 42% of the project cost is available as PSDF grant. The project is expected for commissioning by 2021-22. The project was included under SLDC works in the original ARR CIP. However, the works coming under this scheme belong to Transmission and therefore the work is shifted from SLDC head to Transmission head.

| Table 8.9 Comparison of ARR and revised proposal (Rs.Cr.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| As per ARR |  |  | Revised proposal |  |  |
| Description of work | CoD | Cost | Description of work | CoD | Cost |
| Reliable Communication and Data Acquisition system (under SLDC Capital works) | 2019-20 | 212.45 | Reliable Communication and Data Acquisition system (under SBU-T capital works) | 2021-22 | 175.20 |

8.11 Up gradation of 66KV substation, Ettumanoor to 110KV

8.11.1	The project was originally estimated at a cost of Rs.20.80 Cr and expected for commissioning by 2019-20. However, a large portion of the work is shifted to Transgrid and therefore the project cost has come down to Rs.6.67 Cr and revised CoD as 2020-21.

| Table 8.10 Comparison of ARR and revised proposal (Rs.Cr.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| As per ARR |  |  | Revised proposal |  |  |
| Description of work | CoD | Cost | Description of work | CoD | Cost |
| Upgradation of 66KV Substation, Ettumanoor to 110KV | 2019-20 | 20.80 | Upgradation of 66KV Substation, Ettumanoor to 110KV | 2020-21 | 6.67 |

8.12 Renovation & Modernization of 110KV GIS Substation, Malappuram

8.12.1	The project was planned for an amount of Rs. 62.02 Cr as GIS with expected CoD in 2020-21. The GIS Substation was planned due to limitation in land availability in that area. Considering the high cost of GIS, it was decided to explore possibility of AIS using alternate scheme. Therefore, the execution of the project is shifted to next control period.

| Table 8.11 Comparison of ARR and revised proposal (Rs.Cr.) |  |  |  |  |
| --- | --- | --- | --- | --- |
| As per ARR |  |  | Revised proposal |  |
| Description of work | CoD | Cost (Rs.Cr.) | Description of work | CoD |
| Renovation & Modernization of 110KV GIS Substation, Malappuram | 2020-21 | 62.02 | Renovation & Modernization of 110KV GIS Substation, Malappuram | Next control period |

8.13 Construction of 110KV GIS Substation, Vengaloor

8.13.1	The project was planned for an amount of Rs. 46.39 Cr with expected CoD in 2020-21. The execution of the project is shifted to Transgrid as “Vengallur GIS & TLSP Phase II” Package. The project proposal is revised considering the requirement for 220kV transmission line and 220kV Substation at Vengallur in the Malappuram district.

| Table 8.12 Comparison of ARR and revised proposal (Rs.Cr.) |  |  |  |  |
| --- | --- | --- | --- | --- |
| As per ARR |  |  | Revised proposal |  |
| Description of work | CoD | Cost | Description of work | Status |
| Construction of 110KV GIS S/S, Vengaloor | 2020-21 | 46.39 | Construction of 110KV GIS S/S, Vengaloor | Shifted to Transgrid |

8.14 220KV Substation, Kottayi

8.14.1	The project was originally envisaged for an amount of Rs.66 Cr with expected CoD in 2020-21. However, this project is dropped due to land availability issues. The scheme has been included in the Transgrid scheme under the project of 220KV S/S Venakkara.

| Table 8.13 Comparison of ARR and revised proposal (Rs.Cr) |  |  |  |
| --- | --- | --- | --- |
| As per ARR |  |  | Revised proposal |
| Description of work | CoD | Cost | Status |
| Construction of 220KV S/S, Kottayi | 2020-21 | 66 | Dropped |

8.14.2	The details of capital outlay in the 4 years of the control period for the capital works under this head as per the original estimate in the ARR and revised estimate are submitted below. Minor cost variations between that estimated in the ARR and the revised claim for some capital works are due to the change in employee related cost due to re-scheduling of work. The reason for major variations, if any, is mentioned along with each item of work. It is humbly requested that Hon’ble Commission may approve the revised schedule and cost of these capital works.

| Table 8.14 Normal works above Rs.10 Cr -Capital Outlay (Amount in Rs. Cr) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | As per ARR |  |  |  |  | Revised |  |  |  |  |
| No. | Project | Project cost (Rs.Cr.) | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | Total |
| 1 | 110kV Kanhangad – Cheruvathuer to 220kV S/s Ambalathara | 36.06 | 30 | 6.06 |  |  | 2 | 30.45 | 5.51 |  | 37.96 |
| 2 | Upgradation of 66kV Palakkad Medical College S/S and line (Revised DPR) | 23.1 | 4 | 19.1 |  |  |  |  | 0 |  | 0 |
| 3 | 110 kV GIS Project Vennakkara | 44.6 | 5 | 39.6 |  |  |  | 22.3 | 22.3 |  | 44.6 |
| 4 | Construction of Palakkad- Malampuzha 110kV Line | 14.38 | 4.38 | 10 |  |  |  | 4.38 | 10 |  | 14.38 |
| 5 | 110kV Substation Pattambi | 25.5 | 5 | 20.5 |  |  | 5 | 10.3 | 10.2 |  | 25.5 |
| 6 | Mannuthy 110 kV Project (Revised by AIS instead of GIS) | 26.3 | 6.3 | 20 |  |  |  | 2.9 | 8.7 |  | 11.6 |
| 7 | Upgradation 66kV S/S Ettumanoor to 110kV (Large portion of the work shifted to Transgrid) | 20.80 | 8 | 12.8 |  |  | 0.67 | 2 | 4 |  | 6.67 |
| 8 | Upgradation 66kV S/S, Kuravilangadu and Koothattukulam-Kuravilangadu to 110 kV | 21.65 | 6.65 | 15 |  |  | 0 | 0 | 14 | 7.65 | 21.65 |
| 9 | Upgradation 66kV S/S Koothattukulam | 15.01 | 6 | 9.01 |  |  | 3.4 | 1.5 | 8.37 |  | 13.27 |
| 10 | Upgradation of 66KV Kothamangalam- Kotthttukulam | 14.67 | 4.67 | 10 |  |  | 4.15 | 11 | 1 |  | 16.15 |
| 11 | Upgradation of 66kV SC Pala-Ettumanoor | 15.75 | 3 | 12.75 |  |  | 0 | 10.75 | 5 |  | 15.75 |
| 12 | Upgradation of 66kV S/S Anchal & 66kV SC Edamon –Anchal-Ayur line (Revised based on amount in LoA) | 42.66 | 29.86 | 12.8 |  |  | 8.28 | 20.57 |  |  | 28.85 |
| 13 | Up gradation of 66kV S/S, Karunagappally & 66kV SC Sasthamcotta-Karunagapally line | 18.20 | 12.74 | 5.46 |  |  | 1.92 | 10.51 | 4.07 |  | 16.5 |
| 14 | Construction of 110kV Substation, Chithara | 12.27 | 3.68 | 8.59 |  |  |  |  | 3.68 | 8.59 | 12.27 |
| 15 | Interlinking 110kV GIS S/S, Kollam & Kottiyam S/S | 63.23 | 12.65 | 50.58 |  |  |  |  | 12.65 | 50.58 | 63.23 |
| 16 | 110kV GIS S/S at Kowdiar, Thiruvananthapuram | 34.93 |  | 34.93 |  |  |  |  |  | 34.93 | 34.93 |
| 17 | Upgradation of 66kV Substation Palode to 110kV | 18.45 |  | 18.45 |  |  | 0 | 0 | 9 | 10.75 | 19.75 |
| 18 | 66kV S/S, Ambalavayal & 66kV DC line from 66kV Kaniyambetta-Sulthanbathery | 13.49 | 5 | 8.49 |  |  | 4.585 | 10.66 |  |  | 15.24 |
| 19 | 110kV Substation, Chemperi and line | 27.77 | 14 | 13.77 |  |  | 0.73 | 29.24 |  |  | 29.97 |
| 20 | Upgradation of Kunnamangalam _ Thamarasserry line to 110kV (Revised) | 18.06 | 8.06 | 10 |  |  |  | 10.35 | 13.9 | 13.9 | 38.15 |
| 21 | Upgradation of Kuthumunda to110kV GIS | 33.98 | 3.98 | 30 |  |  | 3.98 | 31.9 |  |  | 35.88 |
| 22 | Upgradation of Mankada S/s to 110kV | 14.65 | 4.65 | 10 |  |  |  | 5.58 | 10.16 |  | 15.75 |
| 23 | Upgradation of 66kV S/S, Mankavu to 110kV | 13.56 | 5.56 | 8 |  |  | 1.8 | 12.64 |  |  | 14.44 |
| 24 | Upgradation of 110kV SC/DC line to 220/110kV MC MV line from Mylatty s/s to Vidyanagar | 29.43 | 20 | 9.43 |  |  | 0 | 7.99 | 23.97 |  | 31.96 |
| 25 | 110kV Substation, Pulikkal | 14.68 | 1.68 | 13 |  |  |  |  | 1.68 | 14.96 | 16.64 |
| 26 | 110kV Substation, Seethangoli | 11.59 | 4.59 | 7 |  |  | 0 | 0 | 3.34 | 10.07 | 13.41 |
| 27 | Upgradation of 33 kV S/S Thambalamanna & 110 kV Agasthiamuzhy -Thambalamanna (S/c, UG cable) | 39.02 | 18.02 | 20 |  |  | 18.02 | 21.88 |  |  | 39.9 |
| 28 | 220KV Substation Kottayi (dropped) | 66 | 0.5 | 30.5 | 35 |  | 0 | 0 | 0 | 0 | 0 |
| 29 | Upgradation of Pudukkad to Kattoor 66kV SC Line | 13.91 | 1 | 7 | 5.91 |  | 1 | 7 | 5.91 |  | 13.91 |
| 30 | Conversion of Ollur Viyyur feeder to 110 kV | 16.72 | 0.72 | 7 | 9 |  | 0.72 | 7 | 9 |  | 16.72 |
| 31 | Upgradation 66kV Pallom-Ettumanoor feeder & associated S/S to 110kV | 69.54 | 9 | 35 | 25.54 |  | 0 | 0 | 30 | 31.4 | 61.4 |
| 32 | Construction of 110kV substation Vazhoor | 14.4 | 1 | 8 | 5.4 |  | 0 | 0 | 5.3 | 7 | 12.3 |
| 33 | Upgradation of 66kV Substation Kuttanadu | 15.16 |  | 7.58 | 7.58 |  | 0 | 0 | 10 | 4.2 | 14.2 |
| 34 | Upgradation 66kV PUNNAPRA-ALAPPUZHA DC Feeder (Commisng shifted to next control period) | 17.54 |  | 8.77 | 8.77 |  | 0 | 0 | 0 | 7.25 | 0 |
| 35 | 110kV Switching Cum S/S at PANTHALACODE | 25.16 |  | 12.58 | 12.58 |  | 0 | 4 | 12 | 9.16 | 25.16 |
| 36 | Upgradation of 66 kV TVT No. I & II feeders | 60.03 | 18 | 30 | 12.03 |  | 4.24 | 12 | 30 | 13.79 | 60.03 |
| 37 | R&M 110kV GIS S/S, Malappuram (shifted to next control period) | 62.02 | 2.02 | 30 | 30 |  | 0 | 0 | 2 | 36 |  |
| 38 | LILO 110kV Edarikode- Tirur to Parappanangadi S/s | 14.96 | 1.96 | 10 | 3 |  | 1.96 | 0.63 | 14.57 |  | 17.16 |
| 39 | Construction 110kV GIS S/S , Vengaloor (shifted to Transgrid) | 46.39 | 2 | 19.48 | 24.91 |  | 0 | 0 | 0 | 0 | 0 |
| 40 | Construction of new 110kV DC line from Kayamkulam to Karunagapally | 41.65 |  | 15.3 | 13.3 | 13.05 | 0 | 0 | 28.79 | 17.71 | 46.5 |
| 41 | Reliable Communication and DA System |  |  |  |  |  | 0 | 21 | 87 | 68 | 176 |
|  | Sub Total |  | 263.67 | 656.33 | 193.02 | 13.05 | 62.46 | 308.53 | 406.11 | 345.94 | 1077.78 |
|  | PSDF funding for Reliable Communication project |  |  |  |  |  | 0 | 22.13 | 44.26 | 7.38 | 73.77 |
|  | Net capital less PSDF funding (Rs.Cr.) |  |  |  |  |  | 62.46 | 286.40 | 361.85 | 338.56 | 1004.01 |

8.14.4	In addition to the above, SBU-T submits along with this petition additional CIP for approval of Hon’ble Commission, wherein additional 13 works are also proposed for this control period. The details of these capital works are enclosed as Appendix-2. The DPRs of these 13 works are enclosed along with this petition. The abstract of these works along with their cash outflow is given below.

| Table 8.15 CAPITAL OUTLAY OF ADDITIONAL NORMAL WORKS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Outlay (Amount in Rs. Crores) |  |  |  |  |  |
| No. | Project | 2019-20 | 2020-21 | 2021-22 | Total |
|  |  | Rs.Cr. | Rs.Cr. | Rs.Cr. | Rs.Cr. |
| 1 | Construction of 110K/11kv Vengara S/S |  | 18.26 | 9.98 | 28.24 |
| 2 | Construction of 110KV S/s Adivaram | 7.821 | 9.069 |  | 16.89 |
| 3 | Construction 110 kV Substation, Kadampuzha |  | 14.06 | 9.47 | 23.53 |
| 4 | Upgradation of Mavelikara-Pallom 66KV DC | 0.1 | 2.1 | 39.6 | 41.8 |
| 5 | Construction of 110KV DC line from 66KV substation Kattappana to 66KV substation, Peerumedu |  | 25 | 15.7 | 40.7 |
| 6 | Upgradation of 66KV Sasthankotta-Chavara DC Line |  | 10 | 11.85 | 21.85 |
| 7 | Upgradation of 66KV Edappon-Kozhencherry SC line and associated bays | 3.1 | 12.4 | 5.15 | 20.65 |
| 8 | Construction of 110KV Substation, Thiruvali | 6.2 | 7.21 |  | 13.41 |
| 9 | Construction of Thimiri substation |  | 9 | 11.87 | 20.87 |
| 10 | Construction of Munnar substation and associated lines | 1 | 14 | 7.13 | 22.13 |
| 11 | Kuthunkal-Nedumkandam |  | 11 | 5 | 16 |
| 12 | Aluva-Kothamangalam |  | 20 | 22.49 | 42.49 |
| 13 | 110KV Substation Murickasery | 0.01 | 8 | 3.5 | 11.6 |
|  | Total | 18.23 | 160.10 | 141.74 | 320.16 |

8.14.5	The GFA addition on account of these works for the years 2019-20, 2020-21 and 2021-22 are given below.

| Table 8.16 GFA addition-Normal works above Rs.10 Cr |  |  |  |  |
| --- | --- | --- | --- | --- |
| No. | Project | 19-20 | 20-21 | 21-22 |
|  | GFA addition through works identified in MYT Petition (A) |  |  |  |
| 1 | Linking between 110kV Kanhangad – Cheruvathuer feeder to 220kV S/s Ambalathara |  | 37.96 |  |
| 2 | Upgradation of 66kV Palakkad Medical College Substation and line (Revised DPR) |  | 0 |  |
| 3 | 110 kV GIS Project Vennakkara |  | 44.6 |  |
| 4 | Construction of Palakkad- Malampuzha 110kV Line |  | 14.38 |  |
| 5 | 110kV Substation Pattambi |  | 25.5 |  |
| 6 | Mannuthy 110 kV Project (Revised ) |  | 11.6 |  |
| 7 | Upgradation of 66kV Substation Ettumanoor to 110kV (Large portion of the work shifted to Transgrid) |  | 6.67 |  |
| 8 | Upgradation of 66kV Substation, Kuravilangadu and Koothattukulam-Kuravilangadu to 110 kV |  |  | 21.65 |
| 9 | Upgradation of 66kV Substation Koothattukulam to 110 kV |  | 13.27 |  |
| 10 | Upgradation of 66KV Kothamangalam- Kotthttukulam Feeder to 110 KV |  | 16.15 |  |
| 11 | Upgradation of 66kV SC Pala-Ettumanoor feeders to 110kV |  | 15.75 |  |
| 12 | Upgradation of 66kV Substation Anchal to 110kV and Upgradation of 66kV SC Edamon –Anchal-Ayur line to 110kV DC | 28.85 |  |  |
| 13 | Up gradation of 66kV Substation, Karunagappally and 66kV SC Sasthamcotta-Karunagapally line to 110kV DC |  | 16.5 |  |
| 14 | Construction of 110kV Substation, Chithara |  |  | 12.27 |
| 15 | Interlinking 110kV GIS Substation, Kollam and 110kV Kottiyam Substation |  |  | 63.23 |
| 16 | 110kV GIS substation at Kowdiar, Thiruvananthapuram |  |  | 34.93 |
| 17 | Upgradation of 66kV Substation Palode to 110kV |  |  | 19.75 |
| 18 | 66kV Substation, Ambalavayal and 66kV DC line from 66kV Kaniyambetta-Sulthanbathery feeder in 110kV Parameters | 15.242 |  | 0 |
| 19 | 110kV Substation, Chemperi and line | 29.97 |  |  |
| 20 | Upgradation of Kunnamangalam _ Thamarasserry line to 110kV (Revised) |  |  | 38.15 |
| 21 | Upgradation of Kuthumunda to110kV GIS | 35.88 |  |  |
| 22 | Upgradation of Mankada S/s to 110kV |  | 15.748 |  |
| 23 | Upgradation of 66kV Substation, Mankavu to 110kV | 14.44 |  |  |
| 24 | Upgradation of 110kV SC/DC line to 220/110kV MC MV line from Mylatty s/s to Vidyanagar |  | 31.96 |  |
| 25 | 110kV Substation, Pulikkal |  |  | 16.64 |
| 26 | 110kV Substation, Seethangoli |  |  | 13.41 |
| 27 | Upgradation of 33 kV Substation Thambalamanna to 110 kV & 110 kV Agasthiamuzhy -Thambalamanna (S/c, UG cable) | 39.9 |  |  |
| 28 | 220KV Substation Kottayi |  |  |  |
| 29 | Upgradation of Pudukkad to Kattoor 66kV SC Line to 110kV DC Line |  | 13.91 |  |
| 30 | Conversion of Ollur Viyyur feeder to 110 kV |  | 16.72 |  |
| 31 | Upgradation of 66kV Pallom-Ettumanoor feeder and associated substations to 110kV |  |  | 61.4 |
| 32 | Construction of 110kV substation Vazhoor |  |  | 12.3 |
| 33 | Upgradation of 66kV Substation Kuttanadu to 110kV |  |  | 14.2 |
| 34 | Upgradation of 66kV PUNNAPRA-ALAPPUZHA DC Feeder to 110 kV (Commissioning shifted to next control period) |  |  | 0 |
| 35 | 110kV Switching Cum Substation at PANTHALACODE |  |  | 25.16 |
| 36 | Upgradation of 66 kV TVT No. I & II feeders |  |  | 60.03 |
| 37 | Renovation and modernisation 110kV GIS Substation, Malappuram (shifted to next control period) |  |  | 0 |
| 38 | LILO on 110kV Edarikode- Tirur to Parappanangadi S/s |  | 17.16 |  |
| 39 | Construction of 110kV GIS Substation , Vengaloor (shifted to Transgrid) |  |  |  |
| 40 | Construction of new 110kV DC line from Kayamkulam to Karunagapally |  |  | 46.5 |
| 41 | Reliable Communication and Data Acquisition System |  |  | 176 |
|  | Sub Total (A) | 164.28 | 297.88 | 615.62 |
|  | PSDF funding for Reliable Communication project |  |  | 73.77 |
|  | Net capital less PSDF funding (Rs.Cr.) | 164.28 | 297.88 | 541.85 |
|  | GFA addition through new works submitted (B) |  |  |  |
| 1 | Construction of 110K/11kv Vengara S/S |  |  | 28.24 |
| 2 | Construction of 110KV S/s Adivaram |  | 16.89 |  |
| 3 | Construction 110 kV Substation, Kadampuzha |  |  | 23.53 |
| 4 | Upgradation of Mavelikara-Pallom 66KV DC |  |  | 41.8 |
| 5 | Construction of 110KV DC line from 66KV substation Kattappana to 66KV substation, Peerumedu |  |  |  |
|  |  |  |  | 40.7 |
| 6 | Upgradation of 66KV Sasthankotta-Chavara DC Line |  |  | 21.85 |
| 7 | Upgradation of 66KV Edappon-Kozhencherry SC line and associated bays |  |  | 20.65 |
| 8 | Construction of 110KV Substation, Thiruvali |  | 13.41 |  |
| 9 | Construction of Thimiri substation |  |  | 20.87 |
| 10 | Construction of Munnar substation and associated lines |  |  | 22.13 |
| 11 | Kuthunkal-Nedumkandam |  |  | 16 |
| 12 | Aluva-Kothamangalam |  |  | 42.49 |
| 13 | 110KV Substation Murickasery |  |  | 11.6 |
|  | Total (B) | 0 | 30.3 | 289.86 |
|  | Grand Total (A)+(B) | 164.28 | 328.18 | 905.48 |

8.14.6	A summary of the GFA addition for the years 2019-20, 2020-21 and 2021-22 due to normal works above Rs.10Cr under SBU-T are summarized below.

| Table 8.17 GFA addition – Normal works above Rs.10Cr (Rs.Cr.) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2019-20 |  |  | 2020-21 |  |  | 2021-22 |  |  |
| In Area under | Estimated in ARR | Provisionally approved | Revised estimate | Estimated in ARR | Provisionally approved | Revised estimate | Estiamted in ARR | Provisionally approved | Revised estimate |
| Normal works above Rs.10Cr | 662.59 | 353.74 | 164.28 | 421.83 | 150.92 | 328.18 | 41.65 | 141.80 | 905.48 |
| Total | 662.59 | 353.74 | 164.28 | 421.83 | 150.92 | 328.18 | 41.65 | 354.25 | 905.48 |
| Less: PSDF Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 73.77 |
|  | 662.59 | 353.74 | 164.28 | 421.83 | 150.92 | 328.18 | 41.65 | 254.25 | 831.71 |

8.15 STATUS OF TRANSGRID WORKS

8.15.1	SBU-T had submitted12 numbers of capital works under ‘Transgrid 2.0 scheme’ proposed for the control period. The physical status as on 30-9-2019 of these works is submitted below.

|  | Table 8.18 TRANSGRID WORKS (Status as on 30-9-2019) |  |  |  |
| --- | --- | --- | --- | --- |
| No | Name of Work | Original Target year | Revised target year | Status as on 30-9-2019 |
| 1 | Kolathunadu | 2021-22 | 2021-22 | Work awarded and is in progress. Foundation 1/279 completed. |
| 2 | Chalakkudy | 2020-21 | 2020-21 | Chalakkudy 220kV S/S Work in progress. Overall Progress 22.75%. 220kV LILO line to Chalakkudy – Work awarded & commenced. |
| 3 | NRHTLS | 2019-20 | 2019-20 | 76% of work completed. |
| 4 | Thalasseri | 2020-21 | 2021-22 | 1. 220kV GIS Thalassery S/S Work Awarded and commenced. 2. 220kV Line to Thalassery from Mundayad – Work commenced. |
| 5 | Eranad | 2019-20 | 2019-20 | Work is in progress. The portion between Madakkathara and Malaparamba charged. Overall progress-68.19% |
| 6 | Aluva | 2019-20 | 2020-21 | 1. 200kV GIS Aluva is in progress. Overall progress – 16% . 2. 220kV Line to ALuva work in progress. Overall progress – 76%. |
| 7 | Kaloor | 2019-20 | 2019-20 | 1. 200kV GIS Kaloor is in progress Overall progress-22%. 2. 220kV LineKaloor :OH portion 65%. Cable portion – 30%. |
| 8 | Kottayam, Thuravur & Ettumanoor | 2020-21 | 2020-21 | 1. 400kV GIS Kottayam – Tender Evaluation in progress. 2. 220kV Thuravur – Land Acquisition in progress and the project shifted to Phase II 3. 220kV Ettumanoor S/S –Work awarded and the drawing approvals in progress. 3. Lines to Kottayam, Thuravur and Ettumanoor – Work Commenced and is in progress. |
| 9 | Kothamangalam & Chithirapuram | 2020-21 | 2020-21 | 1. Kothamangalam 220kV S/S – Work is in progress. Overall progress-33%. 2. 220kV Line to Kothamangalam – Pallivasal - Kothamangalam 220kV MCMV line- Overall progress- 65%, Karukudam Kothamangalam – 95% 3. Chithirapuram S/S – Work is in progress. Overall progress – 1%. |
| 10 | Kunnamangalam | 2019-20 | 2020-21 | 200kV GIS Kunnamangalam is in progress. Official Date of completion 11/01/2020. Overall progress-9%. 2. 220kV Line to Kunnamangalam, the work awarded and is in progress. |
| 11 | Manjeri | 2020-21 | 2019-20 | Work is in progress and is expected to be completed by March 2020. Overall progress – 62.18% |
| 12 | Kunnamkulam | 2020-21 | 2020-21 | 1. 220kV GIS S/S Kunnamakulam Work Awarded and commenced. 2. 220kV Line to Kunnnamkulam from Wadakkanchery – Work commenced and is in progress. |

8.15.2	The revised project cost of the above works and the revised CoD are submitted below.

| Table 8.19 TRANSGRID WORKS |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | As per ARR |  |  | Revised |  |  |  |  |  | Revised |
| No. | Project | Outlay (Amount in Rs. Crores) |  |  |  | Outlay (Amount in Rs. Crores) |  |  |  | Revised COD | Total |
|  |  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2018-19 Actual | 2019-20 | 2020-21 | 2021-22 |  |  |
| 1 | Aluva | 127.87 | 54.8 | 0 |  | 0 | 128.34 | 3 |  | 2019-20 | 131.34 |
| 2 | Kaloor | 125.93 | 53.97 | 0 |  | 0 | 138.81 | 0 |  | 2019-20 | 138.81 |
| 3 | Kothamangalam & Chithirapuram | 119.66 | 219.37 | 59.83 |  | 0 | 309.8 | 54.67 |  | 2020-21 | 364.47 |
| 4 | Kottayam, Thuravur &Ettumanoor |  | 379.17 | 162.5 |  | 0 | 162.5 | 379.17 |  | 2020-21 | 541.67 |
| 5 | Chalakudy | 7.14 | 35.71 | 28.57 |  | 0 | 45.53 | 34.05 |  | 2020-21 | 79.58 |
| 6 | Kunnamkulam | 13.03 | 65.15 | 52.12 |  | 0 | 78.43 | 55.98 |  | 2020-21 | 134.41 |
| 7 | Manjeri | 5.11 | 25.55 | 20.44 |  | 0 | 38.87 | 0 |  | 2019-20 | 38.87 |
| 8 | Thalasseri | 15.7 | 78.52 | 62.81 |  | 0 | 110.53 | 59.94 |  | 2020-21 | 170.47 |
| 9 | Kunnamangalam | 9.19 | 45.95 | 36.76 |  | 0 | 46 | 31.25 |  | 2020-21 | 77.25 |
| 10 | Eranad | 195 | 295 | 62 |  | 142.37 | 453.40 |  |  | 2019-20 | 595.77 |
| 11 | NRHTLS | 23.88 | 23.88 | 31.81 |  | 20.85 | 33.95 | 14.5 |  | 2020-21 | 69.3 |
| 12 | Kolathunadu | 26.1 | 104.38 | 78.29 | 52.19 | 0 | 141.83 | 85.1 | 60.42 | 2021-22 | 287.35 |
|  | Subtotal | 668.61 | 1381.45 | 595.13 | 52.19 | 163.22 | 1687.99 | 957.92 | 60.42 |  | 2629.29 |
|  | PSDF Funding |  |  |  |  |  |  |  |  |  |  |
|  | NRHTLS | 16.72 | 16.72 | 22.27 |  | 20.65 | 46.2 | 0 |  |  | 66.85 |
|  | Eranad | 120.57 | 182.4 | 30.91 |  | 118.59 | 215.34 | 0 |  |  | 333.93 |
|  | Total outlay for Transgrid works less funding | 531.32 | 1182.33 | 541.95 | 52.19 | 23.98 | 1426.45 | 957.92 | 60.42 | 0 | 2228.51 |

8.15.3	A comparison of the project cost as per the ARR and the revised cost is submitted below. The revised claim is based on the actual awarded project cost, whereas the ARR amount was based on estimates. All the 12 numbers of transgrid works except Kottayam package are awarded.

| Table 8.20 Comparison of ARR and revised proposal (Rs.Cr) |  |  |  |
| --- | --- | --- | --- |
|  |  | As per ARR | Revised |
| No. | Project | Project cost | Project cost |
| 1 | Aluva | 182.67 | 131.34 |
| 2 | Kaloor | 179.9 | 138.81 |
| 3 | Kothamangalam & Chithirapuram | 398.86 | 364.47 |
| 4 | Kottayam, Thuravur &Ettumanoor | 541.67 | 541.67 |
| 5 | Chalakudy | 71.42 | 79.58 |
| 6 | Kunnamkulam | 130.3 | 134.41 |
| 7 | Manjeri | 51.1 | 38.87 |
| 8 | Thalasseri | 157.03 | 170.47 |
| 9 | Kunnamangalam | 91.9 | 77.25 |
| 10 | Eranad | 552 | 595.77 |
| 11 | NRHTLS | 79.57 | 69.3 |
| 12 | Kolathunadu | 260.96 | 287.35 |
|  | Subtotal | 2697.38 | 2629.29 |
|  | PSDF Funding | 0 |  |
|  | NRHTLS | 55.71 | 66.85 |
|  | Eranad | 333.88 | 333.93 |
|  | Total outlay for Transgrid works less funding | 2307.78 | 2228.51 |

8.15.4	In addition, the following new works are also planned for the control period under Transgrid Phase II, the DPRs of which are enclosed with the Capital Investment plan (Appendix-2) submitted along with the instant petition.

| Table 8.21 ADDITIONAL TRANSGRID WORKS -CAPITAL OUTLAY (Rs.Cr.) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Name of Work | 2019-20 | 2020-21 | 2021-22 | Expected CoD | Total |
| 1 | Sabari package |  | 122 | 126 | 2021-22 | 248 |
| 2 | Vengallur GIS & TLSP Phase II |  | 136.12 | 68.06 | 2021-22 | 204.18 |
| 3 | Vizhinjam 220/110KV GIS Substation | 0.5 | 26.624 | 43.84 | 2021-22 | 71 |
|  | Total | 0.5 | 284.744 | 229.46 |  | 523.18 |

8.15.5	The GFA addition due to Transgrid works are submitted below.

| Table 8.22 TRANSGRID WORKS GFA Addition (Rs. Cr) |  |  |  |  |
| --- | --- | --- | --- | --- |
| No. | Project | 2019-20 | 2020-21 | 2021-22 |
| 1 | Aluva |  | 131.34 |  |
| 2 | Kaloor | 138.81 |  |  |
| 3 | Kothamangalam & Chithirapuram |  | 364.47 |  |
| 4 | Kottayam, Thuravur &Ettumanoor |  | 541.67 |  |
| 5 | Chalakudy |  | 79.58 |  |
| 6 | Kunnamkulam |  | 134.41 |  |
| 7 | Manjeri | 38.87 |  |  |
| 8 | Thalasseri |  | 170.47 |  |
| 9 | Kunnamangalam |  | 77.25 |  |
| 10 | Eranad | 595.77 |  |  |
| 11 | NRHTLS | 69.3 |  |  |
| 12 | Kolathunadu |  |  | 287.35 |
|  | Subtotal | 842.75 | 1499.19 | 287.35 |
|  | PSDF Funding |  |  |  |
|  | NRHTLS | 66.85 |  |  |
|  | Eranad | 333.93 |  |  |
|  | GFA addition less PSDF funding | 441.97 | 1499.19 | 287.35 |
|  | GFA addition new Transgrid works (Phase II) |  |  | 523.18 |
|  | Grand Total (Rs.Cr.) | 441.97 | 1499.19 |  |

8.15.6	The revised GFA addition due to the TRANSGRID works for the years 2019-20, 2020-21 and 2021-22 are submitted below:

| Table 8.23 GFA addition – Transgrid works (Rs Cr) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2019-20 |  |  | 2020-21 |  |  | 2021-22 |  |  |
| In Area under | Estimated in ARR | Provisionally approved | Revised estimate | Estimated in ARR | Provisionally approved | Revised estimate | Estimated in ARR | Provisionally approved | Revised estimate |
| Transgrid works | 362 .57 | 362.57 | 842.75 | 2073.84 | 1244.84 | 1499.19 | 260.96 | 260.96 | 810.53 |
| Total | 362 .57 | 362.57 | 842.75 | 2073.84 | 1244.84 | 1499.19 | 260.96 | 260.96 | 810.53 |
| Less: PSDF Grant |  |  | 400.78 | 389.58 | 389.58 | 0 | 0 | 0 | 0 |
|  | 362.57 | 362.57 | 441.97 | 1684.26 | 855.26 | 1499.19 | 260.96 | 260.96 | 810.53 |

8.16 SUMMARY OF GFA ADDITION OF SBU-T for 2019-20, 2020-21 & 2021-22

8.16.1	The summary of GFA addition of SBU-T for 2019-20, 2020-21 and 2021-22 are submitted below.

8.17		MID TERM PERFORMANCE REVIEW OF SBU-T FOR 2019-20, 2020-21 & 2021-22

8.17.1	INTEREST & FINANCE CHARGES

CAPITAL EXPENDITURE FOR 2019-20 UPTO SEPTEMBER 2019

8.17.1.1	The capital expenditure incurred by SBU-T up to September 2019 along with the capitalized amount is submitted below.

| Table 8.25 Capital outlay and GFA addition till 30.09.2019 (Rs Cr) |  |  |  |
| --- | --- | --- | --- |
| Sl. no. | Brief description of the work | Cost incurred | Capitalized |
| 1 | Electrical Transmission schemes | 156.12 | 52.66 |
| 2 | Power System Development Fund works | 50.51 | 0.20 |
| 3 | Load Despatch & Communication schemes | 1.79 | 2.41 |
| 4 | CWIP-General | 191.90 |  |
| 5 | TRANSGRID 2.0 project | 50.51 |  |
|  | Total | 450.56 | 55.26 |

8.17.1.2	The Interest & Finance charges actually incurred by SBU-T and SLDC for the year 2019-20 up to September 2019 are Rs. 50.59 Cr. The Interest & Finance charges approved for the year 2019-20 by Hon’ble Commission vide MYT order dated 8-7-2019, actual incurred upto September 2019 and revised Interest & Finance charges for the years 2019-20, 2020-21 and 2021-22for SBU-T & SLDC are submitted below. The revised Interest & Finance charges are arrived based on the opening loan, GFA addition during the year and normative repayment for the year, which is detailed under Chapter-11 of this petition.

| Table 8.26 Interest on capital liabilities for SBU-T & SLDC (Rs Cr ) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Item | Estimated in ARR | Approved vide order dtd.8-7-19 (2019-20) | Actual up to 30-9-19 | Revised estimate for 2019-20 | Approved for 2020-21 | Revised estimate for 2020-21 |  |  | Approved for 2021-22 | Revised estimate for 2021-22 |
| 1 | Average normative loan | 2579.89 | 1,999.99 | 1304.19 | 1,529.39 | 2849.43 |  | 2,984.52 | 3384.12 |  | 4,572.27 |  |
| 2 | Interest rate | 10% | 9.25% | 7.76% | 9.06% | 9.25% |  | 9.06% | 9.25% |  | 9.06% |  |
| 3 | Interest for the year | 257.99 | 185.05 | 50.59 | 138.56 | 263.65 |  | 270.40 | 313.12 |  | 414.25 |  |

8.17.1.3	In the original ARR petition, the Interest and Finance charges of SBU-T and SLDC were clubbed together. As part of segregating the accounts of SLDC, the Interest and Finance charges of SLDC for the years 2019-20 to 2021-22are worked out by segregating it from the I&F charges of SBU-T based on the GFA ratio of SLDC.

8.17.1.4	The GFA of SLDC for the years 2019-20 to 2021-22 is detailed under Chapter- 3: Mid Term Performance Review of SLDC.  A comparison of the GFA of SBU-T with the GFA of SLDC for the years 2019-20 to 2021-22 is submitted below.

| Table 8.27 GFA segregation (Rs Cr) |  |  |  |
| --- | --- | --- | --- |
| Item | 2019-20 | 2020-21 | 2021-22 |
| SBU-T |  |  |  |
| Opening GFA** (Rs.Cr.) | 5094.47 | 6425.07 | 8684.75 |
| SLDC |  |  |  |
| Opening GFA (Rs.Cr.) | 7.63 | 8.6 | 17 |
| Ratio of GFA of SLDC to total GFA of SBU-T & SLDC | 0.15% | 0.14% | 0.20% |

**incl  GFA of SLDC

8.17.1.5	The Interest and Finance charges of SBU-T for the years 2019-20 to 2021-22 after excluding the Interest and Finance Charges of SLDC are submitted below:

| Table 8.28 Interest on capital liabilities (Rs Cr ) for SBU-T |  |  |  |  |
| --- | --- | --- | --- | --- |
| No | Item | RE for 2019-20 | RE for 2020-21 | RE for 2021-22 |
| 1 | Interest & Finance charges for SBU-T & SLDC | 138.56 | 270.40 | 414.25 |
| 2 | GFA ratio of SLDC | 0.15% | 0.14% | 0.20% |
| 3 | Interest & Finance charges of SLDC | 0.21 | 0.38 | 0.84 |
|  | Interest & Finance charges for SBU-T | 138.35 | 270.02 | 413.41 |

8.17.2	Interest on security deposits

8.17.2.1	SBU-T does not hold any security deposit and hence no amount is assigned on this account.

8.17.3	Interest on GPF

8.17.3.1.	  The interest on GPF for SBU-T & SLDC for the years 2019-20, 2020-21 and 2021-22 are detailed in chapter 11. A summary is reproduced in the table below:

| Table 8.29 SBU-T & SLDC : Interest on provident fund (Rs Cr) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Item | Estimated in ARR | Approved (2019-20) | Actual up to 30-9-19 | Revised estimate for 2019-20 | Appvd. For 2020-21 | Revised estimate for 2020-21 | Appvd. For 2021-22 | Revised estimate for 2021-22 |
| 1 | Interest on PF | 23.12 | 22.03 | 7.58 | 20.68 | 23.39 | 22.04 | 24.74 | 23.40 |

8.17.3.2.	The projection of Interest on GPF for SLDC are segregated based on the ratio of employee cost for the year 2018-19 is as submitted below:

| Table 8.30 Segregation of Interest on PF for SBUT & SLDC (Rs.Cr.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| SBU |  | 2019-20 | 2020-21 | 2021-22 |
| SBU-T & SLDC | Employee cost ratio for 2018-19 | 20.68 | 22.04 | 23.40 |
| SLDC | 1.93% | 0.42 | 0.45 | 0.47 |

8.17.3.3.	The interest on GPF for SBU-T   for the years 2019-20, 2020-21 and 2021-22 after excluding the Interest on GPF of SLDC is submitted below.

| Table 8.31 SBU-T : Interest on provident fund (Rs Cr) |  |  |  |  |
| --- | --- | --- | --- | --- |
| No | Item | Revised estimate for 2019-20 | Revised estimate for 2020-21 | Revised estimate for 2021-22 |
| 1 | Interest on Provident fund (SBU-T & SLDC) | 20.26 | 21.59 | 22.93 |
| 2 | Interest on Provident fund (SLDC) | 0.42 | 0.45 | 0.47 |
| 3 | Interest on Provident fund (SBU-T ) | 20.68 | 22.04 | 23.40 |

8.17.4	Interest on Master Trust bonds

8.17.4.1	SBU wise interest on Master Trust Bond and interest is calculated in Chapter 11. The interest for SBU-T & SLDC is reproduced in the Table below. This includes the interest contribution of existing bonds as well as the interest on the additional liability to master trust based on actuarial valuation.

| Table 8.32 SBU-T & SLDC interest on Master Trust bonds (Rs Cr) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Item | Estimated in ARR | Approved (2019-20) | Actual up to 30-9-19 | Revised estimate for 2019-20 | Appvd. For 2020-21 | Revised estimate for 2020-21 | Appvd. For 2021-22 | Revised estimate for 2021-22 |
| 1 | Existing bond | 82.95 | 82.95 | 36.17 | 82.95 | 78.34 | 78.34 | 73.73 | 73.73 |
| 2 | Additional contribution to Master Trust | 42.20 | 22.64 | 0 | 22.64 | 22.64 | 22.64 | 22.64 | 22.64 |
|  | Total | 125.15 | 105.59 | 36.17 | 105.59 | 100.98 | 100.98 | 96.37 | 96.37 |

8.17.4.2.	The projection of Interest on Master Trust Bonds for SLDC are segregated based on the ratio of employee cost for the year 2018-19 is as submitted below:

| Table 8.33 Segregation of Interest on PF for SBUT & SLDC (Rs.Cr.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| SBU |  | 2019-20 | 2020-21 | 2021-22 |
| SBU-T & SLDC | Employee cost ratio for 2018-19 | 105.59 | 100.98 | 96.37 |
| SLDC | 1.93% | 2.04 | 1.95 | 1.86 |

8.17.4.3.	The projection of interest on Master Trust Bond for SBU-T   for the years 2019-20, 2020-21 and 2021-22 after excluding the Interest on Master Trust Bond of SLDC is submitted below.

| Table 8.34 SBU-T : Interest on Master Trust Bond (Rs Cr) |  |  |  |  |
| --- | --- | --- | --- | --- |
| No | Item | Revised estimate for 2019-20 | Revised estimate for 2020-21 | Revised estimate for 2021-22 |
| 1 | Interest on Master Trust Bond (SBU-T & SLDC) | 105.59 | 100.98 | 96.37 |
| 2 | Interest on Master Trust Bond (SLDC) | 2.04 | 1.95 | 1.86 |
| 3 | Interest on Master Trust Bond (SBU-T ) | 103.55 | 99.03 | 94.51 |

8.17.5	Interest on Working Capital

8.17.5.1	The working capital for SBU-T  comprise of, as per Regulation 32, one month O&M cost, cost of maintenance spares at 1% historical cost and receivables for one month less security deposit held, if any.  The interest rate allowed, as per Regulation 32(2), is 2% higher than the Base rate on First of April of the ARR filing Year.  Therefore the Interest on Working Capital in this petition is computed at a rate of 10.95% (8.95% as on 1-4-2019 + 2%).

The parameters adopted for computation of Interest on Working capital for the years 2019-20, 2020-21 and 2021-22 are given below:

| Table 8.35 Parameters for Working Capital (Rs Cr) |  |  |  |
| --- | --- | --- | --- |
| Item | 2019-20 | 2020-21 | 2021-22 |
| Opening GFA of SBU-T & SLDC | 5094.47 | 6425.07 | 8684.75 |
| Normative O&M Cost | 390.83 | 440.48 | 496.30 |

*8.17.5.2	The Interest on Working Capital estimated in ARR for the year 2019-20, approved by Hon’ble Commission, actual for the period up to September 2019 and the revised estimate for the year 2019-20, 2020-21 and 2021-22 are given below.

| Table 8.36 SBU-T& SLDC :Interest on Working capital (Rs Cr) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Item | Estimated in ARR | Approved (2019-20) | Actual up to Sept-19 | Revised for the year 19-20 | Appvd. For 20-21 | Revised for the year 20-21 | Appvd. For 21-22 | Revised for the year 21-22 |
| 1 | O&M Expenses | 363.23 | 397.46 |  | 390.83 | 452.88 | 440.48 | 491.28 | 496.30 |
| 2 | GFA Plants and Equipment |  | 5,637.86 |  | 5094.47 | 6719.97 | 6425.07 | 8147.73 | 8684.75 |
| 3 | Transmission charges |  | 983.69 |  | 934.54 | 1162.47 | 1166.68 | 1283.53 | 1431.94 |
| 4 | O&M Expenses for one month | 31.52 | 33.12 |  | 32.57 | 37.74 | 36.71 | 40.94 | 41.36 |
| 5 | 1% of Historical cost of plants & Equipment | 61.22 | 56.38 |  | 50.94 | 67.20 | 64.25 | 81.48 | 86.85 |
| 6 | Receivables (Transmission charges for one month) | 92.18 | 81.97 |  | 77.88 | 96.87 | 97.22 | 106.96 | 119.33 |
| 7 | Total requirement of working capital | 184.92 | 171.47 |  | 161.39 | 201.81 | 198.18 | 229.38 | 247.53 |
| 8 | Rate of interest | 10.70% | 10.15% |  | 10.95% | 10.15% | 10.95% | 10.15% | 10.95% |
| 9 | Interest on working capital | 19.79 | 17.40 | 9.55 | 21.70 | 20.48 | 23.28 | 23.28 | 27.10 |

8.17.5.3	The projection of Interest on Working capital for SLDC for the years 2019-20, 2020-21 and 2021-22 is submitted below.

| Table 8.37 SLDC :Interest on Working capital (Rs Cr) |  |  |  |  |
| --- | --- | --- | --- | --- |
| No | Item | Revised for 2019-20 | Revised for 2020-21 | Revised for 2021-22 |
| 1 | Interest on working capital | 0.20 | 0.23 | 0.27 |

8.17.5.4	The projection of interest on Working Capital for SBU-T   for the years 2019-20, 2020-21 and 2021-22 after excluding the Interest on Working Capital of SLDC is submitted below.

| Table 8.38 SBU-T : Revised Interest on Working capital (Rs Cr) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No | Item | 2019-20 | 2020-21 | 2021-22 |
| 1 | Interest on working capital of SBU-T & SLDC | 21.70 | 23.28 | 27.10 |
| 2 | Interest on working capital of SLDC | 0.20 | 0.23 | 0.27 |
| 3 | Interest on working capital of SBU-T | 21.50 | 23.05 | 26.83 |

8.17.6	DEPRECIATION

8.17.6.1.	The Depreciation of SBU-T for the year 2019-20 up to September 2019 is Rs. 68.10 Cr as submitted below.  The details are furnished under form-T3. The methodology for calculation of depreciation is detailed under Chapter-11.  The Depreciation approved for the year 2019-20 by Hon’ble Commission vide MYT order dated 8-7-2019, actual incurred up to September 2019 and revised Depreciation for the years 2019-20,2020-21 and 2021-22 are submitted below.

| Table 8.39 Depreciation for SBU-T & SLDC (Rs.Cr.) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Item | Estimated in ARR | Approved (2019-20) | Actual Sept-19 | Revised estimate for 19-20 | Appvd. For 20-21 | Revised estimate for 20-21 | Appvd. For 21-22 | Revised estimate for 21-22 |
| Depreciation allowable for SBU-T & SLDC | 199.58 | 173.47 | 68.10 | 193.78 | 222.92 | 255.10 | 261.09 | 313.17 |

8.17.6.2.	The segregation of Depreciation for SLDC for the years 2019-20, 2020-21 and 2021-22 is based on GFA ratio of SLDC and an abstract of the same is submitted below.

| Table 8.40 SLDC :Depreciation (Rs Cr) |  |  |  |  |
| --- | --- | --- | --- | --- |
| No | Item | Revised for 2019-20 | Revised for 2020-21 | Revised for 2021-22 |
| 1 | Depreciation of SLDC | 0.28 | 0.34 | 0.60 |

8.17.6.3	The projection of Depreciation for SBU-T   for the years 2019-20, 2020-21 and 2021-22 after excluding Depreciation of SLDC is submitted below.

| Table 8.42 SBU-T :Revised Depreciation (Rs Cr) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No | Item | 2019-20 | 2020-21 | 2021-22 |
| 1 | Depreciation of SBU-T & SLDC | 193.78 | 255.10 | 313.17 |
| 2 | Depreciation of SLDC | 0.28 | 0.34 | 0.60 |
| 3 | Depreciation of SBU-T | 193.50 | 254.76 | 312.57 |

8.17.7.		O&M EXPENSES

8.17.7.1	The norms for O&M, number of bays and line length in ckt-km for 66KV and above projected for the years 2019-20, 2020-21 and 2021-22 considering the capital addition planned for these years are submitted below.

|  |  |  | Table 8.43 Normative O&M norms for SBU-T & SLDC (Rs.Cr.) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Item |  |  | Estimated in ARR | Approved (2019-20) | Actual up to 30-9-19 | Revised estimate for 19-20 | Appvd. For 2020-21 | Revised estimate for 20-21 | Appvd. For 2021-22 | Revised estimate for 21-22 |
| 1 | O&M cost for Bay (Rslakh/Bay) |  |  | 11.23 | 11.23 |  | 11.23 | 11.77 | 11.77 | 12.34 | 12.34 |
| 2 | O&M cost (Rslakh/circuit km) |  |  | 0.98 | 0.98 |  | 0.98 | 1.03 | 1.03 | 1.08 | 1.08 |
| 3 | Bays (No.) (for Previous year) |  |  | 2682 | 2682 |  | 2635 | 2914 | 2803.5 | 3007 | 3008.5 |
| 4 | Line (Ckt-Km)(for previous year) |  |  | 9823.195 | 9823.20 |  | 9685.989 | 10670.15 | 10728.69 | 11130.965 | 11578.95 |
| 5 | Normative O&M cost (Rs.Cr.) |  |  | 397.46 | 397.46 | 256.40 | 390.83 | 452.88 | 440.48 | 491.28 | 496.30 |

The details are furnished under T-2 of the Transmission tariff forms attached.

8.17.7.2.	The projection of O&M expenses for SLDC for the years 2019-20, 2020-21 and 2021-22 is based on the methodology detailed under Chapter-3 (ARR of SLDC) and an abstract of the same is submitted below.

| Table 8.44 SLDC : O&M (Rs Cr) |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Revised for 2019-20 | Revised for 2020-21 | Revised for 2021-22 |
| No | Item | (Rs.Cr.) | (Rs.Cr.) | (Rs.Cr.) |
| 1 | O&M of SLDC | 9.96 | 11.77 | 12.89 |

8.17.7.3	The projection of O&M for SBU-T   for the years 2019-20, 2020-21 and 2021-22 after excluding O&M of SLDC is submitted below.

| Table 8.45 SBU-T :Revised Normative O&M (Rs Cr) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No | Item | 2019-20 | 2020-21 | 2021-22 |
| 1 | O&M of SBU-T & SLDC | 390.83 | 440.48 | 496.30 |
| 2 | O&M of SLDC | 9.96 | 11.77 | 12.89 |
| 3 | O&M of SBU-T | 380.87 | 428.71 | 483.41 |

Pay Revision Expenses

8.17.7.4	SBU-T is not claiming pay revision expenses along with this ARR petition. However, it is requested that pay revision expenses as and when arising in the control period may be allowed over and above the norms in line with Kerala State Electricity Regulatory Commission (Terms and Conditions for Determination of Tariff) Regulations, 2018. Details are furnished in chapter 11. An estimate of pay revision expenses of SBU-T and SLDC are submitted below.

| Table 8.46 Pay revision expenses of SBU-T & SLDC (Rs.Cr.) |  |  |  |
| --- | --- | --- | --- |
| Business Unit | 2019-20 | 2020-21 | 2021-22 |
| SBU T | 29.78 | 32.18 | 34.71 |

8.17.7.5	A projection of the O&M expenses of SBU-T based on actual of past years are given in the Table below. The figures shown are excluding the pay revision expenses and contribution to Master Trust. It is seen that the O&M expenses allowed as per norms for the control period are below the actual and may lead to under recovery of cost.

| Table 8.47 O&M Projection based on past actuals (Rs Cr) |  |  |  |  |
| --- | --- | --- | --- | --- |
| O&M Cost | Actual for 2018-19 | 2019-20 | 2020-21 | 2021-22 |
| SBU-T | 490.51 | 524.85 | 561.58 | 600.90 |

The details are included in Form-T2 of the Transmission tariff sheets.

8.17.7.6	In the matter of O&M of SBU-T, Hon Commission may please note that the CERC norms (Regulation 35(3) (a) of CERC (T&C of Tariff) Regulations, 2019) for the above drivers are Rs. 17.69Lakh per bay (weighted average of 220KV & 132 KV and below), Rs.0.24125 lakh/MVA(weighted average of 220KV & 132 KV and below),  and 0.377 for (Double Circuit single conductor) lines for 2019-20. Applying these norms, the normative O&M cost will be Rs.553.94 Cr for 2019-20, against which the norms this Hon’ble Commission allowed only Rs.397.46 Cr.    Therefore, it is submitted that the O&M norms allowed for SBU-T is much lower than CERC allowed benchmark costs. At the same time KSEB Ltd. is taking earnest efforts to control the O&M expenses during the control period and the same will be submitted along with truing up petition. Accordingly, it is requested that since projection based on actual O&M of SBU-T is lower than benchmark CERC norms, actual O&M cost incurred may be allowed during the truing up process if it increases above the norms of this Hon’ble Commission.

8.17.8.		RETURN ON EQUITY

8.17.8.1.	The ROE for SBU-T (including SLDC) claimed, approved and revised estimate for 2019-20, 2020-21 and 2021-22 are submitted below. This ROE is apportioned to SLDC based on GFA ratio as submitted below.

| Table 8.48 ROE (Rs.Cr.) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Item | Estimated in ARR | Approved (2019-20) | Actual up to 30-9-19 | Revised estimate for 19-20 | Appvd. For 20-21 | Revised estimate for 20-21 | Appvd. For 21-22 | Revised estimate for21-22 |
| 1 | RoE of SBU-T & SLDC | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 |
| 2 | RoE of SLDC (based on GFA ratio) |  |  |  | 0.18 |  | 0.17 |  | 0.24 |
| 3 | RoE of SBU-T |  |  |  | 119.81 |  | 119.82 |  | 119.75 |

8.18	Aggregate Revenue Requirement of SBU-T & SLDC

8.18.1.	The SBU-T handles the transmission assets of KSEB Ltd and manages bulk transmission of power within the State for supply to SBU-D. SBU-T as an independent business unit, the cost is recovered as transfer cost from SBU-D as intra-state transmission charges. The total Aggregate Revenue Requirement of SBU-T and SLDC claimed in the original petition, approved, actual up to Sept- 2019 and revised estimate for the years 2019-20, 2020-21 and 2021-22 are submitted below:

| Table 8.49 ARR of SBU-T (Rs.Cr) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Item | Estimated in ARR | Appvd. (2019-20) | Actual upto Sept 2019 | Revised estimate for 2019-20 | Appvd. For 2020-21 | Revised estimate for 2020-21 | Appvd. For 2021-22 | Revised estimate for 2021-22 |
| 1 | Operation & Maintenance Expenses | 397.46 | 397.46 | 256.4 | 390.83 | 452.88 | 440.48 | 491.28 | 496.30 |
| 2 | Interest and finance charges | 257.99 | 185.05 | 50.59 | 138.56 | 263.65 | 270.40 | 313.12 | 414.25 |
| 3 | Interest on Bonds and additional contribution | 125.15 | 105.59 | 36.17 | 105.59 | 100.98 | 100.98 | 96.37 | 96.37 |
| 4 | GPF Interest | 23.12 | 22.03 | 9.55 | 20.68 | 23.39 | 22.04 | 24.74 | 23.40 |
| 5 | Depreciation | 199.58 | 173.47 | 123.3 | 193.78 | 222.92 | 255.10 | 261.09 | 313.17 |
| 6 | Interest on WC and deposits | 20.2 | 17.4 | 9.55 | 21.70 | 20.48 | 23.28 | 23.28 | 27.10 |
| 7 | Other items |  |  | 1.17 |  |  |  |  |  |
| 8 | Total Revenue Expenditure | 1023.5 | 901 | 469.6 | 871.15 | 1084.30 | 1112.28 | 1209.89 | 1370.59 |
| 10 | Return on Equity | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 |
| 11 | Aggregate Revenue Requirement (10+11+12) of SBU-T & SLDC | 1143.49 | 1,020.99 | 589.59 | 991.14 | 1204.29 | 1232.27 | 1329.88 | 1490.58 |
| 12 | Aggregate requirement of SLDC |  |  |  | 13.30 |  | 15.28 |  | 17.17 |
| 13 | Aggregate requirement of SBU-T excl SLDC |  |  |  | 977.84 |  | 1216.99 |  | 1473.42 |

8.19	Non-Tariff Income for SBU-T

8.19.1.	The non-tariff income of SBU-T includes income from sale of scrap, interest on advances made to contractors, interest on staff loans and advances, Rent from buildings etc. The projection of Non-Tariff income of SBU-T for the control period is given below.

| Table 8.50 Non Tariff Income of SBU-T (Rs.Cr.) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Other Income (Rs.Cr.) | Estimated in ARR | Appd (2019-20) | Actual upto Sept 2019 | Revised estimate for 2019-20 | Appvd. For 2020-21 | Revised estimate for 2020-21 | Appvd. For 2021-22 | Revised estimate for 2021-22 |
| 1 | Interest on staff loans and advances | 0.02 |  | 0.00 | 0.02 | 0.02 | 0.02 | 0.03 | 0.03 |
| 2 | Income from statutory investments | 0 |  | 0.00 | 0 | 0 | 0 | 0 | 0 |
| 3 | Income from rent of land or buildings | 0.5 |  | 0.07 | 0.5 | 0.52 | 0.52 | 0.55 | 0.55 |
| 4 | Income from sale of scrap | 2.87 |  | 7.51 | 2.87 | 3.01 | 3.01 | 3.17 | 3.17 |
| 5 | Income from staff welfare activities | 0 |  |  | 0 | 0 | 0 | 0 | 0 |
| 6 | Rental from staff quarters | 0.12 |  | 0.04 | 0.12 | 0.12 | 0.12 | 0.13 | 0.13 |
| 7 | Excess found on physical verification | 0.03 |  | 0.00 | 0.03 | 0.04 | 0.04 | 0.04 | 0.04 |
| 8 | Interest on investments, fixed and call deposits and bank balances | 0.05 |  | 0.09 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |
| 9 | Interest on advances to suppliers/contractors | 0.05 |  | 0.12 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |
| 10 | Income from hire charges from contractors and others | 0 |  | 0.00 | 0 | 0 | 0 | 0 | 0 |
| 11 | Income fromfibre optic cables/co-axial cables on transmission system | 3.9 |  |  | 3.9 | 4.49 | 4.49 | 5.07 | 5.07 |
| 12 | Income from advertisements, etc. | 0 |  |  | 0 | 0 | 0 | 0 | 0 |
| 13 | Miscellaneous receipts | 29.76 |  | 12.20 | 29.76 | 33.52 | 33.52 | 37.26 | 37.26 |
|  | Total Other Income (Rs.Cr.) | 37.3 | 37.30 | 20.02 | 37.30 | 41.82 | 41.82 | 46.35 | 46.35 |

8.20	Net ARR of SBU-T

8.20.1 The net ARR of SBU-T and SLDC for the years 2019-20, 2020-21 and 2021-22 are submitted below.

| Table 8.51 Net ARR for SBU-T & SLDC (Rs.Cr.) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Item |  |  |  |  |  |  |  |  |
|  |  | Estimated in ARR | Appd (2019-20) | Actual upto Sept 2019 | Revised estimate for 2019-20 | Appvd. For 2020-21 | Revised estimate for 2020-21 | Appvd. For 2021-22 | Revised estimate for 2021-22 |
| 1 | Aggregate Revenue Requirement | 1143.49 | 1,020.99 | 589.59 | 991.14 | 1204.29 | 1232.27 | 1329.88 | 1490.58 |
| 2 | Less: Other Income | 37.30 | 37.30 | 20.02 | 37.30 | 41.82 | 41.82 | 46.35 | 46.35 |
| 3 | Less: Revenue from Open Access |  |  |  |  |  |  |  |  |
| 4 | Less: Income from Other Business |  |  |  |  |  |  |  |  |
| 5 | ARR from Transmission Tariff | 1106.19 | 983.69 | 569.57 | 953.84 | 1162.47 | 1190.45 | 1283.53 | 1444.24 |

8.21	Norms for Operation for the years 2019-20 to 2021-22

Transmission System Availability

8.21.1	The availability of transmission system projected for the years2019-20 to 2021-22 is 98%. It is humbly requested that relaxation may be allowed to KSEBL from meeting the availability norms during shutdown works carried out at the time of execution of ‘TRANSGRID WORKS’.

8.22	Transmission losses

8.22.1.	 A projection of the transmission loss of SBU-T based on the capital addition for the years 2019-20  to 2021-22 is submitted below.

| Table 8.52 Transmission Losses (%) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Estimated in ARR for 2019-20 | Appvd. For 2019-20 | Revised 2019-20 | Appvd. For 2020-21 | Revised 2020-21 | Appvd. For 2021-22 | Revised 2021-22 |
|  | Transmission loss up to 66KV | 3.95 | 3.95 | 3.65 | 3.85 | 3.55 | 3.75 | 3.45 |
| Note: The figures show the losses up to the respective voltage level (%) |  |  |  |  |  |  |  |  |  |

8.23	Transmission charges for 2019-20, 2020-21 & 2021-22

8.23.1	SBU-T handles the energy flow to the entire consumers of SBU-D as well as open access consumers. The projection of the energy input to the Transmission network, energy handled, transmission losses and the transmission charges estimated for the years 2020-21 to 2021-22 are submitted below. Transmission charges in Rs/MW/day are calculated assuming a system load factor of 72%.

| Table 8.53 Transmission Charges |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019-20 |  |  | 2020-21 |  | 2021-22 |  |
| No | Item | Estimated in ARR | Appvd. | Revised | Estimated in ARR | Revised | Estimated in ARR | Revised |
| 1 | Energy injected into the system (MU) | 26243.43 | 26243.43 | 26135.55 | 27247.53 | 26867.86 | 28295.30 | 27830.35 |
| 2 | Percentage of loss (%) | 3.95 | 3.95 | 3.65 | 3.85 | 3.55 | 3.75 | 3.45 |
| 3 | Loss of energy (MU) | 1036.62 | 1036.62 | 953.95 | 1049.03 | 955.81 | 1061.07 | 960.15 |
| 4 | Auxiliary consumption (MU) |  | 16.36 | 16.92 |  | 17.76 |  | 18.65 |
| 5 | Energy handled (MU) (1-3) | 25206.81 | 25190.46 | 25164.68 | 26198.50 | 25896.29 | 27234.23 | 26851.55 |
| 6 | Transmission ARR (Rs.Cr.) | 1106.19 | 983.69 | 953.84 | 1394.26 | 1190.45 | 1637.13 | 1444.24 |
| 7 | Transmission Charges (Rs./unit) | 0.44 | 0.39 | 0.38 | 0.53 | 0.46 | 0.60 | 0.54 |
| 8 | Peak demand projection | 4175 | 4300 | 4369 | 4384 | 4500 | 4517 | 4635 |
| 9 | Transmission Charges STOA (Rs/MW/day) | 10082 | 8705 | 8281 | 12102 | 10063 | 13791 | 11902 |
| 10 | LTA/MTOA Transmission Charges (Rs/MW/month or part thereof) | 306662 |  |  | 368095 | 301890 | 419489 | 357060 |

| Appendix- 1 : Ongoing and New Works less than Rs.10Cr(Status as on 30-9-2019) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | As per ARR |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Acheivement |  |  |  |  |  |  |  |
|  | Project | Project Cost * | Commencement | Completion | 2018-19 |  | Actual /Revised Project cost | Actual Commencement | Actual/ Revised Completion | Actual achievement in 2018-19 |  | Status up to Sept-2019 |  |  |
|  |  |  |  |  | Physical | Financial |  |  |  | Physical | Financial | Physical | Financial |  |
|  |  | Rs Cr |  |  | (%) | Rs Cr | Rs Cr |  |  | (%) | Rs Cr | (%) | Rs Cr |  |
| Circle - Kottarakkara |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Karunagapalli SS &Sasthamkotta TL Upgrdn to 110 | 16.5 | 4/19/2017 | 2018-19 | 15 | 0.57 | 16.5 | 19.04.17 | 30-Apr-20 | 27 | 1.92 | 27 | 1.92 |  |
| 2 | Anchal 66kV SS of &Ayoor TL Upgdn to 110kV | 13 | 5/15/2017 | 2018-19 | 14 | 0.03 | 32.2 | 15.5.17 | 31-Dec-19 | 31 | 7.50 | 100 | 32.20 |  |
| 3 | Ayoor 66kV SS Upgradation | 7.3 | 10/11/16 | 2018-19 | 24 | 0.188 | 7.3 | 10.11.2016 | 31-Mar-20 | 34 | 0.87 | 100 | 7.30 |  |
|  | SubTotal - Ongoing | 36.8 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SubTotal - New |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Circle - Alappuzha |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Eramalloor 110 kV SS & LILO | 11.3 | Jul-17 | 2018-19 | 46 | 3.81 | 10.93 | 17-Jul | 19-Jun | 98 | 10.12 | 100 | 10.93 |  |
| 2 | Kattanam 33kV SS Upgradation to 66 kV | 11.8 | 1/9/2017 | 2018-19 | SS-19/ TL- 1 | 0.71 | 11.8 | 17-Sep | 19-Nov | 80 | 5.82 | 100 | 11.80 |  |
| 3 | Alappuzha 110 kV SS | 30.9 | Sept. 2017 | 2019-20 | 1 | 0.27 | 30.9 | 17-Sep | 20-Dec | 0 | 0.00 | 0 | 0.44 |  |
| 4 | Capacity Enhancement of 220 kV SS Punnapra | 6 | Aug-17 | 2018-19 | 85 | 2.4 | 4 | 17-Aug | 18-Nov | 100 | 4.00 | 100 | 4.00 |  |
| 5 | Kalarcode 33kV Substation &Punnapra TL | 5.8 | 2017-18 | 2018-19 | 0.8 | 4.64 | 5.8 | 17-Aug | 19-Nov | 80 | 2.01 | 100 | 5.80 |  |
| 6 | Mattancherry bay extension work | 1 | 2017-18 | 2018-19 | 0.8 | 0.8 | 0.24 | 18-Feb | 19-Nov | 90 | 0.03 | 100 | 0.24 |  |
| 7 | Edathua 110/33kV 16MVA T/F at 110kV SS. | 2 | 2017-18 | 2018-19 | 0.8 | 1.6 | 1.43 | 18-Nov | 19-Feb | 100 | 1.43 | 100 | 1.43 |  |
| 8 | Edappon 220kV SS-110/33kV 16MVA TF | 2.787 | 2017-18 | 2018-19 | 0.8 | 2.2296 | 1.67 | 17-Apr | 19-Feb | 100 | 1.67 | 100 | 1.67 |  |
| 9 | Vallikunnam 33 kV SS - 33kV bay & 5MVA TF | 1 | 2017-18 | 2018-19 | 0.8 | 0.8 | 0.83 | 17-Mar | 18-Dec | 100 | 0.83 | 100 | 0.83 |  |
| 10 | Aroor 110kV SS- 20MVA TF | 2.613 | 2017-18 | 2018-19 | 0.8 | 2.0904 | 2.9 | 18-Feb | 18-Sep | 100 | 1.75 | 100 | 2.90 |  |
|  | New work |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 | Upgradation of Edappon - Mavelikkara 66kV DC feeder to 110kV DC |  |  |  |  |  | 9.34 |  |  |  |  |  |  |  |
|  | SubTotal - Ongoing | 75.2 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SubTotal - New |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Circle - Poovanthuruthu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Erumely 110 kV SS & DC TL (REC Loan) (TL Comptd) | 18.12 | 2/2/2006 | 2019-20 | SS-99 | 16.994 | 18.12 | 02.02.2006 | 09.11.2018 | 100 | 17.61 | 100 | 17.71 |  |
| 2 | 33 kV SS Manimala& TL to Ranni (REC Loan) | 8.75 | 7/21/2011 | 5/27/2018 | 100 | 6.2488 | 8.75 | 21.07.2011 | 27.05.2017 | 100 | 6.28 | 100 | 6.29 |  |
| 3 | 33 kV SS Kallara& Line (SS& TL Commissioned) | 5.16 | 5/20/2013 | 4/18/2018 | 100 | 4.3717 | 5.16 | 20.05.2013 | 18.03.2017 | 98 | 5.03 | 98 | 5.05 |  |
| 4 | Upgradation of 110 kV SS Kanjirappally (2nd Phase) | 8.9 | 3/25/2015 | 2019-20 | 94 | 8.01 | 8.9 | 25.03.2015 | 15.02.2017 | 100 | 8.01 | 100 | 8.01 |  |
| 5 | Puthupally 110 kV SS & LILO of Pallom – Pampady | 8.1 | 2018-19 | 2019-20 | 0 | 3.02 | 8.1 | 19.06.2015 | 31.03.2022 | 0 | 3.02 | 0 | 3.27 |  |
| 6 | 110 kV feeder bay at 220kV S/S, Pallom | 2.9 | 1/3/2017 | 2019-20 | 19 | 0.45 | 2.9 | 01.03.2017 | 29.06.2019 | 51.98 | 0.63 | 100 | 0.76 |  |
| 7 | Mundakkayam 66 KV SS &Kanjirappally TL Upgdn | 17.4 | 7/11/2016 | 2018-19 | 75 / 51 | 1.77 | 6.3 | 5.01.2018 | 08.11.2018 | 100 | 2.50 | 100 | 2.48 |  |
| 8 | Pala 110kV SS - 110kV feeder bay | 2.75 | 2017-18 | 2019-20 | 0 | 0 | 2.75 | 26.07.2018 | 31.03.2020 | 0 | 0.00 | 0 | 0.00 |  |
| 9 | Kanjirappally 110 KV SS – 2 feeder bays | 0.39 | 2017-18 | 10/31/2018 | 73 | 0.3268 | 0.39 | 15.02.2017 | 10.11.2018 | 100 | 0.39 |  |  |  |
| 10 | Mundakkayam 66kV SS Upgdn to 110kV | 11.1 | 2017-18 | 2019-20 | 93 | 0.3268 | 11.1 | 07.11.2016 | 09.10.2019 | 99 | 3.62 | 99 | 4.06 |  |
| 11 | Pallom 220 kV SS - 1X110kV Feeder Bay | 5.8 | 2017-18 | 2019-20 | 23.5 | 0.3268 | 2.9 | 10.01.2014 | 20.02.2015 | 100 | 2.85 | 100 | 2.85 |  |
| 12 | Construction of 4 nos 110 kV feeder bays at Vaikom substation | 5.3 | 2019-20 | 2020-21 | 0 | 0 | 5.3 | 26.06.2019 | 31.3.2021 | 0 | 0.00 | 0 | 0.00 |  |
|  | SubTotal -Ongoing | 89.37 |  |  |  |  |  |  |  |  | 3.24 |  |  |  |
|  | SubTotal -New |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Circle - Thodupuzha |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Kumily 33kV SS and TL fmVandiperiyar DDUGJY | 6.5 | 12/28/2015 | 2020-21 | 53 | 1.63 |  |  |  | 100 | 3.00 |  |  |  |
| 2 | Muttom 110 kV SS | 6 | 5/23/2016 | 2018-19 | 98 | 3.73 |  |  |  | 100 | 2.00 |  |  |  |
| 3 | Adimaly 110 kV SS Capacity Enhancement | 2 | Feb. 2017 | 2018-19 | 97 | 0.16 |  |  |  | 80 | 0.50 | 100 | 0.80 |  |
| 4 | Kulamavu 66 kV SS Renovation | 1 | 8/17/2015 | 2019-20 | 30 | 0.41 |  |  |  | 100 | 0.80 |  |  |  |
| 5 | Marady 110 kV SS & LILO | 12 | 9/5/2016 | 2021-22 | 97 | 5.67 |  |  |  | 100 | 2.00 |  |  |  |
| 6 | Odakkali 66 kV SS in 110 kV Std& LILO | 10 | 3/5/2017 | 2019-20 | 96 | 2.15 |  |  |  | 100 | 3.00 |  |  |  |
| 7 | Rayonpuram 110 kV SS CaptyEnht& 33 kV DC TL | 3 | 1/25/2017 | 2018-19 | 100 / 40 | 1.86 |  |  |  | 40 | 0.10 | 40 | 0.10 |  |
| 8 | Kuruppanpady 110 kV SS Cap Enht,CR& TL DDUGJY | 2 | 6/18/2017 | 2019-20 | 40 | 0.02 |  |  |  | 100 | 1.60 |  |  |  |
| 9 | Koovappady 33kV SS - CR Ext & feeders (DDUGJY) | 1 | 9/27/2016 | 2018-19 | 70 | 0.27 |  |  |  | 100 | 0.80 |  |  |  |
| 10 | Mazhuvannoor 33kV SS – CR EXT &feedersDDUGJY | 1 | 9/27/2016 | 2018-19 | 50 | 0.27 |  |  |  | 100 | 0.80 |  |  |  |
| 11 | Vandanmedu 33kV SS & SC TL to – Vandanmed | 6 | 6/5/2017 | 2019-20 | 10 | 0.35 |  |  |  | 60 | 1.00 | 90 | 2.00 |  |
| 12 | Pallivasal Extension HEP - 220 kV SC line | 1 | 2018-19 | 2019-20 | 0.01 | 0.01 |  |  |  | 1 | 0.00 | 1 | 0.02 |  |
| 13 | Kothamangalam – B’kettu 66 kV TL Upgrdn | 10 | 5/30/2017 | 2019-20 | 79 | 0.87 |  |  |  | 100 | 3.00 |  |  |  |
|  | SubTotal - Ongoing | 61.5 |  |  |  |  |  |  |  |  | 17.00 |  |  |  |
| 1 | 33 kV Substation Vandanmedu and &33 kV SC line Nedumkandom to Vandanmedu | 6 | 05.06.2017 | 2020-21 | 100 | 4.9 |  |  |  | 60 | 1.00 | 90 | 2.00 |  |
| 2 | 110 kV Substation Murickassery and 110 kV NeriyamangalamKuthunkal feeder | 9 | 04.06.2018 | 2021-22 | 4 | 0.05 |  |  |  | 1 | 0.01 | 5 | 0.03 |  |
|  | Sub-Total New | 15 |  |  |  |  |  |  |  |  |  |  |  |  |
| Circle - Thrissur |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Madakathara SS - 200 kV Bus Enhancement PSDF | 2.9 | 8/11/2016 | 29.9.2018 | 100 | 2.24 |  |  |  | 100 | 2.90 |  |  |  |
| 2 | Madakathara 400 kV SS - 200 MVA, Transformer | 12.1 | 02.10.2016 | 17.01.2019 | Completed | 8.16 |  |  |  | 100 | 12.10 |  |  |  |
| 3 | Madakathara 400 kV SS - Setting up of 220kV feeder bay (Malapparambu 1&2) |  |  |  |  |  | 1.62 | 26.2.2019 | 25.08.2019 |  |  | Completed | 0.17 |  |
| 4 | Madakathara 400 kV SS - Providing spare arrangement to 3rd bank |  |  |  |  |  | 1.4 | 06.03.2019 | 31.12.2019 |  |  | 22 | 0.11 |  |
| 5 | Replacement of 220kV high impedance bus bar protection with low impedance bus bar protection. |  |  |  |  |  | 1.2 | 06.08.2019 | 05.02.2020 |  |  | - | - |  |
| 6 | Chalkdy - Kodungallur DC to 110 kV Upgrdn-IPDS | 6.5 |  |  | 45 | 2.925 | 6.5 | 27.3.18 | 31.08.2019 | 86 | 3.92 | 100 | 4.64 |  |
| 7 | Chalakkudy - Kodungallur TL to 110 kV DC & Bays | 1.9 |  |  | SS –78 | 0.994 | 1.9 | 03.7.2018 | 20.8.2019 | 91 | 1.69 | 100 | 1.74 |  |
| 8 | Mala 66 KV SS - Upgdn to 110 kV | 5.25 | 2017-18 | 2018-19 | 48 | 2.52 | 5.25 | 17.10.2017 | 29.2.2020 | 55 | 1.35 | 98 | 2.81 |  |
| 9 | Malayattoor SS – Bays & 110kV SC TL to DC | 21.3 | 2015-16 |  | 13 | 2.1 | 21.3 | Line-06.5.2017& SS-22.3.18 | SS-18.7.2019& Line 30.4.2020 | ss-79 &Line-23 | ss-1.43, Line-1.3187 | ss-100, Line- 42 | ss - 1.7382 & Line -3.17 |  |
| 10 | Karukutty 66kV SS - CB, C&R Panels, Etc& LILO | 1.86 |  | 2019-20 |  |  | 1.86 | 10.6.2019 | 29.2.2019 | Nil | 0.00 | 16 | 0.00 |  |
| 11 | Koratty 33kV SS - control room | 0.5 |  | 2019-20 |  |  | 0.5 | 18.12.2017 | 31.8.19 | 26 | 0.21 | 100 | 0.00 |  |
| 12 | Chalakudy 110KV SS - DP shifting (A) | 0.084 | 2017-18 | 2018-19 | 50 | 0.042 | 0.084 | 14.11.2018 | 15.6.2019 | 50 | 0.00 | 100 | 0.08 |  |
|  | Chalakudy 110KV SS - Shifting of 33,11and LT lines (B) | 0.34 | 2017-18 | 2018-19 | 50 | 0.170 | 0.15 | 1.10.2018 | 31.1.2019 | 50 | 0.00 | 100 | 0.15 |  |
|  | Chalakudy 110 SS – 110 kV Cable Laying (C) | 3.8 | 2017-18 | 2018-19 | 50 | 1.900 | 3.8 | 16.4.2018 | 15.7.2019 | 95 | 0.00 | 100 | 3.70 |  |
|  | Chalakudy 110Kv Ss Rearranging water line (D) | 0.012 | 2017-18 | 2018-19 | 50 | 0.006 | 0.0064 | 11.12.2018 | 17.12.2018 | 100 | 0.01 |  |  |  |
| 13 | Valapad – Kandassankadavu 110 kV DC Line | 4.1 | 6/24/2016 | 8/31/2017 | 100 | 4.1 |  |  | Work completed on 14.06.2018 | 100 | 4.10 |  |  |  |
| 14 | Kodungallur 66 KV SS Upgdn to 110 kV |  |  |  |  |  | 9.5 | 17.10.2018 | SS UPGRDRD to 24.08.2019 | 20 | 3.00 | 80 | 6.00 |  |
| 15 | Irinjalakuda 110kV SS - Cap Enht | 3.5 | 2017-18 | 2018-19 | 50 | 1.75 |  |  | Trfr 1 charged on 12.12.2018 | 100 | 3.50 |  |  |  |
| 16 | Valapad 110 kV SS– Capacity enhancement | 1.62 | 9/30/2017 | 2018-19 | 99 | 1.6038 |  |  |  |  |  |  |  |  |
| 17 | Pudukkad - Kattoor TL upgr to 110kV (HC Case) | 11.2 |  | 2020-21 |  |  |  |  |  |  |  |  |  |  |
| 18 | Blangad&Punna (Chavkd) 33kV SS– Blangad TL | 7.04 | 9/30/2017 | 2018-19 | 80 | 5.632 | 7.04 | 30.09.2017 | 22.02.2019 | 95 | 5.63 | 96 | 5.71 |  |
| 19 | Athani 110 kV SS – Capacity enhancement | 2.6 | 3/10/2017 | 2018-19 | 88 | 2.189 | 2.6 | 14.07.2017 | Trsrcommisioned on 24.5.2019 | 88 | 2.19 | 100 | 2.49 |  |
| 20 | Mundur 33 kV SS – Cap Enht& 33kV Vyr – ParprTL | 1.84 | 2017-18 | 2018-19 | 20 | 0.368 | 1.1 | 10.04.2018 | Trfrenergised on 8-3-2019 | CapEnh-50% | 0.60 | CapEnh-98% | 1.09 |  |
|  |  |  |  |  | 0 | 0 | 0.74 | 23.10.2018 | Not completed | Vyr-ppr TL - Not awarded | 0.00 |  |  |  |
| 22 | Interlinking between parappur and Mullassery 33kV substations |  |  |  |  |  | 1.92 | 21.02.2019 | 31.5.2019 |  |  | 88 | 1.69 |  |
|  | Subtotal -Ongoing |  |  |  |  |  |  |  |  |  | 22.61 |  |  |  |
| Circle - Kalamassery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Thammanam 33kV SS & UGC (APDRP) (SS energized) | 10 | 29/11/2016 | 2018-19 | 95 | 7.58 |  |  | 22.02.2019 | 100% | 7.98 |  |  |  |
| 4 | Brahmapuram 220 kV SS – Connecty to DLF (DW) | 4 | 04/15 | 2018-19 | 90 | 4.21 | 4.681 | 4/1/2015 | 3/1/2020 | 90 | 4.21 | 90 | 4.21 |  |
| 5 | Cherai 110 kV SS &Mannam line (REC, SS Compl2012) | 15 | 2010 | 2018-19 | 95.2 | 22.497 | 30.47 |  | 30.06.2019 | 20% | 24.62 | 100% | 24.62 |  |
| 7 | Thrikkakkara 66 kV SS– Capacity Enht (IPDS) | 2 | 01/01/2017 | 2018-19 | 6.5 | 0.21 | 3.25 | 1/1/2017 | 6/25/2019 | 70 | 1.30 | 100 | 3.25 |  |
| 8 | Perumanoor 66 kV SS – Capacity enht (IPDS) | 2 | 03/06/2017 | 2018-19 | 0.31 | 0.01 |  |  | 30.09.2019 | 50 | 1.32 | 50 | 1.32 |  |
| 9 | Kizhakkambalam 110 kV SS– Capacity Enht (Tx Compl0 | 1.5 | 30/11/2017 | 2018-19 |  | 0.5 |  |  | 14.05.2018 | 100% | 0.14 |  |  |  |
| 10 | Thrikkakkara 66 kV SS – Providing Earth Mat (IPDS) | 0.17 | 2017-18 | 2018-19 | 20 | 0.05 | 0.1855 | 11/30/2017 | 4/5/2018 | 100 | 0.19 |  |  |  |
| 11 | Kalamassery 220kV SS - BB protn&sectionalizer | 3.2 |  | 2019-20 |  |  | 3.2 | 15.07.2019 | 31.03.2020 |  |  |  |  |  |
| 12 | SAS - Automation of 7, 110 kV feeders- ( PSDF) | 2.21 |  | 2018-19 |  |  | 2.498 | 23.03.2018 | 20.07.2019 |  |  | 100% | 2.49 |  |
| 13 | Automation 4, 110 kV feeders : (Part DW) | 1.28 |  | 2018-19 |  |  | 1.427 | 08.03.2018 | 01.11.2018 | 100% | 1.42 |  |  |  |
| 16 | Enhancing the 220kV main bus | 3 | 2017-18 | 2018-19 | 50 | 1.85 | 0.0838 | 27.11.2018 | 31.03.2020 | 95% | 0.61 | 95% | 0.61 |  |
| 17 | Kalamassery -Earth mat @ 66kV yard | 1.07 | 2017-18 | 2018-19 | 50 | 0.535 | 0.6365 | 11.06.2018 | 25.05.2019 | 80% | 0.24 | 100% | 0.45 |  |
| 18 | Feeder bays for 110kV KLPM feeder | 2.985 |  | 2019-20 |  |  | 1.003 | 06.08.2019 | 31.03.2020 | 0 | 0.00 | 35% | 0.00 |  |
| 19 | Kalamassery -Earth mat @ 110kV yard | 2.31 | 08.09.2017 | 07.03.2018 | 100 | 1.691 | 2.31 | 08.09.2017 | 29.06.2018 | 100% | 1.69 |  |  |  |
| 20 | Kalamassery 220 kV SS - LT panel | 0.62 | 2017-18 | 30.11.2018 | 50 | 0.31 |  | 12.07.2017 | 30.04.2019 | 70% | 0.41 | 100% | 0.77 |  |
| 21 | Renovation of Auxiliary No.2 | 0.1 | 2017-18 | 31.10.2018 | 50 | 0.05 |  | 14.02.2018 | 18.09.2018 | 100% | 0.04 |  |  |  |
| 22 | Erection and commissioning of DCDB panels | 0.25 | 2017-18 | 15.12.2018 | 50 | 0.125 |  | 19.10.2018 | 30.04.2019 | 85% | 0.17 | 100% | 0.19 |  |
| 25 | Remetalling of yard | 0.215 | 2017-18 | 31.01.2019 | 50 | 0.1075 | 0.169 | 24.08.2019 | 30.11.2019 | 0 | 0.00 | 30 | 0.04 |  |
| 26 | Providing LAs for 110/66kV Transformers. | 0.035 | 2017-18 | 30.10.2018 | 50 | 0.0175 |  | 03.04.2019 | 06.07.2019 | 0 | 0.00 | 100 | 0.02 |  |
| 27 | Bushings replacement of 63 MVA Transformers | 0.134 | 2017-18 | 31.12.2018 | 50 | 0.067 | 0.127 | 7.3.2019 | 14.3.2019 | 100 | 0.07 |  |  |  |
| 28 | Vyttila UG cable feeder Eqpt& bus coupler bay | 0.62 | 2017-18 | 31.12.2018 | 50 | 0.31 |  | 01.06.2018 |  | 0 | 0.00 | 50 | 0.31 |  |
| 29 | Construction of new control room | 3 | 2017-18 | 31.12.2018 | 50 | 1.635 | 3.27 | 28.01.2019 | 14.07.2019 | 0 | 0.00 | 100 | 2.39 |  |
| 31 | Capacity Enht -1x 10MVA transformer | 1.75 | 2017-18 | 28.02.2019 | 50 | 0.875 | 1.72 | 10.08.2018 | 28.06.2019 | 70 | 1.20 | 100 | 1.65 |  |
| 34 | Kurumassery 110kV SS - 5MVA Transformer | 1.45 | 2017-18 | 2018-19 | 50 | 0.75 |  |  |  | 50 | 0.25 | 100% | 1.45 |  |
| 35 | Thammanam 33kV GIS – SCADA | 0.224 | 2017-18 | 2018-19 | 50 | 0.112 |  |  | 22.02..2019 | 50 | 0.11 | 100% | 0.22 |  |
| 36 | Mattancherry 110kV SS - Capacity Enht | 1.62 | 2017-18 | 2018-19 | 50 | 0.81 | 2.1 |  |  | 0 | 0.00 | 0 | 0.00 |  |
| 37 | NParavur 110 kV SS - 12.5MVA TF | 2 | 2017-18 | 2018-19 | 50 | 1.175 | 2.35 | 31.03.2020 | 1/0/1900 | 0 |  |  |  |  |
| 38 | KLSY 220 - Repl cross bus and CTs of 6 bays ( IPDS) | 0.05 | 2017-18 | 2018-19 | 50 | 0.025 |  | 05.02.2019 | 18.02.2019 | 100% | 0.01 |  |  |  |
| 39 | KLSY-Vyttila 66kV TL Reconductoring (IPDS) | 4 | 2017-18 | 2018-19 | 50 | 2.15 |  | 28.11.2018 | 28.12.2018 | 100% | 3.42 |  |  |  |
| 40 | Edayar SS Solar plant : SCADA & CCTV (IPDS) | 0.08 | 2017-18 | 2018-19 | 50 | 0.04 |  | 23.03.2018 | 28.03.2018 | 100% | 0.01 |  |  |  |
| 41 | Vyttila-P’Cruz 66 kV TL - UG OFC & OPGW-IPDS | 0.2 | 2017-18 | 2018-19 | 50 | 0.1 |  | 03.12.2018 | 29.12.2018 | 100% | 0.20 |  |  |  |
| 42 | Solar panel 25kWp (IPDS) | 0.175 | 2017-18 | 2018-19 | 50 | 0.0875 | 0.1712 | 24.05.2018 | 01.06.2019 |  |  | 100 | 0.17 |  |
| 43 | Solar panel 25kWp (IPDS) | 0.175 | 2017-18 | 2018-19 | 50 | 0.0875 | 0.171 | 5/25/2018 | 7/3/2019 | 90 | 0.05 | 100 | 0.17 |  |
| 44 | Independent control to 66kV supply IPDS | 1.18 | 2017-18 | 2018-19 | 50 | 0.59 | 1.026 | 10/6/2018 | 8/31/2019 | 0.623 | 0.87 | 100 | 1.03 |  |
| 46 | Tripunithura 66kV GIS IPDS | 20 | 2017-18 | 2018-19 | 50 | 10.875 | 25 | 10.08.2018 | 1.08.2019 | 100 | 15.00 | 100 | 19.00 |  |
| 48 | Njarakkal 66 kV SS Cap Enht - 16MVA -IPDS | 1.69 | 2017-18 | 2018-19 | 50 | 1 | 1.88 |  |  | 50 | 1.69 | 100 | 1.88 |  |
| 49 | Varapuzha 33 kV SS – R&M (DDUGJY) | 1.01 | 2017-18 | 2018-19 | 50 | 1 | 1.01 |  | 28.03.2019 | 50 | 1.01 | 100 | 1.01 |  |
| 50 | Alangad 33kV S/S – R&M DDUGJY | 1 | 2017-18 | 2018-19 | 50 | 1 |  |  | 22.07.2019 | 50 | 1.00 | 100 | 1.00 |  |
| 51 | Kurumassery 33 kV SS – R&M – DDUGJY | 1.03 | 2017-18 | 2018-19 | 50 | 1 |  |  | 1.08.2019 | 50 | 1.03 | 100 | 1.03 |  |
| 52 | Puthenvelikkara 33kV SS - R&M - DDUGJY | 1 | 2017-18 | 2018-19 | 50 | 1 |  |  | 12.08.2019 | 50 | 1.00 | 100 | 1.00 |  |
| 66 | Kochi Metro Supply from 110kV New Vyttila (DW) | 1 | 2017-18 | 2018-19 | 50 | 0.771 | 1.542 | 8/6/2016 | 8/14/2019 | 90 | 0.78 | 100 | 0.92 |  |
|  | SubTotal -Ongoing |  |  |  |  |  |  |  |  |  | 15.15 |  |  |  |
|  | SubTotal -New |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Division - Pathanamthitta |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Pandalam 33KV S/S & SC TL to Edappon IPDS | 5.16 | 17-3-2015 | 31-03-2019 | SS68/TL17 | Substation commissioned on 28.3.2019 & line commissioned on 15.3.2019 |  |  |  |  | 4.30 |  |  |  |
| 2 | Enathu 66KV SS (110KV Std) & TL to Adoor | 18.38 | 5/4/2016 | 31-03-2019 | SS46/TL29 |  |  |  | 30.6.2019 |  |  | Substation -99% Trans Line -100% (Substation & feeder commissioned on 26.6.2019) |  |  |
|  | New work |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Upgradation of 66KV substation Adoor to 110KV standard-Bay upgradation | 9.95 | 15-10-2018 | 15.1.2019 |  |  |  |  | 2021-22 |  |  |  |  |  |
|  | SubTotal -Ongoing |  |  |  |  |  |  |  |  |  | 4.30 |  |  |  |
|  | SubTotal -New |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Circle - Kannur |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Rajapuram 33kV Indoor SS | 6 | 7/1/2016 | 2019-20 | 27 | 0.6906 | 6.48 | 10.02.2017 | 31.10.2019 | 50 | 3.24 | 90 | 5.83 |  |
| 2 | Kelakam 33kV Indoor SS | 10 | 22/08/2017 | 2019-20 | 60 | 6.14 | 10 | 42969 | 43679 | 60 | 6.14 | 100 | 9.05 |  |
| 3 | Nedumpoyil 66 KV SS Upgdn to110 kV & DC Line | 12 | 15/12/2015 | 2019-20 | 90 | 6.574 | 13.55 | 15/12/2015 | 27/05/19 | 90 | 6.57 | 98 | 9.85 |  |
| 4 | Sreekandapuram 66 KV SS Upgr to 110 kV & TL | 9.95 | 26/04/2017 | 2019-20 | 65 | 5.35 | 9.95 | 26/04/2017 | 43776 | 65 | 5.35 | 80 | 8.53 |  |
| 5 | Valiyavelicham 110 kV SS – (KSIDC DW) | 11.85 | 10/1/2016 | 43251 | Completed | 5.38 |  | 42644 | 27/3/18 | 99 | 9.70 | 100 | 10.73 |  |
| 6 | Tholambra 33KV SS - Conversion to indoor | 0.63 | 2017-18 | 2018-19 | completed | 0.315 | 0.63 | 42826 | 22/3/19 | 100 | 0.40 | 100 | 0.61 |  |
| 7 | Pinarayi 110KV SS - Capacity Enht | 2 |  | 2019-20 |  |  | 3.37 | 17/1/17 |  | 35 | 0.11 | 50 | 0.65 |  |
| 8 | Dharmadam 33 kV SS - Conversion to indoor | 0.9 |  | 2019-20 |  |  | 0.9 | 23/11/18 |  | 40 | 0.00 | 70 | 0.21 |  |
| 9 | Kodiyeri 33 kV SS -Conversion to indoor | 0.9 | 2017-18 | 2018-19 | 50 | 0.485 | 0.9 | 27/7/18 |  |  |  | 70 | 0.31 |  |
| 10 | Panoor110kV SS - Cap enht -1 x 16MVA TF & bay | 2 | 2017-18 | 2018-19 | 50 | 1.3 | 2.6 | 19/7/18 | 28/6/19 | 50 | 1.20 | 100 | 2.10 |  |
| 11 | Puthur 33kV SS - Conversion to indoor | 0.92 |  | 2019-20 |  |  |  | 13/12/18 |  | 30 | 0.00 | 65 | 0.00 |  |
| 12 | 220kV SS, Kanhirode - capacity enhancement by installing 2X12.5MVA transformer | 2.5 | 2020-21 | 2020-21 |  |  |  |  |  |  |  |  |  |  |
| 13 | Kannur Sports Council -shifting of 110 kV line (DW) | 1 | 2017-18 | 2018-19 | completed | 0.625 |  | 2018-19 | 2018-19 | 100 | 1.00 |  |  |  |
| 14 | 33 kV Payyannur Town-11kV Indoor 8 Panel set Convertion | 0.76 | 2017-18 | 2018-19 | 50 | 0.38 |  |  | 2020-21 |  |  | 50 | 0.17 |  |
| 15 | 33kV Alakkode-New 11kV Outlet | 0.07 | 2017-18 | 2018-19 | completed | 0.07 |  | 2018-19 | 2018-19 | 100 | 0.07 |  |  |  |
| 16 | 220kV SS Taliparamba-Erection of 220 kV bus isolators | 0.09 | 2017-18 | 2018-19 | completed | 0.09 |  | 2018-19 | 2018-19 | 100 | 0.09 |  |  |  |
| 17 | 220kV SS Taliparamba-Yard metalling | 0.04 | 2017-18 | 2018-19 | completed | 0.04 |  | 2018-19 | 2018-19 | 100 | 0.04 |  |  |  |
| 18 | 220kV SS Taliparamba-Renovation of 220kV Isolators | 0.05 | 2017-18 | 2018-19 | completed | 0.05 |  | 2018-19 | 2018-19 | 100 | 0.05 |  |  |  |
| 19 | Puthiyatheru 33 kV SS - 11kV panel to indoor Conv | 0.9 | 2017-18 | 2018-19 | 50 | 0.45 |  |  | 2020-21 | 50 |  | 50 | 0.19 |  |
| 20 | 110 kV SS Mangad-Providing chain link fencing | 0.08 | 2017-18 | 2018-19 | completed | 0.08 |  | 2018-19 | 2018-19 | 100 | 0.08 |  |  |  |
| 21 | 110kV SS Mangad-Leak proofing of control room | 0.09 | 2017-18 | 2018-19 | completed | 0.09 |  | 2018-19 | 2018-19 | 100 | 0.09 |  |  |  |
| 22 | 110kV SS Mangad-Renovation of store compund | 0.18 | 2017-18 | 2018-19 | Completed | 0.18 |  | 2018-19 | 2018-19 | 100 | 0.18 |  |  |  |
| 23 | 110kV SS Mundayad-Second 16MVA Transformer | 2 | 2017-18 | 2018-19 | completed | 1.25 |  | 2018-19 | 2018-19 | 100 | 2.00 |  |  |  |
| 24 | 110kV SS Mundayad-Water connection to yard | 0.02 | 2017-18 | 2018-19 | 50 | 0.01 |  | 2018-19 | 2018-19 | 100 | 0.02 |  |  |  |
| 25 | Mylatty 220kV SS - Nitrogen drying and Overhauling of TF | 0.2 | 2017-18 | 2018-19 | 25 | 0.06 |  | 2018-19 | 2019-20 | 25 | 0.06 | 25 | 0.06 |  |
| 26 | Mylatty 220kV SS – Replacing 220kV TF CB & BC | 0.0215 | 2017-18 | 2018-19 | 50 | 0.01075 |  | 2017-18 | 2018-19 | 50 | 0.01 | 100 | 0.02 |  |
| 27 | Mylatty 220 kV SS – Quarters Renewal | 0.1495 | 2017-18 | 43447 | 40 | 0.11 | 0.46 | 2018-19 | 2019-20 | 40 | 0.11 | 40 | 0.11 |  |
| 28 | Mylatty 220kV SS- Switch Yard Renweal | 0.0465 | 2017-18 | 43495 | 50 | 0.02325 |  | 25.03.2019 | 03.06.2019 | 50 | 0.02 | 100 | 0.05 |  |
| 29 | Mylatti 220kV SS –Video conference hall | 0.5 | 2019-20 | 43831 |  | 0 |  |  |  |  |  | 10 | 0.00 |  |
| 30 | 220 kV Substation, Mylatty - Bay extension for upgradation of Mylatty- Thoudugoli line | 0.2 | 2019-20 | 2020-21 | 0 | 0 |  |  |  | 0 | 0.00 | 0 | 0.00 |  |
| 31 | 220 kV Substation, Mylatty - Bay extension for proposed 110 kV Substation at Kuttikkol | 0.5 | 2019-20 | 2020-21 | 0 | 0 |  |  |  | 0 | 0.00 | 0 | 0.00 |  |
| 32 | Mulleria 110KV SS – TF Bay Extn - 16 MVA TF | 2 | 2017-18 | 31.12.2018 | 50 | 1.15 |  | 2018-19 | 2018-19 | 100 | 2.00 |  |  |  |
| 33 | Badiadka - 33 KV Substation - Conversion to indoor | 0.25 | 2017-18 | 31.03.2019 | 50 | 0.125 |  | 2018-19 | 2019-20 | 50 |  | 50 | 0.13 |  |
| 34 | Perla 33 KV SS - Control room extension and cable trench | 0.17 | 2017-18 | 31.03.2019 | 50 | 0.085 |  | 2018-19 | 2018-19 | 100 | 0.17 |  |  |  |
| 35 | Perla 33 KV SS - Store shed | 0.0451 | 2017-18 | 2018-19 | 50 | 0.02255 |  | 2018-19 | 2018-19 | 100 | 0.05 |  |  |  |
| 36 | West Eleri 33 kV SS – Capacity addition by installation of 5 MVA transformer | 0.7 | 2017-18 | 2019-20 | 50 | 0.35 | 0.4 |  |  |  |  |  |  |  |
| 37 | Cheruvathur 110 kV SS – Cap Enh 2X10 MVA TF | 1.99 | 2017-18 | 2019-20 | 50 | 0.995 | 1.99 | 13.03.2019 |  | 50 | 1.00 | 75 | 1.00 |  |
| 38 | Thrikkaripur - 33 KV SS - Conversion indoor | 0.88 | 2017-18 | 2019-20 | 50 | 0.44 | 0.15 | 06.03.2019 | 27.011.2019 | 5 | 0.00 | 5 | 0.00 |  |
| 39 | Belur 33 KV SS - Conversion to indoor | 0.99 | 2017-18 | 2019-20 | 50 | 0.495 | 0.255 | 13.08.2018 | 10.04.2019 | 70 | 0.14 | 100 | 1.00 |  |
| 40 | 110KV SS Mulleria - Earthmat | 0.23 | 2019-20 | 2019-20 |  |  | 0.23 | 2019-20 | 2019-20 |  |  | 25 | 0.06 |  |
| 41 | 110KV SS Kasaragod - Installation of new capacitor bank | 0.15 | 2019-20 | 2019-20 |  |  | 0.15 | 2019-20 | 2019-20 |  |  | 90 | 0.10 |  |
| 42 | 33KV SS Kasaragod town - Capacity enhancement from 2 x 5MVA to 2 X 8MVA | 0.92 | 2019-20 | 2019-20 |  |  | 0.92 | 2019-20 | 2019-20 |  |  | 100 | 0.92 |  |
| 43 | 110KV SS Manjeshwar - Earthmat | 0.3 | 2019-20 | 2019-20 |  |  | 0.3 | 2019-20 | 2019-20 |  |  | 25 | 0.08 |  |
| 44 | 33kV SS Alakkode-11kV outdoor to indoor conversion | 0.76 | 2019-20 | 2020-21 |  |  |  |  |  |  |  | 50 | 0.18 |  |
|  | Subtotal -Ongoing |  |  |  |  |  |  |  |  |  | 5.84 |  |  |  |
|  | Subtotal-New |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Circle - Malappuram |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Perinthalmanna SS Upgdn to 110 kV & DC LILO | 16.7 | 4/5/2015 | 3/31/2017 | Commisioned | 8.5593 | 16.7 | 13/02/2015 | 1/1/2020 | 99 | 8.56 | 99.5 | 8.56 |  |
| 2 | 33 kV SS Pothukallu& connected lines | 5.72 | 1/11/2012 | 2018-19 | 47 | 1.93 | 9.6 | 30/09/2011 | 12/19 | 47 | 1.93 | 89 | 3.10 |  |
| 3 | Malaparamba to Ramapuram DC Line to MC | 3.44 | 4/29/2013 | 4/29/2018 | Commisioned | 1.98 | 3.44 | 4/29/2013 | 25/10/2019 | 99 | 1.98 | 99 | 3.16 |  |
| 4 | Kalpakanchery&Edarikode 33kV SS – SC Tap Line | 3.45 | 4/4/2016 | 6/4/2017 | Commisioned | 2.883 | 3.45 | 4/4/2016 | 6/4/2017 | Commisioned | 2.88 |  |  |  |
| 5 | Malappuram – Tirur 110 kV Line Doubling (Ph1&2) | 1.55 | 09/16 | 2018-19 | 100 / 89 | 2.038 | 2.43 | 14/09/2016 | 31/07/2019 | 100 / 89 | 2.04 |  |  |  |
| 6 | Manjeri SS Upgdn to 110 kV with 2 No 110kV feeder bay | 8.21 | 1/11/2012 | 2018-19 | 100 /23 | 2.83 | 8.21 | 1/4/2016 | 12/19 | 90/86 | 2.83 | 90/86 | 2.83 |  |
| 7 | Tirur Traction SS supply with UGC (DW) | 9.08 |  | 2018-19 | 93 /100 | 2.61 | 9.08 | 4/3/2016 | 07.09.2018 | 100/100 | 2.61 |  |  |  |
| 8 | Kizhissery – Edavanna 33kV Line | 4.07 | 9/30/2017 | 2018-19 | 33 | 0.03175 | 4.07 | 30/09/2017 | 12/19 | 33 | 0.71 | 95 | 1.09 |  |
| 9 | Ramapuram – Melattur 110 kV TL &Melattur Bays | 2.95 | 6/6/2016 | 2018-19 | TL-100 | 2.9 | 2.95 | 6/6/2016 | 2016-17 | 100 | 2.90 |  |  |  |
| 10 | Nilambur&Edakkara SS Upgdn to 110 kV & TL | 13.21 | 02/18 | 2018-19 | TL-15 | 0.021 | 13.21 | 11/2/2016 | 03/21 | TL-100, | 0.02 | TL-100, SS-15% | 0.43 |  |
| 11 | Shanthinagar – Pokkottumpadam 33kV Line | 2.85 | 12/16 | 2018-19 | TL-100 | 0.2687 | 2.85 | 22/02/2017 | 03/18 | 100 | 1.18 | 100 | 1.26 |  |
| 12 | Installation of 2nd 12.5 MVA Transformer at 110kV SS Melattur | 2.92 | 09/18 | 2018-19 | 95 | 0 | 2.92 | 09/18 | 02.05.2019 | 95 | 0.00 | 98 | 0.05 |  |
| 13 | Installation of 2nd 16 MVA Transformer at 110kV SS Melattur | 3.04 | 03/19 | 2019-20 | 0 | 1.28384 | 3.04 | 03/19 | 02/20 | 0 | 1.28 | 20 | 1.28 |  |
| 14 | Capacity Enhancement by replacing 2x12.5MVA with 2X20MVA at 110kV SS, Kizhissery | 4.57 | 12/18 | 2019-20 | 50 | 1.19027 | 4.57 | 12/18 | 2020-21 | 50 | 1.19 | 70 | 1.19 |  |
| 15 | Installation of 2nd 5MVA Transformer at 33kV SS Kalikavu | 1.03 | 12/19 | 2019-20 | 0 | 0 | 1.03 | 12/19 | 03/20 | 0 | 0.00 | 0 | 0.00 |  |
| 16 | Replacing existing 2X5MVA Transformers with 2X8MVA, at 33kV SS Makkaraparamba | 2.56 | 04/19 | 03/20 | 0 | 0 | 2.56 | 04/19 | 03/20 | 0 | 0.00 | 85 | 1.39 |  |
| 17 | Replacing 2x12.5MVA Transformers with 2x20MVA at 110kV Substation, Tirur | 4.76 | 3/1/2017 | 2018-19 | 100% | 4.76 | 4.76 | 3/1/2017 | 2020-21 | 98% | 4.60 | 98% | 4.60 |  |
| 18 | Enhancement of 220kV Malaparamba Substation Capacity to 400MVA | 15.85 | 8/8/2019 | 2020-21 | NIL | NIL | 15.85 | 10/8/2019 | 2020-21 | 0% | NIL | 5% | 7.86 |  |
| 19 | Extention of Control room and 10 panel set at 33kV Kooriyadsubstn | 1.5 | 01/19 | 2020-21 | NIL | NIL | 1.5 | 17/01/2019 | 2020-21 | 0% | NIL | 2% | 0.07 |  |
| 20 | Rennovation of 110kV Bus bar at 220kV Substation, Malaparamba | 4.5 | 03/20 | 03/21 | NIL | NIL | 4.5 | 03/20 | 03/21 | 0% | NIL | 0% | NIL |  |
| 21 | Replacing 2x16MVA Transformer with 2x25MVA Transformer at 110kV Substation, Edarikkode | 4.9 | 05/20 | 03/21 | NIL | NIL | 4.9 | 05/20 | 03/21 | 0% | NIL | 0% | NIL |  |
| 22 | Construction of 2 Nos 110kV Bays at 110kV Substation, Edarikkode | 1.1 | 01/19 | 08/19 | NIL | NIL | 1.10 | 01/19 | 03/21 | 60% | 0.00 | 60% | 0.85 |  |
| 23 | Providing 1x16MVA Transformer at Edappal | 3.47 | 06/20 | 10/20 | NIL | NIL | 3.47 | 06/20 | 10/20 | 0% | NIL | 0% | NIL |  |
| 24 | 25MVAR Capacitor bank at 110kV Substation, Edappal | 0.26 | 01/20 | 03/20 | NIL | NIL | 0.26 | 01/20 | 03/20 | 0% | NIL | 0% | NIL |  |
| 25 | Capacity enhancement work at 110kV Substation, Kuttippuram | 7.3 | 11/19 | 10/20 | NIL | NIL | 7.3 | 11/19 | 10/20 | 0% | NIL | 0% | NIL |  |
| 26 | Upgradation of 66kV Substation, Mankada to 110kV | 4.34 | 06/20 | 12/21 | NIL | NIL | 4.34 | 06/20 | 12/21 | 0% | NIL | 0% | NIL |  |
| 27 | Upgradation of 66kV line to Mankada substation | 2.65 | 08/19 | 05/20 | NIL | NIL | 2.65 | 08/19 | 05/20 | 0% | NIL | 10% | 0.85 |  |
| 28 | Control room extn and 10 Panel set at 33kV Substation, Othukkungal | 1.5 | 05/20 | 01/21 | NIL | NIL | 1.5 | 05/20 | 01/21 | 0% | NIL | 0% | NIL |  |
| 29 | Providing 2x8MVA Transformers at 33kV Substation, Othukkungal | 1.2 | 06/20 | 10/20 | NIL | NIL | 1.2 | 06/20 | 10/20 | 0% | NIL | 0% | NIL |  |
| 30 | Providing 1x5MVA Transformer at 33kV Substation, Tavanur | 1 | 01/19 | 06/20 | NIL | NIL | 1.00 | 01/19 | 03/20 | 0% | NIL | 0% | NIL |  |
| 31 | 33kV Chelari - Kooriyad line | 4.2 | 02/20 | 03/21 | NIL | NIL | 4.2 | 02/20 | 03/21 | 0% | NIL | 0% | NIL |  |
| 32 | 33kV Substation, Changaramkulam | 5.82 | 05/20 | 03/21 | NIL | NIL | 5.82 | 05/20 | 03/21 | 0% | NIL | 0% | NIL |  |
| 33 | 33kV Edappal - Changarmkulam line | 2.91 | 06/20 | 02/21 | NIL | NIL | 2.91 | 06/20 | 02/21 | 0% | NIL | 0% | NIL |  |
| 34 | Construction of new control room at 110kV Ponnani Substation | 0.45 | 04/20 | 03/21 | NIL | NIL | 0.45 | 04/19 | 03/21 | 0% | NIL | 0% | NIL |  |
| 35 | New 110kV Feeder bay at 110kV Substation, Ponnani | 0.6 | 2021-22 | 2021-22 | NIL | NIL | 0.6 | 05/21 | 09/21 | 0% | NIL | 0% | NIL |  |
| 36 | Construction of balance compound wall for 110kV Substation, Parappanangadi | 0.2 | 08/20 | 01/21 | NIL | NIL | 0.2 | 08/20 | 01/21 | 0% | NIL | 0% | NIL |  |
|  | Sub Total -ongoing works |  |  |  |  |  |  |  |  |  | 10.43 |  |  |  |
|  | Circle - Palakkad |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Kollengode – Vadakkenchery 110 kV DC TL | 15 | 18/03/2017 | 2018-19 | 30 | 2 | 2.8 | 2017 | 2020 | 30 | 0.30 | 60 | 0.30 |  |
| 3 | Agali 33 kV SS - 5 MVA TF - DDUGJY | 0.91 | 21/10/2017 | 2018-19 | 75 | 0.72 |  |  |  | 70 | 0.70 | 100 | 0.29 |  |
| 4 | Kollengode 110 kV SS - Replacing 33 kV TF | 3 | 21/11/2017 | 2019-20 | 15 | 0.3 | 1 | 2018 | 2021 | 30 | 0.21 | 45 | 0.23 |  |
| 5 | Palakkad 220 kV SS - 160 MVA TF | 5 | 2017-18 | 2018-19 | 20 | 0.27 |  |  | 2019-20 | 100 |  | 100 | 3.76 |  |
| 6 | Palakkad-Medical College S/s upgradation | 4 | 2017-18 | 2018-19 | 50 | 5 | 10 |  | 2019-20 | 80 |  | 100 | 0.24 |  |
| 7 | Bay Extension for 110kV DC Line to Malampuzha | 0.8 | 2017-18 | 2018-19 | 50 | 2.75 |  |  | 2020-21 |  |  | 50 | 0.26 |  |
| 8 | Replacing Faulty Spare Unit 53.33 MVA TFR | 0.25 | 2017-18 | 2018-19 | 50 | 0.4 |  |  | 2019-20 |  |  | 90 | 0.15 |  |
| 9 | Control Room Window for Leak Proofing of AC | 0.005 | 2017-18 | 2018-19 | 50 | 0.125 |  |  |  |  |  | 0 |  |  |
| 10 | Construction of Bike shed infront of control room | 0.0125 | 2017-18 | 2018-19 | 50 | 0.0025 | 0.01 |  | 2018-19 | 100 | 0.01 |  |  |  |
| 11 | Compound wall & tiles | 0.0558 | 2017-18 | 2018-19 | 50 | 0.00625 | 0.058 |  | 2019-20 |  |  | 0 | 0.00 |  |
| 12 | Concrete interlocking tiles at courtyard | 0.034 | 2017-18 | 2018-19 | 50 | 0.0279 | 0.034 |  | 2019-20 |  |  | 0 | 0.00 |  |
| 14 | Replacing 2x220kV CB of Transformer Bank | 0.26 | 2017-18 | 2018-19 | 50 | 0.02065 | 0.172 |  | 2019-20 |  |  | 75 | 0.24 |  |
| 15 | Yard concreting & spreading Metal (6th Phase) | 0.3 | 2017-18 | 2018-19 | 50 | 0.13 | 0.44 |  | 2019-20 |  |  | 90 | 0.00 |  |
| 16 | Providing security camera in 220/11KV Yard | 0.03 | 2017-18 | 2018-19 | 50 | 0.15 | 0.28 |  | 2019-20 |  |  | 80 | 0.02 |  |
| 17 | Capacity enhancement -2x200MVA transformers | 10 | 2017-18 | 2018-19 | 50 | 6 | 6 | 2018-19 | 2018-19 | 50 | 6.00 | - | - |  |
| 18 | Second 110V 400 AH battery with charger | 0.135 | 2017-18 | 2018-19 | 100 | 0.135 | 0.135 | 2017-18 | 2018-19 | 100 | 0.14 | - | - |  |
| 19 | New Yard and road | 0.13 | 2017-18 | 2018-19 | 50 | 0.0675 | 0.1428 | 2019-20 | 2019-20 | 50 | 0.07 | 100 | 0.14 |  |
| 20 | 220 kV yard metalling | 0.39 | 2017-18 | 2018-19 | 50 | 0.065 | 0.39 | 2019-20 | 2019-20 | 50 | 0.63 | 100 | 0.39 |  |
| 21 | Yard Security Camera (220/11KV Yard) | 0.03 |  | 2019-20 | - | - | 0.164 | 2019-20 | 2019-20 | - | - | 100 | 0.16 |  |
| 22 | Tiles in 11kV control room | 0.06 |  | 2019-20 | - | - | 0.154 | 2019-20 | 2019-20 | - | - | 100 | 0.15 |  |
| 26 | Renovation of 3 Quarters | 0.08 |  | 2019-20 | - | - | 0.452 | 2019-20 | 2019-20 | - | - | 100 | 0.45 |  |
| 29 | Renovation of control room &office | 0.095 | 2019-20 | 2019-20 | - | - | 0.925 | 2019-20 | 2019-20 | - | - | 100 | 0.93 |  |
| 40 | Construction of Bell mouth and Providing drainage |  |  |  |  |  | 0.283 | 2019-20 | 2019-20 | - | - | 100 | 0.28 |  |
| 42 | Providing new pipe connection inside the yard | 0.0078 | 2017-18 | 2018-19 | 50 | 0.005 |  |  |  | 100 | 0.01 |  |  |  |
| 43 | Nalleppilli DP Structure - 11kV AB switch | 0.0025 | 2017-18 | 2018-19 | 50 | 0.0039 |  |  |  | 100 | 0.00 |  |  |  |
| 48 | Construction of vehicle shed | 0.01 |  | 2019-20 |  |  |  | 4/17/2018 | 6/14/2018 | 100 | 0.02 |  |  |  |
| 49 | Metaling of 11kV DP structure area | 0.01 |  | 2019-20 |  |  |  | 5/5/2016 | 12/29/2018 | 100 | 0.03 |  |  |  |
| 50 | Strengethening of earthing system | 0.2 |  | 2019-20 |  |  |  |  |  | 100 | 0.05 |  |  |  |
| 51 | Flooring of Tiles and Repair | 0.02 |  | 2019-20 |  |  |  |  |  | 100 | 0.03 |  |  |  |
| 53 | Replacing 11kV VCB panel (12panel set) | 0.4 |  | 2019-20 |  |  |  |  |  | 100 | 0.40 |  |  |  |
| 54 | Construction of firewall | 0.12 | 2018-19 | 2018-19 | 100% | 0.055 | 0.1275 |  |  | 100% | 0.06 |  |  |  |
| 56 | Providing earthmat in existing yard | 0.3 |  | 2019-20 |  |  | 0.22 |  |  |  |  | 8% | 0.00 |  |
| 57 | Feeder Bay extension - for Vennakkara GIS TL | 0.25 |  | 2020-21 |  |  |  |  |  |  |  |  |  |  |
| 58 | Instruments, tools and safety equipments | 0.003 |  | 2019-20 |  |  |  |  |  |  |  | 100% | 0.00 |  |
| 59 | Mac road up to transformer and fencing | 0.05 |  | 2019-20 |  |  | 0.068 |  |  | 100% | 0.05 |  |  |  |
| 60 | Instruments, tools and safety equipments | 0.005 |  | 2019-20 |  |  |  |  |  |  |  | 100% | 0.01 |  |
| 61 | Tower Insertion - Sreekrishnapuram and Kongad 33 kV | 0.1 |  | 2018-19 |  |  | 0.74 |  |  | 100% | 0.74 |  |  |  |
| 63 | Yard metalling, Earthing (11 KV) etc | 1 | 2017-18 | 2018-19 | 50 | 6.15 | 0.0081 |  |  | 100% | 0.01 |  |  |  |
| 65 | Mat Earthing | 0.15 | 2017-18 | 2018-19 | 50 | 0.55 | 0.1471 | 2018-19 | 2018-19 | 100 | 0.15 | - | - |  |
| 66 | Transformer (110 kV )CB Replacment | 0.09 | 2017-18 | 2018-19 | 50 | 0.075 |  |  |  | 100 | 0.08 |  |  |  |
| 70 | Palakkad &Malampuzha SS Interlinking – 2 TLs | 1.2 | 2017-18 | 2018-19 | 50 | 0.275 |  |  |  | 100 | 1.20 |  |  |  |
| 71 | Malampuzha 110kV SS – 1x 10MVA TF & Bay | 1.5 | 2017-18 | 2018-19 | 50 | 0.6 |  |  |  |  |  | 65 | 0.10 |  |
| 74 | Replacement of 110kV CT &OTCR | 0.09 | 2019-20 | 2019-20 |  |  |  |  |  |  |  |  |  |  |
| 75 | Construction of Pillars for Gate in front of Yard | 0.002 | 2017-18 | 2018-19 | 50 | 0.045 | 0.002 | 2018-19 | 2018-19 | 100 | 0.00 | - | - |  |
| 76 | Replacement of old Battery Charger 30A | 0.009 | 2017-18 | 2018-19 | 50 | 0.001 | 0.009 | 2018-19 | 2018-19 | 100 | 0.01 | - | - |  |
| 77 | Installation of 110kV Bus Coupler (Gas Insulated) | 0.47 | 2019-20 | 2019-20 | 50 | 0.0045 | - | - | - | - | - | - | - |  |
| 78 | Providing 1 No 11 kV feeder outlet (pengattiri) | 0.0025 | 2018-19 | 2018-19 | - | - | 0.028 | 2018-19 | 2018-19 | 100 | 0.03 | - | - |  |
| 79 | Construction of vehicle shed | 0.001 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - |  |
| 80 | Replacement of Station Battery 200AH | 0.031 |  | 2019-20 | 100 | 0.0252 | 0.0252 | 2018-19 | 2018-19 | 100 | 0.03 | - | - |  |
| 81 | Construction of vehicle shed | 0.001 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | - | - |  |
| 83 | Splitting of 110 KV Bus by providing Bus Isolator | 0.06 | 2019-20 | 2020-21 | - | - | - | - | - | - | - | - | - |  |
| 84 | 110 KV Bus PT- 3 Nos | 0.04 | 2020-21 | 2020-21 | - | - | - | - | - | - | - | - | - |  |
| 85 | Koottanad 110kV SS - 16 MVA TF | 2.2 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | 25 | 1.19 |  |
| 86 | Compound wall 110 Kv yard | 0.02 |  | 2019-20 | - | - | - | - | - | - | - | - | - |  |
| 87 | Replacing 11 kV AB switch | 0.014 | 2018-19 | 2018-19 |  |  | 0.006 | 2018-19 | 2018-19 | 100 | 0.01 | - | - |  |
| 89 | Providing 110KV Bus spliting isolator | 5 | 2019-20 | 2020-21 |  |  | - | - | - | - | - | - | - |  |
| 90 | Yard fencing infront of Control room. | 1 | 2020-21 | 2020-21 |  |  | - | - | - | - | - | - | - |  |
| 93 | KollengodeVadakkenchery 110kV Line | 24 |  | 2019-20 |  |  | 24 | 04/03/2017 | 31/12/2019 | 20 | 1.22 | 75 | 6.71 |  |
| 106 | Yard light - LED lamp | 0.05 | 2017-18 | 2018-19 | 50 | 0.01 | 0.00425 | 2018-19 | 2018-19 | 100 | 0.00 | - | - |  |
| 109 | Kothachira& NH Feeders - AutoreclosureReplcmt | 0.06 | 2018-19 | 2018-19 | 100 | 0.0744 | 0.0744 | 2018-19 | 2018-19 | 100 | 0.07 | - | - |  |
| 110 | New Control Room Civil works | 0.1 | 2018-19 | 2018-19 | 100 | 0.0941 | 0.0941 | 2018-19 | 2018-19 | 100 | 0.09 | - | - |  |
| 112 | New prefab Control room with 11 kV indoor panel | 0.75 | 2019-20 | 2019-20 | - | - | - | - | - | - | - | 50 | 0.19 |  |
| 113 | Thiruvegapura 33 SS -Cap Enh - -1x 5 MVA TF | 0.4 | 2017-18 | 2018-19 | 50 | 0.375 | - | - | - | - | - | - | - |  |
| 114 | Construction of 110 kV substation Pattambi | 8 | 2019-20 | 2020-21 |  |  | - | - | - | - | - | - | - |  |
| 115 | Construction 110 kV line |  | 2020-21 | 2020-21 |  |  | - | - | - | - | - | - | - |  |
| 116 | Installation of 5MVAR capacitor bank | 0.15 |  | 2019-20 |  |  |  |  |  |  |  |  |  |  |
| 121 | Construction of compound wall | 0.01 | 2017-18 | 2018-19 | 50 | 0.075 |  |  |  | 100 | 0.08 |  |  |  |
| 132 | Palakkad - Malampuzha 110kV DC line | 5.5 |  | 2020-21 |  |  | 3.55 |  |  |  |  | 15% | 0.00 |  |
| 133 | Olavakkode Substation civil work icluding filling | 0.4 | 2018-19 | 2019-20 | 100% | 0.32 | 0.28 |  |  |  |  |  |  |  |
| 134 | Olavakkode Substation drawing 33kV ABC | 0.16 | 2017-18 | 2018-19 | 100% | 0.65 | 0.53 |  |  | 100 | 0.36 |  |  |  |
| 136 | Olavakkode Substation Equipment & Erection | 1.2 | 2018-19 | 2019-20 | 50% | 0 |  |  |  |  |  | 100% | 1.10 |  |
| 137 | Olavakkode Substation containerised substation | 2.5 | 2018-19 | 2019-20 | 50% | 0 |  |  |  |  |  | 100% | 2.20 |  |
|  | Sub Total Ongoing works |  |  |  |  |  |  |  |  |  | 3.58 |  |  |  |
|  | Circle -Thiruvananthapuram |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Kattakkada 220 kV SS & TL to Pothencode | 112.15 | 9/23/2009 | 2018-19 | Completed | 104.26 |  |  |  | 100 | 104.26 |  |  |  |
| 4 | Aryanad 33 kV SS Upgradation of & SC TL | 8.41 | 9/7/2014 | 2018-19 | completed | 8.3289 |  |  |  | 100 | 8.33 |  |  |  |
| 5 | Vilakulam 33 kV SS Upgdn& SC TL (RAPDRP)(Name of Work: Construction of 33 kV Substation,Vilakkulam and 33kV SC Line and constructionof 33 kV feeder bay at 110 kV Substation,Varkala). | 8.3 | 3/16/2016 | 2018-19 | 30 / 50 | 3.05 |  | 01.10.2016 |  | 82 | 4.70 | 85 | 4.70 |  |
| 6 | Kacheri 33 kV SS Upgdn& UGC (RAPDRP)(Name of Work: Construction of 33 kV Substation, Kachery and laying of 33 kV UG cable from 110 kV Substation ,Attinga to 33 kV Substation, Kachery) | 6.6 | 9/21/2016 | 2018-19 | 95 / 100 | 4.6967 |  | 27.02.2017 |  | 95 | 0.00 | 99 | 5.43 |  |
| 8 | VydyuthiBhavanam 33 kV SS & UGC (IPDS) | 7.43 | 2/15/2018 | 2018-19 | 2 | 0.02 | 5.9 | 8.11.2018 | 7.9.2019 | 43 | 0.36 | 100 | 7.00 |  |
| 9 | Neyyattinkara SS Upgdn 110 kV | 8.37 | 1/12/2017 | 2018-19 | 2 | 0.38 | 8.37 | 22.1.2018 | 5.7.2019 | 50 | 4.24 | 100 | 7.69 |  |
|  | Subtotal -Ongoing | 165.2 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Sub Total -ogoing works |  |  |  |  |  |  |  |  |  | 112.59 |  |  |  |
|  | Circle - Kozhikode |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Kinaloor 110 kV SS & LILO | 9.5 | 11/19/2015 | 42777 | Commisioned | 6.0501 |  |  |  | 100 | 9.50 |  |  |  |
| 2 | Cyber Park 66 kV SS & LILO (Part DW) (TL- Compltd) | 9 | 4/22/2016 | 2018-19 | SS- 97 | 5.2002 | 5.2352 | 4/22/2016 | 28-05-2019 | 97 | 5.20 | 100 | 5.24 |  |
| 3 | Gandhi Road- Chevayur 110 kV UG Cable | 23 | 1/23/2017 | 2018-19 | 65 | 14.3862 | 23 | 2016-2017 | 4/1/2019 | 0.95 | 12.00 | 1 | 12.00 |  |
| 4 | Mankavu 66kV SS Upgration to 110kV | 11.86 | 2017-18 | 43497 | 75 | 8.895 | 11.86 | 7/10/1905 | 2020-2021 | 30 | 1.80 | 75 | 0.90 |  |
| 5 | Kunnamangalam- Kuttikkattor Line to 110 KV | 5 | 2017-18 | 43497 | 75 | 3.75 |  | 2018-19 | 2019-20 | 40 | 2.53 | 45 | 0.70 |  |
| 6 | Gandhi Road – Chevayur 110 kV UGC & bays | 23 | 2017-18 | 43525 | 75 | 17.25 |  | 16.03.2018 | 25.03.2019 | 100 | 23.00 |  |  |  |
| 7 | Nallalam 220kV SS Cap Enht - Power transformers | 17.21 |  | 43586 | 35 | 6.12 |  | 18-19 | 20-21 | 35 | 6.12 | 40 | 6.19 |  |
| 8 | Kuttikkattur SS Upgradation to 110kV | 8 | july2018 | 2019-20 | 0.05 | 0.3 |  | 7/1/2018 |  | 5 | 0.30 | 20 | 0.30 |  |
| 9 | Ramanattukara 33kV SS – 5MVA TF (DDUGJY) | 0.66 | 2017-18 | 2018-19 | 75 | 0.495 | 1.4535 | 2018-19 | 15-03-2019 | 100 | 1.45 |  |  |  |
| 10 | Nallalam 220kV SS - Downstream works | 3.5 |  | 43891 | 50 | 1.2 |  | 18-19 | 20-21 | 50 | 1.20 | 10 | 2.00 |  |
| 11 | Ambalavayal 66 kV SS and TLs | 12.56 | 2017-18 | 2018-19 | 70 | 8.792 | 12.56 | 2017-18 | 2019-20 | 27 | 1.01 | 63 | 2.59 |  |
| 12 | Kaniyambetta - Kuthumunda 66kV SC to DC TL | 12.37 | 2017-18 | 2018-19 | 70 | 8.659 | 12.37 | 31-1-2017 | 15-5-2019 | 60 | 8.52 | 100 | 10.50 |  |
| 13 | Kalpetta 33kV - Cap Enht - 8 MVA TF (IPDS) | 0.53 | 2017-18 | 2018-19 | 70 | 0.371 | 0.743 | 3/3/2019 | 3/31/2019 | 100 | 0.74 |  |  |  |
| 14 | Reconductoring of KuthumundaUppatty DC line | 0.972 | 2019-20 | 2019-20 | Nil | Nil | 0.16 | 10-10-2019 |  | Nil | Nil | Nil | Nil |  |
| 15 | Nallalam 220kV SS Cap Enht - Power transformers | 17.21 |  | 5/1/2019 | 35 | 6.12 |  | 18-19 | 20-21 | 35 | 6.12 | 40 | 6.19 |  |
| 16 | Kuttikkattur SS Upgradation to 110kV | 8 |  | 6/1/2019 | 0.05 | 0.3 |  | 7/1/2018 |  | 5 | 0.30 | 20 | 0.30 |  |
| 17 | Nallalam 220kV SS - Downstream works | 3.5 |  | 3/1/2020 | 50 | 1.2 |  | 18-19 | 20-21 | 50 | 1.20 |  |  |  |
| 18 | Meppayur 110kV SS Cap Enht - 2x12.5MVA TF | 2.67 | 2017-18 | 2019-20 |  |  | 2.9 |  |  |  | 0.46 | 0.57 | 0.47 |  |
| 19 | 33KV Substation Melady – Replacement of 33/11KV 5MVA TF with 8MVA TF | 0.093 | 2018-19 | 22/8/2019 | Commisioned | 0.09 |  |  |  |  |  | 1 | 0.07 |  |
| 20 | 33KV Substation Balussery – Replacement of 33/11KV 5MVA TF with 8MVA TF | 0.093 | 2018-19 | 23/9/2019 | Commisioned | 0.09 |  |  |  |  |  | 1 | 0.07 |  |
|  | New works |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | New 11kV outlet from Ambalaparamba substation | 0.11 |  | 2019-20 |  |  |  |  |  |  |  |  |  |  |
| 2 | Alternate feeding arrangement to Vellannur 33kV S/s from Kunnamangalam S/s | 6.21 |  | 2019-20 |  |  |  |  |  |  |  |  |  |  |
|  | Sub Total -Ongoing works |  |  |  |  |  |  |  |  |  | 12.90 |  |  |  |
|  | Sub Total -New works |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | System Operation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | DPLCC, Prot Coupler Etc - MDA – PKD & KKM-KHD | 0.4773 | 2017-18 | 2018-19 | 75 | 0.4655 | 0.4773 | 2017-18 | 2019-20 | 0 | 0.00 | 100 | 0.01 |  |
| 2 | SDH for FOC - (OPGW-DWSM) Etc | 0.8919 | 2017-18 | 2018-19 | 75 | 0 | 0.8919 | 2017-18 | 2019-20 | 50 | 0.00 |  | 0.89 |  |
| 3 | Kattakada Substation – GPS System | 0.02 | 2017-18 | 2018-19 | 75 | 0.015 | 0.0283 | 2017-18 | 2019-20 | 100 | 0.01 |  |  |  |
| 4 | OFC & OPGW - Mylatty, Talipba and Nileswar SS | 3.77 | 2017-18 | 2018-19 | 75 | 2.8275 | 3.77 | 2017-18 | 2018-19 | 100 | 0.94 |  |  |  |
| 5 | Mini RTU for Small Hydro Electric Power Stations | 0.2704 | 2017-18 | 2018-19 | 50 | 0.2328 | 0.2704 | 2017-18 | 2019-20 | 50 | 0.23 | 100 | 0.04 |  |
| 6 | PDH Equipments | 2.31 | 2017-18 | 2018-19 | 75 | 1.7325 | 1.33 | 2017-18 | 2019-20 |  | 0.00 | 100 | 1.33 |  |
| 7 | Power Quality Analyser for Kannur &Kalamassery |  |  |  |  |  | 0.1055 | 2018-19 | 2019-20 |  |  | 100 | 0.11 |  |
| 8 | SLM for SOCs (Kannur, T’puram and Klsy) | 0.3452 | 2017-18 | 2018-19 | 75 | 0.2589 | 0.3357 | 18.05.2019 | 2019-20 |  | 0.00 | 100 | 0.35 |  |
| 9 | OFC (ADSS) etc -Sholayar and Poringal | 1.124 | 2017-18 | 2018-19 | 75 | 0.843 | 1.124 |  |  |  |  | 85 | 0.00 |  |
| 10 | Dam Level Monitoring System 7 locations | 0.185 | 2017-18 | 2018-19 | 0 | 0 | 0.185 | 2015-16 | 2019-20 | 0 | 0.00 | 80 | 0.00 |  |
| 11 | Digital ProtCoupler& PLCC – K’KulamSch& 3 SS | 1.035 | 2017-18 | 2018-19 | 75 | 0.77625 | 0.7599 | 2018-19 | 2019-20 | 75 | 0.00 | 100 | 0.76 |  |
| 12 | ADMS for 322 Substations - PSDF Scheme. |  |  |  |  |  | 5.1389 | 2018-19 | 2019-20 |  |  | 10 | 0.37 |  |
| 13 | Kalamassery SLDC building Lift replacement | 0.1834 | 2017-18 | 2018-19 | 75 | 0.13755 | 0.165 | 2018-19 | 2019-20 | 0 | 0.00 | 50 | 0.00 |  |
| 14 | Edappon Com SbDvn - 2nos of O4LC card | 0.010486 | 2017-18 | 2018-19 | 75 | 0.007864 | 0.010486 | 2017-18 | 2018-19 | 100 | 0.00 |  |  |  |
| 15 | Kannur SOC Purchase of 6 DCDB Panel | 0.04 | 2017-18 | 2018-19 | 75 | 0.03 | 0.04 | 2017-18 | 2018-19 | 100 | 0.01 |  |  |  |
| 16 | Purchase of Battery 48V,100Ah/200Ah | 0.125 | 2017-18 | 2018-19 | 75 | 0.09375 | 0.125 | 2017-18 | 2018-19 | 100 | 0.03 |  |  |  |
| 17 | Purchase of Battery 48V,50A | 0.1155 | 2017-18 | 2018-19 | 75 | 0.086625 | 0.1155 | 2017-18 | 2018-19 | 0 | 0.03 |  |  |  |
| 18 | RTU Ambalathara work Part( M/s spectron) |  |  |  |  |  | 0.2229 | 20.12.2017 | 2019-20 | 75 | 0.00 | 100 | 0.22 |  |
| 19 | DPC work Part Knhrd,Ampl, Mylty(M/s ZIV) |  |  |  |  |  | 0.0118 | 2018-19 | 2019-20 | 0 | 0.00 | 100 | 0.01 |  |
| 20 | DPC AKD, SRR(M/s ZIV) |  |  |  |  |  | 0.0509 | 7.03.2019 | 2019-20 |  |  | 100 | 0.05 |  |
| 21 | Waves charger spares( M/s Waves) |  |  |  |  |  | 0.0223 | 2018-19 | 2019-20 |  |  | 100 | 0.02 |  |
| 22 | Video conference facility at GISS Gandhi Road( M/s Twisted pair) |  |  |  |  |  | 0.0035 | 2018-19 | 2019-20 |  |  | 100 | 0.00 |  |
| 23 | 6 Nos. AC( M/s Nikshan) |  |  |  |  |  | 0.0182 | 2018-19 | 2019-20 |  |  | 100 | 0.02 |  |
| 24 | GPRS modem |  |  |  |  |  | 0.0072 | 2018-19 | 2019-20 |  |  | 100 | 0.01 |  |
| 25 | Supply of battery sets |  |  |  |  |  | 0.1 | 2018-19 | 2019-20 | 0 | 0.00 | 100 | 0.10 |  |
| 26 | Battery chargers( M/s waves) |  |  |  |  |  | 0.13 | 2018-19 | 2019-20 | 0 | 0.00 | 100 | 0.13 |  |
| 27 | Installation, Testing and Commissioning of Digital Protection Coupler and PLCC with PC for Pallom and Kayamkulam |  |  |  |  |  | 0.0572 | 2017-18 | 2019-20 | 40 | 0.00 | 100 | 0.06 |  |
| 28 | TOD Meter(Klsy and Knr) |  |  |  |  |  | 0.0638 | 2018-19 | 2019-20 |  |  | 100 | 0.06 |  |
| 29 | Spare Protection Coupler Cards (GE Alstom make) |  |  |  |  |  | 0.0537 | 2018-19 | 2019-20 |  |  | 100 | 0.05 |  |
| 30 | Purchase of 48V,100Ah/200Ah Battery |  |  |  |  |  | 0.084 | 2018-19 | 2019-20 |  |  | 100 | 0.08 |  |
| 31 | Battery Charger 48V,50 Amp |  |  |  |  |  | 0.0995 | 2018-19 | 2019-20 |  |  | 100 | 0.10 |  |
| 32 | Replacement of VRLA Battery -SCADA SD TVM |  |  |  |  |  | 0.0135 | 2018-19 | 2019-20 |  |  | 100 | 0.01 |  |
| 33 | Purchase of spare card for DPC For EMPC feeder |  |  |  |  |  | 0.0414 | 2018-19 | 2019-20 |  |  | 100 | 0.04 |  |
| 34 | Suplyinstallation,testing and commissioning of Digital protection couplers and PLCC with PC Kayamkulam Transmission Scheme |  |  |  |  |  | 0.7599 | 12.06.2018 | 2019-20 |  | 0.00 | 100 | 0.76 |  |
| 35 | Purchase of Portable SLM-cum-Oscillator at Moozhiyar |  |  |  |  |  | 0.1119 | 2018-19 | 2019-20 |  |  | 100 | 0.11 |  |
| 36 | Purchase of fixed wireless phones |  |  |  |  |  | 0.0066 | 2018-19 | 2019-20 |  |  | 100 | 0.01 |  |
| 37 | Purchase of spare cards for the Digital PLCC panel (ABB ETL 42) installed at 220kV Pothencode and Kattakada substations of the Pothencode-Kattakada 220kV feeder- Rs.670000 |  |  |  |  |  | 0.067 | 2018-19 | 2019-20 |  |  | 100 | 0.07 |  |
| 38 | Purchase of Single Phase Relay test kit |  |  |  |  |  | 1.03 | 11.10.2019 | 10.01.2020 |  |  | 0 | 0.00 |  |
| 39 | CB Timing Kit PET TVM |  |  |  |  |  | 0.1145 | 13.05.19 | 2019-20 |  |  | 0 | 0.00 |  |
| 40 | 3 Phase Relay Test Kit |  |  |  |  |  | 0.3538 | 30.01.2019 | 2019-20 |  |  | 100 | 0.35 |  |
| 41 | Purchase of measuring equipments |  |  |  |  |  | 0.0027 | 2019-20 | 2019-20 |  |  | 100 | 0.00 |  |
| 42 | HV cable for IR tester |  |  |  |  |  | 0.0043 | 2019-20 | 2019-20 |  |  | 100 | 0.00 |  |
| 43 | CB Timing Kit PET Kannur |  |  |  |  |  | 0.0156 | 2019-20 | 2019-20 |  |  | 0 | 0.00 |  |
| 44 | GPS |  |  |  |  |  | 0.0346 | 2019-20 | 2019-20 |  |  | 100 | 0.03 |  |
| 45 | Frequency protection Relays |  |  |  |  |  | 0.0058 | 2019-20 | 2019-20 |  |  | 100 | 0.01 |  |
| 46 | Clamp Meter |  |  |  |  |  | 0.0355 | 2019-20 | 2019-20 |  |  | 100 | 0.04 |  |
| 47 | Micro Ohm Meter PET Kannur |  |  |  |  |  | 0.0924 | 2019-20 | 2019-20 |  |  | 100 | 0.09 |  |
| 48 | Multi Meter |  |  |  |  |  | 0.002 | 2018-19 | 2019-20 |  |  | 100 | 0.00 |  |
| 49 | Subtotal -Ongoing |  |  |  |  |  |  |  |  |  | 1.03 |  |  |  |
| 50 | New Works |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 51 | Purchase of LMU-LMDU and Co-axial cable(22sets LMU-LMDU and 1950 mtr cable) |  |  |  |  |  | 0.5805 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 52 | Analog PLCC Panel |  |  |  |  |  | 0.26 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 53 | Purchase of two number of PLCC Panels with two channel protection coupler for 220kV Sabarigiri-Theni feeder and Idulli-Udumal |  |  |  |  |  | 0.115 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 54 | Implementation of Integrated Communication Management System with work flow automation |  |  |  |  |  | 0.15 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 55 | Other Purchase/works from SOC |  |  |  |  |  | 0.81825 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 56 | Purchase of Differential & Distance Relay for Relay Divisions(122 Distance and 84 differential) |  |  |  |  |  | 0.7923 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 57 | Purchase of High voltage DC test kit |  |  |  |  |  | 0.6 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 58 | Line Differential protection Relays For PCOD(PGCIL 1,2,3,4) |  |  |  |  |  | 0.22 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 59 | Conversion of Edamon 110kV bay to Digital |  |  |  |  |  | 1.25 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 60 | Implementation of Integrated Protection Management System with work flow Automation |  |  |  |  |  | 0.15 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 61 | Line impedence measurement unit |  |  |  |  |  | 0.1357 | 20.09.19 | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 62 | Megger make Digital insulation tester(buy back scheme |  |  |  |  |  | 0.05 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 63 | Other Purchase/works from SOC |  |  |  |  |  | 0.3395 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 64 | Renovation of Office of CE(SO) |  |  |  |  |  | 0.1 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 65 | Other SOC & TNMS works |  |  |  |  |  | 0.4822 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 66 | Upgradtion of SCADA beyond 2011 Works under the scope of M/s PGCIL KLSY & KSEBL |  |  |  |  |  | 0.0864 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 67 | Modernisation of MT & SOC office |  |  |  |  |  | 0.0503 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 68 | Procurement of SLM and Osilloscope |  |  |  |  |  | 0.668 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 69 | Procurement of Protection coupler panel for Chalakudy- MDKA and CHKY- LP link,Aluva- Pallikkara and BRPM-Kaloor link |  |  |  |  |  | 0.24 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 70 | Digital Protection Coupler for 220kV Pothencode - Kattakada # 1, 2 220kV Kattakada- Vizhinjam # 1, 2 |  |  |  |  |  | 0.1536 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 71 | Digital Protection Coupler for Trivandrum PGCIL - Pothencode 220kV(8 Nos) and CSD Arekode(2 Nos) |  |  |  |  |  | 0.276 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 72 | OPGW Laying work Moozhiyar, Kochupamba -Thriveni (27 km) |  |  |  |  |  | 1.2 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 73 | Procurement of 48V 200AH Plante type Battery Set |  |  |  |  |  | 0.07 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 74 | Procurement of 48V 400AH VRLA type Battery Set |  |  |  |  |  | 0.1 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 75 | Procurement of 48V, 100A SMPS Battery Charger |  |  |  |  |  | 0.13 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 76 | Procurement of Power Quality Analyzer for transducers(Communication) |  |  |  |  |  | 0.085 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 77 | Procurement of IP Phones |  |  |  |  |  | 0.072 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 78 | Purchase of spare cards for the Digital PLCC panel (ABB ETL 600) installed at 220kV Kundara and 110kV Parippally substations of the Kundara - Parippally 110kV feeder |  |  |  |  |  | 0.061 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 79 | Firewall and License |  |  |  |  |  | 0.06 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 80 | Povision for spare cards for RTUs, Battery Chargers |  |  |  |  |  | 0.15 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 81 | Purchase of 48V, 50A SMPS Battery Charger for Transgrid Project |  |  |  |  |  | 0.1 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 82 | Procurement of ETL 42 Spare cards of ABB Panel |  |  |  |  |  | 0.1 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 83 | Procurement of Protection coupler panel for Idukki-Kothamangalam link |  |  |  |  |  | 0.06 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 84 | PLCC Panel, Wave Trap, Coupling capacitor, LMU and LMDU for Kothamangalam end of Bhoothathankettu SHEP |  |  |  |  |  | 0.115 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 85 | Primary Current Injection kit |  |  |  |  |  | 1.05 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 86 | Multifunction Commissioning Kit with Primary Injection facility |  |  |  |  |  | 0.53 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 87 | Purchase of Spare relays |  |  |  |  |  | 0.65 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 88 | Procurement of 15 kV Digital insulation tester with digital and Analog display |  |  |  |  |  | 0.26 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 89 | Single phase Rlay test kit, RSD,PKD and RSD MDKTRA ,RSD Pallom |  |  |  |  |  | 0.613 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 90 | GPS MODULE for existing OMICRON Kit |  |  |  |  |  | 0.12 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 91 | Purchase of Energymeter testing & calibrating kit (with Phantom loading facility) |  |  |  |  |  | 1.1 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 92 | Three phase relay test kit with provision for digital substation teting |  |  |  |  |  | 1.76 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 93 | CT Analyser |  |  |  |  |  | 0.93 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 94 | Three phase DCRM test kit(CB Analyser) |  |  |  |  |  | 0.75 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 95 | 160kVAC Hi-pot test kit |  |  |  |  |  | 0.35 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 96 | Testing solution for IEC 61850 SAS |  |  |  |  |  | 0.3 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 97 | Transformer Turns Ratio and Winding Resistance Measurement kit |  |  |  |  |  | 0.9 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
| 98 | Procurement of new spare Tan delta measurement kit for use under SOC Kannur, TVM |  |  |  |  |  | 1.4 |  | 2020-21 | 0 | 0.00 | 0 | 0.00 |  |
|  | Subtotal-New |  |  |  |  |  |  |  |  |  |  |  |  |  |

Appendix 2: ADDITIONAL CAPITAL INVESTMENT PLAN OF SBU-TRANSMISSION FOR THE REMAINING YEARS OF THE CONTROL PERIOD

Kerala State Electricity Board Limited (KSEBL), is an integrated State Public Sector power utility in the State of Kerala, performing the three functions of Electricity Generation, Transmission, and Distribution through three Strategic Business Units (SBUs) with SBU-T carrying out the function of State Load Dispatch Centre also.

As per the second transfer scheme, it is the function of the State Transmission Utility to ensure development of an efficient, co-ordinated and economical system of intra-state transmission lines for smooth flow of electricity from a generating station to the load centres.  Further, the second transfer scheme entrusts the responsibility on the STU to develop and execute long term plans for evacuation and supply of power at voltages of and above 33KV, in consultation and co-ordination with the other SBUs and under the policy framework developed by KSEB Ltd. so as to satisfy the present and future needs to the generation and distribution SBUs. The SBU-T handles the total energy sold to consumers and licensees within the state, power drawn by open access consumers and the small quantum of energy sold outside the state.

Transmission system is the backbone of the power system.  The growth of transmission system should match with the growth of generation capacity in the State and ideally it must be ahead of generation both in time and capacity to avoid congestion or bottling up of power. Efficient operation of transmission system in terms of providing reliability, avoidance of disturbance, maintaining voltage level and reducing transmission losses requires continuous strengthening of transmission system.

The transmission planning by KSEBL is done for achieving the above objective and also to provide 24 x 7 power supply to all consumers with n-1 and n-1-1 and n-2 reliability as per CEA Transmission planning criteria and CEA (Grid Standards) Regulations, 2010 as amended from time to time. Further, the transmission planning inside the State has to move ahead synchronously with generation addition and development of regional and inter regional transmission planning. Development of transmission system must match with generating capacity on one side and growing demand on the other side. With Open Access in transmission, the role of transmission has changed from a mere infrastructure to an enabler in operation of a competitive power market.

Investments in transmission are made with prudence and benefits are socialized. In addition to the financial benefit as evaluated through IRR computation, there are other intangible benefits on account of realization of the planned elements including the benefits on account of better capacity utilization and consequently higher energy yield from generating stations, opportunity financial gains on account of transmitting additional power through the strengthened network to meet additional loads etc. which cannot be quantified.

Thus, for transmission projects, though the initial investment cost appears to be high and financial benefit lower, the benefit due to the project available in the long run including intangible benefits is manifold which spans for more than 35 years from the date of commissioning.

Limitations of the present Intra state transmission network

The presently available intra-state transmission system in the State is analyzed to be insufficient for catering to the current demand in an unconstrained manner. There were very little additions in the state in 220 and 400kV level since 1992   and the infrastructure created is not sufficient to meet the increasing load growth. With the projected load in the coming years and the existing transmission network, there can be serious consequences as submitted below:

- Absence of additional capacity will lead to extreme low voltage pockets and chances of system collapse. Analysis carried out indicate that the voltage profile in Malabar area is even below the statutory requirement under the present loading conditions and is observed to reach an extreme low value under the horizon scenario studied with a projected demand of 4800MW.

- Under utilization of assets due to de-rating resulting in financial loss.

- The peak load system loss will increase heavily causing huge financial loss.

The planning criteria mandated by the Central Electricity Authority requires that the transmission network should not be subjected to any constraints like overloading or under voltage consequent to an [n-1] condition like the loss of any one circuit of a double circuit feeder or one transformer of a multi transformer installation. It also states that the transmission system shall meet ‘N-1-1’ criteria also, wherein after suffering single contingency (N-1), grid is still vulnerable to experience second contingency, though less probable (‘N-1-1’), wherein some of the equipment's may be loaded up to their emergency limits. The present day transmission system in KSEBL is found to be not fully complying with these criteria and is analyzed to be deficient in meeting  the current demand in a secure and reliable manner as well as extremely inadequate to meet the projected future demand.

Consequent to the formation of S3region for Kerala control area, the import capability (ATC) of the state will be assessed periodically based on which sanction for Long Term and Medium Term Open Access will be granted for the import of power from outside the State. The ATC in-turn depends on the transmission capability of the intra-state network to transmit the power in an unconstrained manner satisfying all the statutory planning and operational criteria as laid out in Central Electricity Authority’s planning criteria and Grid code respectively. Any constraints like low voltages or security issues violating the contingency criteria consequent to the absence of a strong and stable transmission network inside the state will lead to the reduction of the import capability. Therefore the augmentation of intra state transmission network is essential.

To achieve the above objective, SBU-T has evolved a multiyear capital expenditure plan which is grouped as follows:

- Ongoing  projects & New projects costing less than Rs.10Cr

- Normal capital works (above 10Cr) proposed in the control period 2018-19 to 2021-22

- Transgrid works.

- SLDC related capital works.

The Multiyear capital expenditure plan for the period 2018-19 to 2021-22 was submitted before Hon’ble Commission along with the Multiyear ARR petition on October 30, 2018.

In addition to the capital investment already submitted before Hon’ble Commission, following new works are planned for the control period, the details of which are submitted below. The DPR of these works are submitted along with this petition. The following works are categorized under Normal works above Rs.10Cr.

- Construction of 110/11kV Substation at Vengara

KSEBL, is considering Capacity Enhancement, Upgradation, Renovation and Modernization (R&M), and new proposals for elements in the Transmission system.  The present project is aimed for improving the transmission system in and around Kadampuzha and nearby areas

“110kV Substation, Vengara  ” project envisages  construction of 110/11kV substation with 2 x 12.5 MVA transformers and the construction of 8 km 110 kV LILO line from Kizhissery-Malappuram 110 kV line ( 1KIML1)to the proposed Vengara substation site.

The project is expected to facilitate the industrial and commercial development of Vengara and Oorakam grama panchayaths and nearby areas and to meet future demand, improve the quality and reliability of supply to about 3.5 Lakh people.

The estimated cost of the project is Rs 24 Cr and is expected to be commissioned by 2021-22.

- Construction of 110KV S/S at Adivaram

At present the Electrical section Puthuppady is fed from 66 kV substation Thamarassery through 11 kV Puthuppadi feeder, 11 kV Kuppayakode feeder and 11 kV Adivaram feeder. 11 kV Puthuppadi feeder feed Poolode, Kakkavayal, Kannappankundu and Valliyad area and 11 kV Kuppayakode feeder caters the load of   Kalappuram, kannoth area and Adivaram feeder feed  Eangapuzha town, Kaithapoyil area, Adivaram town, chippilithode and Nooramthode area. During shut down of Adivaram 11kV feeder, Engapuzha town area is  back fed via 11kV  Kuppayakode feeder through Kalapuram AB. Presently in this area there are about 8000 consumers and 19 transformers (100kVA transformers- 13no, 160kVA transformer- 1no, 250kVA transformer- 1Nos and 25kVA transformer-4Nos) of Puthuppadi section area. Also the Kuppayakode feeder feed 42 transformers (160 kVA transformers- 2 Nos, 100 kVA transformers-33 Nos, and 25 kVA transformers 7 Nos) under Electrical Section,  Kodenchery before reaching Kalappuram area, this feeder covers about 24 kms of thickly vegetated and hilly areas under Kodenchery section before reaching Kalappuram and hence break down of feeder and supply interruption is more in this area. As there is no substation in that area, the back feeding of this feeder is not possible during shut down of 66 kV Substation Thamarassery. A new 110kV substation in Adivaram envisages an integral development of the transmission & distribution system in this area. The scope of work includes the following:

Construction 110kV substation at Adivaram with

- two Nos of 110 kV feeder bays

- 1x12.5 MVA 110/11 kV Transformers and 0.5 km 110 kV DC line.

The estimated cost of the project is Rs 11.50 Cr and is expected to be commissioned by 2020-21.

- Construction 110 kV Substation,  Kadampuzha

The project “110kV substation, KADAMPUZHA ” contains construction of 110/11kV substation with 2 x 12.5 MVA transformers and the construction of 4.5 km 110 kV LILO line from Malaparamba - Kuttippuram 110 kV line to the proposed Kadampuzha substation site..

The project is expected to facilitate the industrial and commercial development of Kottakkal Municipality and nearby areas Marakkara and Edayur grama panchayath and to meet future demand, improve the quality and reliability of supply to about 3.75 Lakh customers

The growth of Load in Kottakkal, Edayur, Puthanathani and Kadampuzha towns and surrounding areas are expected to increases rapidly in the coming years due to commercial establishments and residential loads.

These areas are now fed by six 11kV feeders, viz. 11kV Puthanathani feeder, 11kV Kadampuzha feeder, 11 kV Edayur from 110kV Substation, Kuttippuram, 11kV Chenakkal feeder and 11 kV Parappur feeder from 110 kV Substation, Edarikode, 11kV Vattalloor feeder from 33kV Substation, Makkarapparamba. Since all the above feeders are over loaded, interruption due to routine maintenance and feeder faults will affect a large number of consumers for long time. This situation can be avoided by constructing the proposed substation.

The estimated cost of the project is Rs 19.80 Cr and is expected to be commissioned by 2021-22.

- Up gradation of Mavelikkara - Pallom 66kV DC

The work involves upgrading 41km of existing 66kV Pallom Mavelikara DC line and Changanassery 66kV substations to 110kV standards with corresponding bay upgradation at Pallom and Mavelikara Substations.

Currently the station load at 66kV side of Thiruvalla, Chumatra and Changanasery is 108A,80A and145A respectively. Hence the total load on the feeders is around 333A  which implies a corresponding MVA rating of  38.45MVA. On upgrading to 110kV standard, the 333A at 66kV level will correspondingly reduce to 200A. With this, we can arrive that the power loss at 66kV level is  around 2.7 times that at 110kV.

The scope of work includes bay upgradation of 66KV substation, Changanachery, upgradation of 66KV system to 110KV at 220KV Substation, Pallom, upgradation of 66KV – 6TVMV#1 and 6TVMV#2 bays to 110KV bays at 110KV substation, Mavelikara, upgrdation of 19.74 km Pallom-Mavelikara 66KV DC line to 110KV , upgradation of 21.26KM Pallom-Mavelikara 66KV DC line to 110KV.

The estimated cost of the project is Rs.68.35 Crore and is expected for commissioning by 2021-22.

- Construction of 110KV DC line Kattappana  -  Peerumedu

The work involves construction of two 110 KV feeder bays each at Kattappana and Peerumedu substations for terminating the line. The line part involves construction of 36 KM 110 KV DC line from Kattappana substation to Peerumedu substation.With this the excess power available at existing and upcoming Muthirapuzha group generating stations during wet seasons can be evacuated to Peerumedu, Vandiperiyar and the nearby substations in Pallom – Peerumedu line. Power evacuation of existing wind project and upcoming wind – solar hybrid projects at Ramakalmedu and nearby areas can also be done with this interlinking. Also the proposed 220 kV Kuyilimala substation can be fully utilized by loading to peerumedu area. Feeding of Kuyilimala substation is proposed from the Idukki – Udumulpet 220 kV line. This line will become power rich after commissioning of PES and Upper Sengulam projects. Hence its evacuation will be easier with Kuyilimala substation and Kattappana – Peerumedu line. Thus this proposed line is an interlinking between major source point and major load point. Also with this line back feeding facility will be available from Peerumedu side to Vazhathoppu, Nedumkandam and Kattappana substations and vice versa. With this it will be very easier to maintain uninterruptable power supply at Pallom – Peerumedu – Moozhiyar belt during overload at Sabarimala festival season. The line is proposed to be constructed as 110 KV DC line after converting all associated substations to 110 KV.The estimated project cost is Rs. 40.7 Cr and the project is expected for CoD by 2021-22.

- Up gradation of 66KV Sasthankotta-Chavara DC line to 110KV

At present, the 110kV Substation Chavara is fed from 220kV substation Kundara and from 110kV substations Sasthamcotta through KMML, an EHT consumer. The 110kV Kavanad Substation is fed from 110kV Chavara substation. There is no direct feeding to 110kV Chavara Substation from 110kV Sasthamcotta substation. If any fault occurs at 220kV Substation kundara, the Chavara, KMML and Kavanadu 110 KV Substations has to be fed from Sasthamcotta  Substation. By the up gradation of this proposed line, we can provide 2 Nos. feeders extra to Chavara Substation and hence the supply at the Chavara Substation will become more stable which in turn benefit KMML and Kavanadu Substation. More over the proposed site for the 110 KV Substation, Thevalakkara is very near to this proposed Sasthamcotta - Chavara line and can be tapped very easily. This will improve the voltage profile and load restrictions in Thevalakkara and near by areas. There will be a load growth in  near future in kollam, kavanad area due to the development of Kollam- Kavanad bypass  and by the up gradation of  this line, Chavara, Kavanad substations will become more stable to meet the load requirement. Also this will benefits for the new proposal for interlinking of 110kV Kavanad Subatation and 110kV Perinad substations. Also a 50MW solar project is proposed at west kallada by NHPC. This power is proposed to be evacuated through the 110kV Kundara – Chavara KMML feeder Hence to improve the stability and reliability of Sasthamcotta, Chavara, KMML, Kavanad Substations, this upgradation is essential. The estimated project cost is Rs.21.85 Cr and the anticipated CoD is 2020-21.

- Up gradation of 66KV Edappon-Kozhencherry SC line to 110KV DC

This project comes under the downstream work of Transgrid project.  The downstream work  is the up-gradation of existing 66kV D/C Edappon-Kozhencherry feeder to 110kV D/C.The 66kV Edappon-Kozhencherry D/C line is lying idle and disconnected from both Edappon and Kozhenchery substations for more than 8 years, with the gantry arrangements of feeders at both stations decommissioned; consequent upon the upgradation of Kozhenchery and Ranni Substations to 110kV voltage level. Kozhenchery and Ranni Substations are now fed from Pathanamthitta Substation through Pathanamthitta – Kozhenchery - Ranni Double Circuit lines. Kakkad power house and other small hydel stations in the Pamba basin are also connected to the 110kV Bus of Pathanamthitta Substation.This work also include the construction of two numbers 110kV feeder bays at  Edappon and Kozhenchery Substations  after dismantling the existing isolated 66kV bay. The estimated project cost is Rs.18.35 Cr and the project is expected for CoD by 2020-21.

- Construction of 110KV Substation, Thiruvali

The scope of the project includes

- Construction of 2 Nos 110kV  Feeder Bays, 2Nos Transformer Bays,

- installation of 2Nos 12.5MVA 110/11kV Transformers.

- LILOing Elamkur-Nilambur 110kV line

For providing alternate 11kV feeders to the scheme  area and for providing back up support to 110kV network of 220kV Substation, Elamkur , construction of 110kV Substation,Thiruvaly is essential and it is proposed to construct 110kV Substation , Thiruvaly  by LILOing  Elamkur-Nilambur 110kV line by installing 2x12.5 MVA transformers,  considering the reduction in Peak Load System loss , additional load expected in the area and the relief in the loading of transmission elements in the vicinity . The estimated project cost is Rs.12.50 Cr and the anticipated CoD is 2020-21.

- Construction of  110KV Substation, Thimiri

The scope of work includes

- Construction of 110kV Substation, Thimiri  by constructing

- 5.5km of 110kV DC LILO line from 110kV Payyannur – Cherupuzha 110kV feeder 1  (1PYCP-1 ) at Thattummal to Thimiri  using Panther

- Construction of 2Nos. of 110kV Feeder   bays,

- 2Nos. of Transformer Bays

- 1No. of 110kV Bus coupler bay

- 6 Nos. of 11kV Outgoing feeders

The project is expected to facilitate the industrial development and meet future demand in Alakode, Mathamangalam, Nadukani etc. area and improve the quality and reliability of supply to about 2.5 Lakh customers in the Town and 1.5 Lakh consumers in Alakode and Nadukani substation supply area. Since the population growth in this region is increasing day by day, construction of new 110kV Substation is inevitable to avoid future load problems and interruptions.

The estimated cost of the project is Rs.20.87 Cr and is expected to be commissioned by 2021-22.

- Construction of 66kV Substation atMunnar , 33kV Substation Marayoorand associated lines

The scope of work includes construction of 66KV Substation, construction of 66KV substation, Munnar & associated 66KV DC line, 33KV substation, Marayoor and associated 33KV DC line.  The estimated cost of the project is Rs.15.79 Cr and expected to be commissioned by 2021-22.

- Kuthunkal Nedumkandam 110 kV DC line  Project

The proposal envisages linking Kuthunkal – Neriyamangalam 110 kV line to 66 kV Nedumkandam substation by construction of  17 km 110 kV DC line and installation of 40 MVA 110/66 kV transformers at Nedumkandam substation  in Idukki district under Transmission circle Thodupuzha. At present 66 KV supply to Vazhathoppu, Nedumkandam and Kattappana substations is feeding from the 50 year old Sengulam – Moolamattom 66 KV SC feeder and its tap line to Kattappana. In the line at Kuyilimala there is a switching station from which either Sengulam or Moolamattom supply is feeding to the three substations. The total peak load of the three substations is more than 240 A and conductor snapping was frequent since the line is constructed using ACSR MINK conductor of capacity 167 A. Due to this the Sengulam – Kuyilimala portion of the line reconductoring work with ACSR DOG is completed. Moolamattom - Kuyilimala portion reconductoring cannot be easily done since the tower is not strong. Even after reconductoring, the problem is not fully solved since the DOG conductor also is fully loaded. Considering a load growth of 10% in the area the problem will re strike during the coming years. 	Since the present source points (Moolamattom & Sengulam) are far away from the load center (about 70 KM) low voltage complaints are frequent.  This project will help in resolving these issues. The estimated cost of the project is Rs.25.55 Cr and the anticipated CoD is in 2019-20.

- Aluva-Kothamangalam

The scope of work includes up-gradation of   the  existing  66 kV Kothamangalam –Aluva DC feeder  to 110  kV  standard by  replacing  the towers, & existing  copper conductors with ACSR wolf.This is an important tie feeder between 66kV Kothamangalam Substation and Aluva Substation. It is  this  feeder and  the 66Pallivasal -Aluva  feeder;  through which  the  generation of  the  Pallivasal  Station (37.5MW)  is  being evacuated  to  Aluva side. The  66kV Pallivasal- Aluva  feeder is  already  being  upgraded  to  220/110 kV multi-circuit,  by  the  Transgrid. The 66kV  Kothamangalam S/S  is  also being  upgraded  to  220 kV, and  the  work  has  started. Also  since  the  new  Boothathankettu SHEP  is   upcoming, the  evacuation from  this  Station also is  to be considered.   The Boothathankettu SHEP (24MW) is targeted to complete by 2020. As per the Boards  approved long term plan, for evacuation of power above 12 MVA, the voltage level of feeders need to be 66 kV or above. The estimated cost of the project is Rs. 39.60 Crores and expected to commission in 2020-21.

- Construction of 110kV Substation at Murickasery and associated 8KM 110kV line.

The scope of work includes construction of 110KV substation at Murickasery and associated 8KM 110KV line. The estimated cost of the project is Rs.11.6 Cr and the project is expected to commission in 2021-22.

A summary of the additional normal capital works planned for the control period and the proposed outlay are submitted below:

| Table CAPITAL OUTLAY OF ADDITIONAL NORMAL WORKS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Outlay (Amount in Rs. Crores) |  |  |  |  |  |
| No. | Project | 2019-20 | 2020-21 | 2021-22 | Total |
|  |  | Rs.Cr. | Rs.Cr. | Rs.Cr. | Rs.Cr. |
| 1 | Construction of 110K/11kv Vengara S/S |  | 18.26 | 9.98 | 28.24 |
| 2 | Construction of 110KV S/s Adivaram | 7.821 | 9.069 |  | 16.89 |
| 3 | Construction 110 kV Substation, Kadampuzha |  | 14.06 | 9.47 | 23.53 |
| 4 | Upgradation of Mavelikara-Pallom 66KV DC | 0.1 | 2.1 | 39.6 | 41.8 |
| 5 | Construction of 110KV DC line from 66KV substation Kattappana to 66KV substation, Peerumedu |  | 25 | 15.7 | 40.7 |
| 6 | Upgradation of 66KV Sasthankotta-Chavara DC Line |  | 10 | 11.85 | 21.85 |
| 7 | Upgradation of 66KV Edappon-Kozhencherry SC line and associated bays | 3.1 | 12.4 | 5.15 | 20.65 |
| 8 | Construction of 110KV Substation, Thiruvali | 6.2 | 7.21 |  | 13.41 |
| 9 | Construction of Thimiri substation |  | 9 | 11.87 | 20.87 |
| 10 | Construction of Munnar substation and associated lines | 1 | 14 | 7.13 | 22.13 |
| 11 | Kuthunkal-Nedumkandam |  | 11 | 5 | 16 |
| 12 | Aluva-Kothamangalam |  | 20 | 22.49 | 42.49 |
| 13 | 110KV Substation Murickasery | 0.01 | 8 | 3.5 | 11.6 |
|  | Total | 18.23 | 160.10 | 141.74 | 320.16 |

A summary of GFA addition due to the additional works is submitted below:

| Table GFA Addition |  |  |  |  |
| --- | --- | --- | --- | --- |
| No. | Project | 2019-20 | 2020-21 | 2021-22 |
|  |  | Rs.Cr. | Rs.Cr. | Rs.Cr. |
| 1 | Construction of 110K/11kv Vengara S/S |  |  | 28.24 |
| 2 | Construction of 110KV S/s Adivaram |  | 16.89 |  |
| 3 | Construction 110 kV Substation, Kadampuzha |  |  | 23.53 |
| 4 | Upgradation of Mavelikara-Pallom 66KV DC |  |  | 41.8 |
| 5 | Construction of 110KV DC line from 66KV substation Kattappana to 66KV substation, Peerumedu |  |  |  |
|  |  |  |  | 40.7 |
| 6 | Upgradation of 66KV Sasthankotta-Chavara DC Line |  |  | 21.85 |
| 7 | Upgradation of 66KV Edappon-Kozhencherry SC line and associated bays |  |  | 20.65 |  |
| 8 | Construction of 110KV Substation, Thiruvali |  | 13.41 |  |  |
| 9 | Construction of Thimiri substation |  |  | 20.87 |  |
| 10 | Construction of Munnar substation and associated lines |  |  | 22.13 |  |
| 11 | Kuthunkal-Nedumkandam |  |  | 16 |  |
| 12 | Aluva-Kothamangalam |  |  | 42.49 |  |
| 13 | 110KV Substation Murickasery |  |  | 11.6 |  |
|  | Total | 0 | 30.3 | 289.86 |  |

TRANSGRID WORKS

SBU-T had submitted 12 numbers of Transgrid works for approval of Hon’ble Commission in the Capital Investment Plan submitted during October 2018. In addition to this, following new works are also planned for this control period, the details of which are submitted.

Sabari Lines and Substation package

The project involves a comprehensive Sabari Lines and Substations package with a 220kV SCADA enabled GIS substation at Pathanamthitta which would receive power at 220kV level from both 220kV Edappon substation and Sabarigiri – Edamon (SBEM) 220kV lines, each through double circuit feeders. The lines for this substation from Edappon are planned by constructing 16km of MCMV lines through the right of way of Edappon-Adoor 66 kV line and 12.7km of MCMV lines through the right of way of Adoor-Pathanamthitta 66 kV line. The lines from SBEM are LILOed from Padom as 8.2km of new 220kV DC lines with new RoW and 3.42km MCMV line through the RoW of Punaloor-Koodal 110kV line and as 14.5km new MCMV line through the RoW of Koodal-Pathanamthitta 66kV line. The substation planned at Pathanamthitta will have four 220kV feeders, one 100MVA 220/110kV transformer and 110kV cable connectivity to the 110kV yard of Pathanamthitta AIS. The lines portion is estimated at Rs. 141.2 Crore and the substation part is estimated at Rs. 54.1 Crore.

The second part of the project involves construction of a 220kV/110kV SCADA enabled GIS substation at Kakkad with 220kV feeders LILOed from Sabarigiri-Ambalamugal (SBAM) line at Valupara. The line proposed is 220kV SC line of 1.66km through new RoW from Valupara to Kakkad. The GIS substation at Kakkad will have two 220 kV feeders, one 100 MVA 220/110kV transformer and two 110kV feeders one of which providing cable connectivity to the 110kV substation yard at the Kakkad power house. The lines portion is estimated at Rs.6.3 Crore and the substation part is estimated at Rs. 42.4 Crore.

The estimated cost of the project is Rs 244 Cr and is expected to be commissioned by 2021-22.

220/110kV GIS & 220/110kV GIS, Vengallur & Thrissivaperur Line Strengthening Package - Phase II (Kunnamkulam to Vengallur 220/110kV MCMV line)

The project “Vengallur GIS & TLSP Phase II” as mentioned above forms a part of the TransGrid 2.0 Project and consists of following new substations and transmission line project.

- Project A : 110/11kV GIS Vengallur (Execution Phase 1)

Construction of 110/11kV GIS at Vengallur, Malappuram district with station capacity of 2x12.5MVA transformer, 6x110kV Feeders with Double Busbar arrangement and 11kV 10 panel set

- Project B : 220/110kV MCMV line from Kunnamkulam to Vengallur (Execution  Phase 2A)

TLSP Phase II - Construction of 42km 220/110kV MCMV transmission line from Kunnamkulam Substation in Thrissur district to Vengallur in Malappuram district using existing/new RoW

- Project C : 220/110kV GIS Vengallur (Execution Phase 2B)

Construction of 220/110kV GIS at Vengallur, Malappuram district with station capacity of 2x100MVA transformers, 2x220kV Feeders and Double Busbar arrangement (upgradation of the 110/11kV GIS constructed under Project A) will be implemented in Phase 2

The estimated cost of the project is Rs 204.15 Cr and is expected to be commissioned by 2021-22.

Vizhinjam 220/110KV GIS Substation

This project is for the upgradation of the existing 66kV, Vizhinjam substation to a 220kV GIS substation. 220kV GIS is planned at the existing Vizhinjam substation premises with a capacity of 2x100MVA.This project is intended to meet the future power requirement in the southern part and the coastal area of Thiruvananthapuram District. The development of Vizhinjam area with the completion of the International seaport will make the power demand to increase very high. This station will ensure a secure and reliable network satisfying N-1 criteria in this area and there will be a good relief in the loading of the existing feeders.

The southern side and the coastal belt of the Thiruvananthapuram District like Veli, Vizhinjam, Balaramapuram, Neyyattinkara, Muttathara areas will get the feeding from both the 220kV substations Kattakada (existing) & Vizhinjam (proposed). This will mitigate total supply failure in the event of tripping of one circuit of the Pothencode - Paruthippara 110kV DC line. There will be a good relief in the loading of the existing feeders. Moreover considerable increase in the voltage profile can be expected. The proposed 220kV Vizhinjam substation is the only solution for the supply reliability in these areas. The Substation proposed is to achieve the above and the cost is estimated as Rs. 75.00Cr.The project is expected to commission by 2021-22. A summary of the additional TRANSGRID works planned for the control period and the proposed outlay are submitted below:

| Table ADDITIONAL TRANSGRID WORKS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| CAPITAL OUTLAY (Rs.Cr.) |  |  |  |  |  |  |
|  | Name of Work | 2019-20 | 2020-21 | 2021-22 | Expected CoD | Total |
| 1 | Sabari package |  | 122 | 126 | 2021-22 | 248 |
| 2 | Vengallur GIS & TLSP Phase II |  | 136.12 | 68.06 | 2021-22 | 204.18 |
| 3 | Vizhinjam 220/110KV GIS Substation | 0.5 | 26.624 | 43.84 | 2021-22 | 71 |
|  | Total | 0.5 | 284.744 | 229.46 |  | 523.18 |

| Table ADDITIONAL TRANSGRID WORKS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| GFA ADDITION (Rs.Cr.) |  |  |  |  |  |
|  | Name of Work | 2019-20 | 2020-21 | 2021-22 | Expected CoD |
| 1 | Sabari package |  |  | 248 | 2021-22 |
| 2 | Vengallur GIS & TLSP Phase II |  |  | 204.18 | 2021-22 |
| 3 | Vizhinjam 220/110KV GIS Substation |  |  | 71 | 2021-22 |
|  | Total |  |  | 523.18 |  |

The remaining projects are in proposal/design/ approval/ stages, their details can be provided to the Commission as and when the projects are ready for implementation. SBU-T humbly request Hon’ble Commission permission to submit the details of these projects in future.

Hon Commission may please condone any inadvertent error/omission that may have crept in this petition. The petitioner may be given an opportunity to rectify the same detected subsequently. The petitioner may also be allowed to the petitioner to make further submission, addition and alteration to this petition as may be necessary from time to time.

CHAPTER 9: MID YEAR PERFORMANCE REVIEW OF SLDC FOR THE YEAR 2019-20& REVISED ESTIMATE FOR 2020-21 & 2021-22

9.1.	As per Regulation 66(2), the State Load Despatch Centre shall submit separate audited accounts of its business. The Regulation 66 (2) further states that in case separate accounts are not available, the Commission may approve as the Aggregate Revenue Requirement of State Load Despatch Centre, a portion of the approved Aggregate Revenue Requirement of the transmission business of KSEB Limited, based on the proposal submitted by it only for the first year of the Control Period.  In compliance with the same, KSEBL evolved a procedure for segregation of accounts of SLDC. The accounts of SLDC submitted in this petition are based on this procedure.

9.2.	KSEBL had provisionally segregated the accounts of SLDC in the MYT ARR submitted before Hon’ble Commission on October 31, 2018. In the instant petition, the midyear performance of SLDC for the year 2019-20, revised ARR of SLDC for 2019-20 and revised estimate for the years 2020-21 and 2021-22 are submitted below.

Gross Fixed Asset of SLDC

9.3.	The details of GFA addition originally claimed and approved by Hon’ble Commission for SLDC for the years 2019-20 to 2021-22 are submitted below.

| Table 9.1 GFA addition estimated in ARR and provisionally approved (Rs Cr) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Estimated in ARR |  |  | Approved |  |  | Revised |  |  |
| No. | Name of Work | 2019-20 | 2020-21 | 2021-22 | 2019-20 | 2020-21 | 2021-22 | 2019-20 | 2020-21 | 2021-22 |
| 1 | Ongoing projects plus new small works | 7.14 | 0 | 0 |  |  |  | 0.97 | 8.40 | 0 |
| 2 | New projects | 53 | 12 | 212.45 | 53.00 | 12.00 | 212.45 | 0 | 0 | 53 |
|  | Total | 60.14 | 12 | 212.45 | 53.00 | 12.00 | 212.45 | 0.97 | 8.40 | 53 |

9.4	SLDC had submitted before Hon’ble Commission a detailed Capital Investment Plan of SLDC for the control period along with the MYT petition filed on 30th October 2018. The CIP of SLDC miscellaneous  small purchases/works in addition to few major works. The changes made in the major works and the reasons for the same are submitted below:

1.	ADMS Work: The project was planned for an amount of Rs. 7.14 Cr with expected completion in 2019-20.  The completion of the project is shifted to the year 2020-21 due to non availability of supplies and contractors.

2. SAMAST: The DPR of SAMAST work has been prepared and is submitted for PSDF grant. The completion schedule of SAMAST amounting to Rs.53 Cr is shifted to 2021-22.

3.	Reliable Communication & Data Acquisition: The project ‘Reliable Communication & Data acquisition’ amounting to Rs.212.45 Cr is shifted to the CAPEX of SBU-T and accounted under SBU-T GFA. Therefore the same is removed from the CIP of SLDC.

4.	Miscellaneous works: An amount of Rs.12 Cr was included in the CIP of SLDC towards purchase of tools and plants of Relay and communication. Since Relay and Communication wings come under SBU-T, these works are shifted to CIP of SBU-T.

9.5	The GFA of SLDC for each year of the control period is computed based on the asset addition projected for the respective year as per the Capital Investment Plan for SLDC submitted along with the Mid Term Review petition. The revised GFA of SLDC projected for the year 2019-22 is as submitted below.

| Table 9.2 Opening GFA of SLDC for the control period (Rs.Cr.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Asset group | 2018-19 (Actual) | 2019-20 | 2020-21 | 2021-22 |
| 1 | Land & Land rights | 0 | 0 | 0 | 0 |
| 2 | Building and Civil Works | 0.28 | 0.29 | 0.39 | 0.79 |
| 3 | Hydraulic Works | 0.00 | 0 | 0 | 0 |
| 4 | Other Civil Works | 0.00 | 0 | 0 | 0 |
| 5 | Plant & Machinery | 0.29 | 0.48 | 1.24 | 9.22 |
| 6 | Lines Cable Network etc. | 0.00 | 0 | 0 | 0 |
| 7 | Vehicles | 0.00 | 0 | 0 | 0 |
| 8 | Furniture & fixtures | 0.06 | 0.08 | 0.08 | 0.08 |
| 9 | Office Equipment's | 0.03 | 0.07 | 0.10 | 0.10 |
| 10 | Communication equipment | 0.00 | 0 | 0 | 0 |
| 11 | SCADA and IT system | 6.31 | 6.31 | 6.39 | 6.40 |
| 12 | Other equipment | 0.40 | 0.40 | 0.40 | 0.40 |
|  | Total | 7.37 | 7.63 | 8.60 | 17 |

9.6	A comparison of the GFA of SBU-T with the GFA of SLDC for the years 2019-20 to 2021-22 is submitted below.

| Table 9.3 GFA segregation(Rs Cr) |  |  |  |
| --- | --- | --- | --- |
| Item | 2019-20 | 2020-21 | 2021-22 |
| SBU-T |  |  |  |
| Opening GFA** (Rs.Cr.) | 5094.47 | 6425.07 | 8684.75 |
| SLDC |  |  |  |
| Opening GFA (Rs.Cr.) | 7.63 | 8.6 | 17 |
| Ratio of GFA of SLDC to total GFA of SBU-T & SLDC | 0.15% | 0.14% | 0.20% |

**incl  GFA of SLDC

Operation and Maintenance Expenses of SLDC

9.7	Expenditure incurred for the following offices are considered as SLDC expenditure for segregation and for assessing the O&M expenses of SLDC, the details corresponding to the following offices are extracted from SARAS software.

- Main LD station at Kalamassery and Sub LD at Thiruvananthapuram

- SCADA Sub division, Kalamassery and Thiruvananthapuram

- TNMS, Kalamassery

- Office of Chief Engineer, Transmission – System Operation, Kalamassery.

- In the case of repairs and maintenance expenditure, additional amount of Rs. 14 lakhs per year is also included considering the high AMC charges for SCADA equipments  and based on past actual.

9.8	Based on the above methodology adopted for segregation of accounts of SLDC, the O&M expenses of SLDC projected for the control period are given below.

| Table 9.4 O&M expenses of SLDC (Rs Cr) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| As per ARR |  |  |  |  | Revised |  |  |  |  |
| Item | 2019-20 | 2020-21 | 2021-22 | Actual upto Sept-19 |  | 2019-20 | 2020-21 |  | 2021-22 |
| Employee cost | 17.24 | 18.97 | 20.86 | 4.24 |  | 8.18 | 9.84 | 10.82 |  |
| R&M Expenses | 0.62 | 0.69 | 0.75 | 0.32 |  | 0.65 | 0.71 | 0.75 |  |
| A&G Expenses | 1.35 | 1.63 | 1.93 | 0.31 |  | 1.14 | 1.21 | 1.32 |  |
| O&M expenses | 19.22 | 21.28 | 23.55 | 4.87 |  | 9.96 | 11.77 | 12.89 |  |

The details are furnished under S-2 of the SLDC ARR forms.

Pay Revision Expenses

9.9	SLDC is not claiming pay revision expenses along with this ARR petition. However, it is requested that pay revision expenses as and when arising in the control period may be allowed over and above the norms in line with CERC norms and Kerala State Electricity Regulatory Commission (Terms and Conditions for Determination of Tariff) Regulations, 2018.  An estimate of pay revision expenses of SLDCis submitted below. The estimate is same as that submitted in the original ARR petition. The projection of Pay Revision expenses for SLDC segregated based on the ratio of employee cost for the year 2018-19 is as submitted below:

| Table 9.5 Projection of Pay revision expenses (Rs.Cr.) for SLDC |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| SBU |  | 2019-20 | 2020-21 | 2021-22 |
| SBU-T & SLDC |  | 29.78 | 32.18 | 34.71 |
| SLDC | Employee cost ratio for 2018-19 : 1.93% | 0.57 | 0.62 | 0.67 |

Depreciation of SLDC

9.10	In the original ARR petition, the depreciation claim of SBU-T and SLDC were clubbed together. As part of segregating the accounts of SLDC, the depreciation of SLDC for the years 2019-20 to 2021-22are worked out by segregating from the Depreciation of SBU-T based on the GFA ratio of SLDC. The Depreciation of SLDC is submitted below.

| Table 9.6 Segregation of Depreciation of SLDC (Rs Cr) |  |  |  |
| --- | --- | --- | --- |
| Item | 2019-20 | 2020-21 | 2021-22 |
| Depreciation of SBU-T | 193.78 | 255.10 | 313.17 |
| GFA ratio | 0.15% | 0.14% | 0.20% |
| Depreciation of SLDC | 0.28 | 0.34 | 0.60 |

Return on Equity

9.11	 The ROE for SBU-T (including SLDC) is Rs. 119.99 Cr each year during the Control Period. This ROE is apportioned to SLDC based on GFA ratio   as submitted below. The RoE of SLDC is submitted below.

| Table 9.7 Segregation of RoE of SLDC (Rs Cr) |  |  |  |
| --- | --- | --- | --- |
| Item | 2019-20 | 2020-21 | 2021-22 |
| RoE of SBU-T | 119.99 | 119.99 | 119.99 |
| GFA ratio | 0.15% | 0.14% | 0.20% |
| RoE of SLDC | 0.18 | 0.17 | 0.24 |

Interest on Working Capital

9.12	As per Regulation 32(f) of KSERC (Terms and conditions for determination of Tariff) Regulations, 2018, the working capital of SLDC shall comprise of,-

(i) operation and maintenance expenses for one month; plus

(ii) cost of maintenance spares at one per cent of the historical cost ofplant and equipments; plus

(iii) receivables equivalent to State Load Despatch Centre charges forone month.

(2) Interest on normative level of working capital as per this Regulation shall be allowed at a rate equal to two percent higher than the base rate as on the First day of April of the financial year in respect of which the petition for approval of Aggregate Revenue Requirement and determination of tariff is filed.

| Table SLDC : Interest on Working capital (Rs Cr) |  |  |  |  |
| --- | --- | --- | --- | --- |
| No | Item | 2019-20 | 2020-21 | 2021-22 |
| 1 | O&M expenses (as per norms) | 0.83 | 0.98 | 1.07 |
| 2 | Maintenance Spares (as per norms) | 0.08 | 0.09 | 0.17 |
| 3 | Receivables (as per norms) | 0.90 | 1.08 | 1.24 |
| 4 | Total Working Capital | 1.81 | 2.14 | 2.48 |
| 5 | Interest Rate (as per norms) (2% + base rate as on 1-4-2019) | 10.95% | 10.95% | 10.95% |
| 6 | Interest on Working Capital | 0.20 | 0.23 | 0.27 |

Interest and Finance charges

9.13	In the original ARR petition, the Interest and Finance charges of SBU-T and SLDC were clubbed together. As part of segregating the accounts of SLDC, the Interest and Finance charges of SLDC for the years 2019-20 to 2021-22 is worked out by segregating from the I&F charges of SBU-T based on the GFA ratio of SLDC. The  I&F charges of SLDC is submitted below.

| Table 9.8 Segregation of I&F charges of SLDC (Rs Cr) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Item | 2019-20 | 2020-21 | 2021-22 |
| Interest & Finance charges of SBU-T | 138.56 | 270.40 | 414.25 |
| GFA ratio | 0.15% | 0.14% | 0.20% |
| Interest & Finance charges of SLDC | 0.21 | 0.38 | 0.84 |

Interest on GPF

9.14	  The interest on GPF for SLDC for the years 2019-20, 2020-21 and 2021-22 is reproduced in the table below:

| Table 9.9 Segregation of Interest on PF (Rs.Cr.) for SBUT & SLDC |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| SBU |  | 2019-20 | 2020-21 | 2021-22 |
| SBU-T & SLDC | Employee cost ratio for 2018-19 | 20.68 | 22.04 | 23.40 |
| SLDC | 1.93% | 0.42 | 0.45 | 0.47 |

Interest on Master Trust bonds

  - The projection of Interest on Master Trust Bonds for SLDC are segregated based on the ratio of  employee cost for the year 2018-19 is as submitted below:

| Table 9.10 Segregation of Interest on Master Trust for SBUT & SLDC (Rs. Cr.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| SBU |  | 2019-20 | 2020-21 | 2021-22 |
| SBU-T & SLDC |  | 105.59 | 100.98 | 96.37 |
| SLDC | Employee cost ratio for 2018-19 : 1.93% | 2.04 | 1.95 | 1.86 |

Aggregate Revenue Requirement of SLDC

9.16	 The total Aggregate Revenue Requirement of SLDC for the years 2019-20 to 2021-22 is submitted below:

| Table 9.11 ARR of SLDC (Rs.Cr.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Particulars | 2019-20 | 2020-21 | 2021-22 |  |  |
| 1 | Expenses |  |  |  |  |  |
| a) | Operating Expenses |  |  |  |  |  |
| i) | Employee expenses | 8.18 | 9.84 | 10.82 |  |  |
| ii) | Administrative and General Expenses | 0.65 | 0.71 | 0.75 |  |  |
| iii) | Repair and Maintenance Expenses | 1.14 | 1.21 | 1.32 |  |  |
| iv) | Interest on Working Capital | 0.20 | 0.23 | 0.27 |  |  |
| v) | RLDC Fee and Charges (*) |  |  |  |  |  |
| b) | Capital expense components |  |  |  |  |  |
| i) | Depreciation | 0.28 | 0.34 | 0.60 |  |  |
| ii) | Interest and finance charges on term loan | 0.21 | 0.38 | 0.84 |  |  |
|  | Interest on GPF | 0.42 | 0.45 | 0.47 |  |  |
|  | Interest on Master Trust Bond | 2.04 | 1.95 | 1.86 |  |  |
| iii) | Return on equity | 0.18 | 0.17 | 0.24 |  |  |
| iv) | Income Tax provision |  |  |  |  |  |
| 2 | Total Revenue Expenditure (a+b+c) | 13.30 | 15.28 | 17.17 |  |  |
| 3 | Less: Non Tariff income |  |  |  |  |  |
| 4 | Less: Income from other business |  |  |  |  |  |
| 5 | Aggregate Revenue Requirement | 13.30 | 15.28 | 17.17 |  |  |

- Claimed in SBU-D ARR

| Table 9.12 SLDC Charges for 2019-20, 2020-21 & 2021-22 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019-20 |  | 2020-21 |  | 2021-22 |  |
| No | Item | Estimated in ARR | Revised | Estimated in ARR | Revised | Estimated in ARR | Revised |
| 1 | Peak demand projection | 4175 | 4369 | 4384 | 4500 | 4517 | 4635 |
| 2 | SLDC ARR (Rs.Cr.) | 19.77 | 13.30 | 21.93 | 15.28 | 24.26 | 17.17 |
| 3 | SLDC charges for LTA (Rs/MW/month) | 5482 | 3523 | 5791 | 3930 | 6216 | 4288 |
| 4 | SLDC charges for STOA (Rs/MW/day) | 180 | 116 | 190 | 129 | 204 | 141 |

| Form-T1: Summary of ARR of SBU-T (Rs.Cr) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Item | Estimated in ARR | Appvd. Vide order dtd. 8-7-2019 (2019-20) | Actual upto Sept 2019 | Revised estimate for 2019-20 | Appvd. For 2020-21 | Revised estimate for 2020-21 | Appvd. For 2021-22 | Revised estimate for 2021-22 |
| 1 | Operation & Maintenance Expenses | 397.46 | 397.46 | 256.4 | 390.83 | 452.88 | 440.48 | 491.28 | 496.3 |
| 2 | Interest and finance charges | 257.99 | 185.05 | 50.59 | 138.56 | 263.65 | 270.44 | 313.12 | 417.04 |
| 3 | Interest on Bonds and additional contribution | 125.15 | 105.59 | 36.17 | 105.59 | 100.98 | 100.98 | 96.37 | 96.37 |
| 4 | GPF Interest | 23.12 | 22.03 | 9.55 | 20.68 | 23.39 | 22.04 | 24.74 | 23.40 |
| 5 | Depreciation | 199.58 | 173.47 | 123.3 | 193.78 | 222.92 | 255.10 | 261.09 | 313.17 |
| 6 | Interest on WC and deposits | 20.2 | 17.4 | 9.55 | 21.70 | 20.48 | 23.28 | 23.28 | 27.10 |
| 7 | Adjustment of Controllable/uncontrollable factors | 0 | 0 | 0 |  |  |  |  |  |
| 8 | Other items |  |  | 1.17 |  |  |  |  |  |
| 10 | Total Revenue Expenditure | 1023.5 | 901 | 469.6 | 871.14 | 1084.30 | 1112.28 | 1209.89 | 1376.16 |
| 11 | Return on Equity | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 |
| 12 | Tax on RoE | 0 | 0 | 0 | 0 |  | 0 |  | 0 |
| 13 | Aggregate Revenue Requirement (10+11+12) of SBU-T & SLDC | 1143.49 | 1,020.99 | 589.59 | 991.14 | 1204.29 | 1231.86 | 1329.88 | 1490.58 |
| 14 | Aggregate requirement of SLDC |  |  |  | 13.30 |  | 15.28 |  | 17.17 |
| 15 | Aggregate requirement of SBU-T excl SLDC |  |  |  | 977.83 |  | 1216.99 |  | 1473.42 |
| 16 | Less: Other Income | 37.3 | 37.30 | 20.02 | 37.30 | 41.82 | 41.82 | 46.35 | 46.35 |
| 17 | Less: Revenue from Open Access |  |  |  |  |  |  |  |  |
| 18 | Less: Income from Other Business |  |  |  |  |  |  |  |  |
| 19 | ARR from Transmission Tariff | 1106.19 | 983.69 | 569.57 | 953.84 | 1162.47 | 1190.45 | 1283.53 | 1444.24 |

Transmission & SLDC Tariff forms

| Form-T2: O&M Expenses |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Particular | 2019-20 |  |  |  | 2020-21 | 2021-22 |
|  |  | Apr-Sep (Actual) | Estimated for the year | Approved by the Commission | Revised estimate for 2019-20 | Projected | Projected |
| 1 | Bay Basis |  |  |  |  |  |  |
| a | Op. Balance of no. of Bays |  | 2682 | 2682 | 2635 | 2803.5 | 3008.5 |
| b | Addition of no. of Bays during year |  |  |  | 205 |  |  |
| c | Deletion of no. of Bay during year |  |  |  |  |  |  |
| d | Cl. Balance of no. of Bays |  | 2682 | 2682 | 2840 |  |  |
| e | Average no. of Bays during Year |  |  |  |  |  |  |
| f | Applicable O&M cost Norm for Bay :- Rs _____Lakh/Bay |  | 11.23 | 11.23 | 11.23 | 11.77 | 12.34 |
| A | O&M Expense per Bay, Rs L |  |  |  |  |  |  |
| 2 | ckt-km Basis |  |  |  |  |  |  |
| a | Op. Balance of ckt-km |  | 9823.2 | 9823.2 | 9686 | 10728.69 | 11578.95 |
| b | Addition of ckt-km during year |  |  |  | 850.3 |  |  |
| c | Deletion of ckt-km during year |  |  |  |  |  |  |
| d | Cl. Balance of ckt-km |  | 9823.2 | 9823.2 | 10536.3 |  |  |
| e | Average ckt-km during Year |  |  |  |  |  |  |
| f | Applicable O&M cost Norm - Rs _____Lakh / ckt-km |  | 0.98 | 0.98 | 0.98 | 1.03 | 1.08 |
| B | O&M Expense Rs. Lakh | 256.4 | 397.46 | 397.46 | 390.83 | 440.48 | 496.3 |
|  | Pay revision expenses |  |  |  |  |  |  |
| 3 | Total O&M Expenses (as per norms) (A+B) |  |  |  |  |  |  |
| 4 | Total O&M Expenses (actual) |  |  |  | 524.85 | 561.58 | 600.9 |

| Form T 2(a) : Employee expenses Rs. Crore |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Particulars | 2019-20 |  |  | 2020-21 | 2021-22 | Remarks |
|  |  | Apr-Sep (Actual) | Estimated for the year | Approved by the Commission | Projected | Projected |  |
| 1 | 2 | 7 | 8 | 9 | 10 | 11 | 13 |
| 1 | Basic Salary | 146.21 | 324.41 |  | 347.11 | 371.41 |  |
| 2 | Dearness Allowance (DA) | 38.94 | 74.77 |  | 80.01 | 85.61 |  |
| 3 | House Rent Allowance | 2.57 | 5.80 |  | 6.20 | 6.64 |  |
| 4 | Conveyance Allowance | 0.00 | 0.00 |  | 0.00 | 0.00 |  |
| 5 | Leave Travel Allowance | 0.01 | 0.02 |  | 0.02 | 0.03 |  |
| 6 | Earned Leave Encashment | 16.66 | 22.70 |  | 24.29 | 25.99 |  |
| 7 | Other Allowances | 0.92 | 2.09 |  | 2.24 | 2.39 |  |
| 8 | Medical Reimbursement | 0.67 | 1.91 |  | 2.04 | 2.19 |  |
| 9 | Overtime Payment | 0.00 | 0.00 |  | 0.00 | 0.00 |  |
| 10 | Bonus/Ex-Gratia Payments | 0.98 | 1.03 |  | 1.11 | 1.18 |  |
| 11 | Interim Relief / Wage Revision | 0.00 | 0.00 |  | 0.00 | 0.00 |  |
| 12 | Staff welfare expenses | 0.17 | 0.18 |  | 0.19 | 0.21 |  |
| 13 | Net Employee Costs | 207.14 | 432.91 |  | 463.21 | 495.64 |  |
| 14 | Terminal Benefits | 0.00 | 0.00 |  | 0.00 | 0.00 |  |
| 15 | Provident Fund Contribution | 0.00 | 0.00 |  | 0.00 | 0.00 |  |
| 16 | Provision for PF Fund | 0.00 | 0.00 |  | 0.00 | 0.00 |  |
| 17 | Pension Payments | 0.00 | 0.00 |  | 0.00 | 0.00 |  |
| 18 | Gratuity Payment | 0.00 | 0.00 |  | 0.00 | 0.00 |  |
| 19 | Annual Contribution for Terminal Liabilities based on actuarial valuation | 0.00 | 0.00 |  | 0.00 | 0.00 |  |
| 20 | Contribution of KSEB Ltd towards National Pension Scheme | 0.98 | 0.00 |  | 0.00 | 0.00 |  |
| 21 | Others | 0.00 | 0.04 |  | 0.04 | 0.05 |  |
| 22 | Gross Employee Expenses | 208.13 | 432.95 |  | 463.26 | 495.69 |  |
| 23 | Less: Expenses Capitalized | 22.60 | 69.64 |  | 74.52 | 79.74 |  |
| 24 | Net Employee Expenses | 185.53 | 363.31 |  | 388.74 | 415.95 |  |

| Form T 2(b) : Administrative & General Expenses Rs. Crore |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Particulars | Current Year (n) |  |  | Ensuing Year (n+1) | Year (n+2) | Remarks |
|  |  | Apr-Sep (Actual) | Estimated for the year | Approved | Projected | Projected |  |
| 1 | 2 | 7 | 8 | 9 | 10 | 11 | 13 |
| 1 | Rent Rates & Taxes | 0.21 | 0.7 |  | 0.74 | 0.79 |  |
| 2 | Insurance | 0 | 0.38 |  | 0.41 | 0.43 |  |
| 3 | Telephone & Postage, etc. | 0.83 | 2.74 |  | 2.9 | 3.09 |  |
| 4 | Legal charges | 0.2 | 0.59 |  | 0.63 | 0.67 |  |
| 5 | Audit Fees | 0 | -0.03 |  | -0.03 | -0.03 |  |
| 6 | Consultancy charges | 0 | 0.02 |  | 0.02 | 0.02 |  |
| 7 | Other Professional charges | 0.39 | 0.9 |  | 0.96 | 1.02 |  |
| 8 | Conveyance | 3.31 | 7.31 |  | 7.75 | 8.25 |  |
| 9 | Vehicle Running Expenses Truck / Delivery Van | 0.08 | 0.2 |  | 0.21 | 0.22 |  |
| 10 | Vehicle Hiring Expenses Truck / Delivery Van | 0.1 | 0.29 |  | 0.31 | 0.33 |  |
| 11 | Electricity charges | 0.02 | 0.07 |  | 0.07 | 0.07 |  |
| 12 | Water charges | 0.08 | 0.17 |  | 0.18 | 0.19 |  |
| 13 | Entertainment | 0.1 | 0.23 |  | 0.24 | 0.26 |  |
| 14 | Fees & subscription | 0.18 | 0.54 |  | 0.57 | 0.61 |  |
| 15 | Printing & Stationery | 0.44 | 1.05 |  | 1.11 | 1.18 |  |
| 16 | Advertisements, exhibition publicity | 0.01 | 0.3 |  | 0.31 | 0.33 |  |
| 17 | Contribution/Donations | 0.22 | 0.45 |  | 0.48 | 0.51 |  |
| 18 | Training expenses | 0.01 | 0.07 |  | 0.08 | 0.08 |  |
| 19 | Miscellaneous Expenses | 0.25 | 0.62 |  | 0.66 | 0.7 |  |
| 20 | SRPC expenses | 0.24 | 0.24 |  | 0.25 | 0.27 |  |
| 21 | Sports and related activities | 0.01 | 0.09 |  | 0.09 | 0.1 |  |
| 22 | Freight | 0.52 | 0.95 |  | 1.01 | 1.07 |  |
| 23 | Purchase Related Advertisement Expenses | 0.3 | 0.84 |  | 0.89 | 0.95 |  |
| 24 | Office Expenses | 38.17 | 77.81 |  | 82.48 | 87.84 |  |
| 25 | License Fee and other related fee | 1.31 | 4.19 |  | 4.44 | 4.73 |  |
| 26 | V-sat, Internet and related charges | 0.05 | 0.03 |  | 0.03 | 0.03 |  |
| 27 | Books & periodicals | 0 | 0.01 |  | 0.02 | 0.02 |  |
| 28 | Others | 0.4 | 12.98 |  | 13.76 | 14.66 |  |
| 29 | Others- Other Purchase related Expenses | 2.66 | 1.09 |  | 1.15 | 1.23 |  |
| 30 | Gross A&G Expenses | 50.07 | 114.88 |  | 121.77 | 129.68 |  |
| 31 | Net A&G Expenses | 50.07 | 114.88 |  | 121.77 | 129.68 |  |

| Form T 2(c) : Repair & Maintenance Expenses Rs. Crore |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Particulars | Current Year (n) |  |  |  | Ensuing Year (n+1) | Year (n+2) | Remarks |
|  |  | Apr-Sep (Actual) | flood | Estimated for the year | Approved by the Commission | Projected | Projected |  |
| 1 | 2 | 7 |  | 8 | 9 | 10 | 11 | 13 |
| 1 | Plant & Machinery | 12.49 | 0.01 | 29.66899901 |  | 31.74582894 | 33.96803697 |  |
| 2 | Buildings | 1.06 | 0.00 | 2.666559233 |  | 2.853218379 | 3.052943666 |  |
| 3 | Civil Works | 2.81 | 0.00 | 5.359245423 |  | 5.734392603 | 6.135800085 |  |
| 4 | Hydraulic Works | 0.04 | 0.00 | 0.087929816 |  | 0.094084903 | 0.100670846 |  |
| 5 | Lines & Cable Networks | 3.76 | 0.00 | 8.35817303 |  | 8.943245142 | 9.569272302 |  |
| 6 | Vehicles | 0.39 |  | 0.890687961 |  | 0.953036118 | 1.019748647 |  |
| 7 | Furniture & Fixtures | 0.05 |  | 0.118843704 |  | 0.127162764 | 0.136064157 |  |
| 8 | Office Equipment | 0.18 |  | 0.474525611 |  | 0.507742404 | 0.543284372 |  |
| 9 | Gross R&M Expenses | 20.79 | 0.01 | 47.62496379 |  | 50.95871125 | 54.52582104 |  |
| 10 | Less: Expenses Capitalised |  |  | 0 |  | 0 | 0 |  |
| 11 | Net R&M Expenses | 20.79 | 0.01 | 47.62496379 |  | 50.95871125 | 54.52582104 |  |

| Form-T3: Depreciation for SBU-T & SLDC (Rs.Cr.) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Estimated in ARR | Approved vide order dtd. 8-7-2019 (2019-20) | Actual upto Sept-2019 | Revised estimate for 2019-20 | Appvd. For 2020-21 | Revised estimate for 2020-21 | Appvd. For 2021-22 | Revised estimate for 2021-22 |
| Item |  |  |  |  |  |  |  |  |
| Net depreciation allowable for SBU-T & SLDC | 199.58 | 173.47 | 68.10 | 193.78 | 222.92 | 255.13 | 261.09 | 314.78 |

| Form-T4: Interest on capital liabilities (Rs Cr ) for SBU-T & SLDC |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Item | Estimated in ARR | Approved vide order dtd.8-7-19 (2019-20) | Actual up to 30-9-19 | Revised estimate for 2019-20 | Approved for 2020-21 | Revised estimate for 2020-21 |  |  | Approved for 2021-22 | Revised estimate for 2021-22 |
| 1 | Average normative loan | 2579.89 | 1,999.99 | 1304.19 | 1,529.39 | 2849.43 |  | 2,985.00 | 3384.12 |  | 4,603.11 |  |
| 2 | Interest rate | 10% | 9.25% | 7.76% | 9.06% | 9.25% |  | 9.06% | 9.25% |  | 9.06% |  |
| 3 | Interest for the year* | 257.99 | 185.05 | 50.59 | 138.56 | 263.65 |  | 270.44 | 313.12 |  | 417.04 |  |

| Form T4C: SBU-T & SLDC interest on Master Trust bonds (Rs Cr) |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Item | Estimated in ARR | Approved vide order dtd.8-7-19 (2019-20) | Actual upto 30-9-19 | Revised estimate for 2019-20 | Appvd. For 2020-21 | Revised estimate for 2020-21 |  | Appvd. For 2021-22 |  | Revised estimate for 2021-22 |  |
| 1 | Existing bond | 82.95 | 82.95 | 36.17 | 82.95 | 78.34 |  | 78.34 |  | 73.73 |  | 73.73 |
| 2 | Additional contribution to Master Trust | 42.20 | 22.64 | 0 | 22.64 | 22.64 |  | 22.64 |  | 22.64 |  | 22.64 |
|  | Total | 125.15 | 105.59 | 36.17 | 105.59 | 100.98 |  | 100.98 |  | 96.37 |  | 96.37 |

| Form-T5: SBU-T& SLDC :Interest on Working capital (Rs Cr) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Estimated in ARR | Approved vide order dtd. 8-7-2019 (2019-20) | Actual upto Sept-2019 | Revised for the year 2019-20 | Appvd. For 2020-21 | Revised for the year 2020-21 | Appvd. For 2021-22 | Revised for the year 2021-22 |
| No | Item |  |  |  |  |  |  |  |  |
| 1 | O&M Expenses | 363.23 | 397.46 |  | 390.83 | 452.88 | 440.48 | 491.28 | 496.30 |
| 2 | GFA Plants and Equipment |  | 5,637.86 |  | 5094.47 | 6719.97 | 6425.07 | 8147.73 | 8684.75 |
| 3 | Transmission charges |  | 983.69 |  | 934.54 | 1162.47 | 1166.68 | 1283.53 | 1431.94 |
| 4 | O&M Expenses for one month | 31.52 | 33.12 |  | 32.57 | 37.74 | 36.71 | 40.94 | 41.36 |
| 5 | 1% of Historical cost of plants & Equipment | 61.22 | 56.38 |  | 50.94 | 67.20 | 64.25 | 81.48 | 86.85 |
| 6 | Receivables (Transmission charges for one month) | 92.18 | 81.97 |  | 77.88 | 96.87 | 97.22 | 106.96 | 119.33 |
| 7 | Total requirement of working capital | 184.92 | 171.47 |  | 161.39 | 201.81 | 198.18 | 229.38 | 247.53 |
| 8 | Rate of interest | 10.70% | 10.15% |  | 10.95% | 10.15% | 10.95% | 10.15% | 10.95% |
| 9 | Interest on working capital | 19.79 | 17.40 | 9.55 | 21.70 | 20.48 | 23.28 | 23.28 | 27.10 |

|  |  |  | Form-T7: ROE (Rs.Cr.) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Item |  |  | Estimated in ARR | Approved vide order dtd.8-7-2019 (2019-20) | Actual upto 30-9-2019 | Revised estimate for 2019-20 | Appvd. For 2020-21 | Revised estimate for 2020-21 | Appvd. For 2021-22 | Revised estimate for 2021-22 |
| 1 | RoE of SBU-T & SLDC |  |  | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 | 119.99 |
| 2 | RoE of SLDC (Segregated based on GFA ratio) |  |  |  |  |  | 0.18 |  | 0.17 |  | 0.24 |
| 3 | RoE of SBU-T |  |  |  |  |  | 119.81 |  | 119.82 |  | 119.75 |

|  |  |  | Form-T10: Non Tariff Income of SBU-T (Rs.Cr.) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No | Other Income (Rs.Cr.) |  |  | Estimated in ARR | Appd vide order dtd.8-7-2019 (2019-20) | Actual upto Sept 2019 | Revised estimate for 2019-20 | Appvd. For 2020-21 | Revised estimate for 2020-21 | Appvd. For 2021-22 | Revised estimate for 2021-22 |
| 1 | Interest on staff loans and advances |  |  | 0.02 |  | 0.00 | 0.02 | 0.02 | 0.02 | 0.03 | 0.03 |
| 2 | Income from statutory investments |  |  | 0 |  | 0.00 | 0 | 0 | 0 | 0 | 0 |
| 3 | Income from rent of land or buildings |  |  | 0.5 |  | 0.07 | 0.5 | 0.52 | 0.52 | 0.55 | 0.55 |
| 4 | Income from sale of scrap |  |  | 2.87 |  | 7.51 | 2.87 | 3.01 | 3.01 | 3.17 | 3.17 |
| 5 | Income from staff welfare activities |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |
| 6 | Rental from staff quarters |  |  | 0.12 |  | 0.04 | 0.12 | 0.12 | 0.12 | 0.13 | 0.13 |
| 7 | Excess found on physical verification |  |  | 0.03 |  | 0.00 | 0.03 | 0.04 | 0.04 | 0.04 | 0.04 |
| 8 | Interest on investments, fixed and call deposits and bank balances |  |  | 0.05 |  | 0.09 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |
| 9 | Interest on advances to suppliers/contractors |  |  | 0.05 |  | 0.12 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |
| 10 | Income from hire charges from contractors and others |  |  | 0 |  | 0.00 | 0 | 0 | 0 | 0 | 0 |
| 11 | Income fromfibre optic cables/co-axial cables on transmission system |  |  | 3.9 |  |  | 3.9 | 4.49 | 4.49 | 5.07 | 5.07 |
| 12 | Income from advertisements, etc. |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |
| 13 | Miscellaneous receipts |  |  | 29.76 |  | 12.20 | 29.76 | 33.52 | 33.52 | 37.26 | 37.26 |
|  | Total Other Income (Rs.Cr.) |  |  | 37.3 | 37.30 | 20.02 | 37.30 | 41.82 | 41.82 | 46.35 | 46.35 |

| Form-S1: ARR of SLDC (Rs.Cr.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Particulars | 2019-20 | 2020-21 | 2021-22 |  |  |
| 1 | Expenses |  |  |  |  |  |
| a) | Operating Expenses |  |  |  |  |  |
| i) | Employee expenses | 8.18 | 9.84 | 10.82 |  |  |
| ii) | Administrative and General Expenses | 0.65 | 0.71 | 0.75 |  |  |
| iii) | Repair and Maintenance Expenses | 1.14 | 1.21 | 1.32 |  |  |
| iv) | Interest on Working Capital | 0.20 | 0.23 | 0.27 |  |  |
| v) | RLDC Fee and Charges (*) |  |  |  |  |  |
| b) | Capital expense components |  |  |  |  |  |
| i) | Depreciation | 0.28 | 0.34 | 0.60 |  |  |
| ii) | Interest and finance charges on term loan | 0.21 | 0.38 | 0.83 |  |  |
|  | Interest on GPF | 0.42 | 0.45 | 0.47 |  |  |
|  | Interest on Master Trust Bond | 2.04 | 1.95 | 1.86 |  |  |
| iii) | Return on equity | 0.18 | 0.17 | 0.24 |  |  |
| iv) | Income Tax provision |  |  |  |  |  |
| 2 | Total Revenue Expenditure (a+b+c) | 10.82 | 12.91 | 14.86 |  |  |
| 3 | Less: Non Tariff income |  |  |  |  |  |
| 4 | Less: Income from other business |  |  |  |  |  |
| 5 | Aggregate Revenue Requirement | 13.30 | 15.28 | 17.17 |  |  |

| Form S2: O&M expenses of SLDC (Rs Cr) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| As per ARR |  |  |  | Revised |  |  |  |  |
| Item | 2019-20 | 2020-21 | 2021-22 | Actual upto Sept-19 | 2019-20 | 2020-21 |  | 2021-22 |  |
| Employee cost | 17.24 | 18.97 | 20.86 | 4.24 | 8.18 | 9.84 | 10.82 |  |  |
| R&M Expenses | 0.62 | 0.69 | 0.75 | 0.32 | 0.65 | 0.71 | 0.75 |  |  |
| A&G Expenses | 1.35 | 1.63 | 1.93 | 0.31 | 1.14 | 1.21 | 1.32 |  |  |
| O&M expenses | 19.22 | 21.28 | 23.55 | 4.87 | 9.96 | 11.77 | 12.89 |  |  |

|  | Form S 2.1 :Employee expenses (Rs.Lakhs) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| S. No. | Particulars | Current Year |  |  | Ensuing Year | Year |
|  |  | (2019-20) |  |  | (2020-21) | (2021-22) |
|  |  | Approved | Apr-Sep(Actual) | Estimated | Projected | Projected |
| 1 | 2 | 6 | 7 | 8 | 9 | 10 |
| I | Employee's Cost (Other Than Covered In 'III'&'IV') |  |  |  |  |  |
| 1 | Basic Salary |  | 282.45 | 595.69 | 655.25 | 720.78 |
| 2 | Additional Pay |  | 0.05 | 0.12 | 0.13 | 0.14 |
| 3 | D.A. |  | 95.88 | 202.20 | 222.42 | 244.66 |
| 4 | House Rent Allowance |  | 5.19 | 11.01 | 12.11 | 11.84 |
| 5 | Other Allowances & Relief |  | 2.81 | 5.00 | 5.50 | 6.05 |
| 6 | Sub-Total: (1 to 5) | 0.00 | 386.38 | 737.25 | 895.41 | 983.47 |
| 7 | Medical Expenses Reimbursement |  | 0.55 | 1.16 | 1.27 | 1.40 |
| 8 | Travelling Allowance(Conveyance Allowance) |  | 0.00 | 0.00 | 0.00 | 0.00 |
| 9 | Leave Travel Assistance |  | 0.00 | 0.30 | 0.50 | 0.60 |
| 10 | Honorarium/Overtime |  | 0.00 | 0.00 | 0.00 | 0.00 |
| 11 | Load Despatch Allowance |  | 0.00 | 0.00 | 0.00 | 0.00 |
| 12 | Earned Leave Encashment |  | 37.47 | 78.99 | 86.89 | 95.58 |
| 13 | Payment Under Workman's Compensation |  | 0.00 | 0.00 | 0.00 | 0.00 |
| 14 | Any Other Item |  | 0.00 | 0.00 | 0.00 | 0.00 |
| 15 | Arrears to Wage Revision |  | 0.00 | 0.00 | 0.00 | 0.00 |
| 16 | Sub-Total (7 to 15) | 0.00 | 38.02 | 80.45 | 88.66 | 97.58 |
| 17 | Staff Welfare Expenses |  | 0.00 | 0.10 | 0.15 | 0.20 |
| II | Apprentice And Other Training Expenses |  | 0.00 | 0.00 | 0.00 | 0.00 |
| III | Payment/Contribution To PF Staff Pension And Gratuity |  | 0.00 | 0.00 | 0.00 | 0.00 |
| 1 | Terminal Benefits |  | 0.00 | 0.00 | 0.00 | 0.00 |
| a. | Provident Fund Contribution |  | 0.00 | 0.00 | 0.00 | 0.00 |
| b. | Provision for PF Fund |  | 0.00 | 0.00 | 0.00 | 0.00 |
| c. | Pension Payments |  | 0.00 | 0.00 | 0.00 | 0.00 |
| d. | Gratuity Payment on super annuation |  | 0.00 | 0.00 | 0.00 | 0.00 |
| e. | SuperAnnuation Fund, If any |  | 0.00 | 0.00 | 0.00 | 0.00 |
| f. | Any other terminal benefit(Encashment) |  | 0.00 | 0.00 | 0.00 | 0.00 |
| 2 | Any Other Items |  | 0.00 | 0.00 | 0.00 | 0.00 |
|  | Total III | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| IV | Grand Total [I.6 + I.16 + I.17 + II + III] | 0.00 | 424.40 | 817.80 | 984.22 | 1081.25 |
| V | Incentive Payment |  | 0.00 | 0.00 | 0.00 | 0.00 |
| VI | Grand Total | 0.00 | 424.40 | 817.80 | 984.22 | 1081.25 |
| VII | Less Expenses Capitalised |  | 0.00 | 0.00 |  |  |
|  | Net Employee expenses | 0.00 | 424.40 | 817.80 | 984.22 | 1081.25 |

|  | Form S 2.2 : Administrative and General Expenses (Rs.Lakhs) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Particulars | Current Year |  |  | Ensuing Year | Year | Remarks |
|  |  | (2019-20) |  |  | (2020-21) | (2021-22) |  |
|  |  | Approved | Apr-Sep(Actual) | Estimated | Projected | Projected |  |
| 1 | 2 | 6 | 7 | 8 | 9 | 10 | 13 |
| A) | Administration Expenses |  |  |  |  |  |  |
|  | Rent rates and taxes |  |  |  |  |  |  |
| i) | Rent |  | 0.00 | 0.00 | 0.00 | 0.00 |  |
| ii) | Rates & Taxes |  | 1.18 | 2.50 | 2.80 | 3.10 |  |
|  | Sub - total of Rent rates and taxes | 0.00 | 1.18 | 2.50 | 2.80 | 3.10 |  |
| iii) | Insurance |  | 0.05 | 1.80 | 2.00 | 2.20 |  |
| iv) | Revenue Stamp Expenses,Telephone,P&T & Telex Charges |  | 5.30 | 7.45 | 8.20 | 8.76 |  |
| v) | Legal Charges |  | 0.01 | 0.10 | 0.10 | 0.10 |  |
| vi) | Audit Fees |  | 0.00 | 0.00 | 0.00 | 0.00 |  |
| vii) | Technical Fees, Consultancy and Other Professional Charges |  | 0.24 | 0.50 | 0.60 | 0.70 |  |
| viii) | Conveyance and Travel |  | 3.70 | 7.50 | 8.00 | 8.50 |  |
| ix) | Electricity charges |  | 0.00 | 0.00 | . | 0.00 |  |
| x) | Vehicle Running & Hiring Expenses |  | 1.39 | 4.79 | 5.30 | 5.80 |  |
| xi) | Vehicles Running Expenses Petrol And Oil |  | 0.27 | 0.60 | 0.70 | 0.80 |  |
| xii) | Security / Service Charges Paid To Outside Agencies |  | 11.16 | 25.50 | 28.10 | 28.50 |  |
|  | Sub-Total of Admistrative Expenses | 0.00 | 23.30 | 50.74 | 55.80 | 58.46 |  |
| B) | Other Charges |  |  |  |  |  |  |
| i) | Fee And Subscriptions Books And Periodicals |  | 0.00 | 0.01 | 0.00 | 0.00 |  |
| ii) | Printing And Stationery |  | 0.78 | 1.66 | 1.87 | 2.07 |  |
| iii) | Advertisement Expenses (Including Purchase Related) Exhibition & Demo. |  | 0.00 | 0.10 | 0.10 | 0.15 |  |
| iv) | Water Charges |  | 0.00 | 0.00 | 0.00 | 0.00 |  |
| v) | Bank Charges |  | 0.00 | 0.00 | 0.05 | 0.05 |  |
| vi) | Miscellaneous Expenses |  | 6.47 | 10.03 | 11.04 | 12.04 |  |
| vii) | Office Expenses |  | 0.96 | 2.00 | 2.20 | 2.50 |  |
|  | Sub-Total of other charges | 0.00 | 8.21 | 13.80 | 15.26 | 16.81 |  |
| C) | Material Related Expenses |  | 0.00 | 0.00 | 0.00 | 0.00 |  |
| i) | Incidental Stores Expenses |  | 0.00 | 0.00 | 0.00 | 0.00 |  |
|  | Sub Total of Material related expenses | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |  |
| D) | Total A&G expenses | 0.00 | 31.51 | 64.54 | 71.06 | 75.27 |  |

|  | Form S 2.3 : Repair and Maintenance expenses (Rs.Lakhs) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Particulars | Current Year |  |  | Ensuing Year | Year | Remarks |
|  |  | (2019-20) |  |  | (2020-21) | (2021-22) |  |
|  |  | Approved | Apr-Sep(Actual) | Estimated | Projected | Projected |  |
| 1 | 2 | 6 | 7 | 8 | 9 | 10 | 13 |
| 1 | Plant & Machinery |  | 18.29 | 66.42 | 73.46 | 80.51 |  |
| 2 | Building |  | 5.19 | 24.40 | 23.78 | 25.00 |  |
| 3 | Civil Works |  | 6.71 | 20.00 | 22.02 | 24.00 |  |
| 4 | Lines, Cables, Networks, etc. |  | - | 0.40 | 0.20 | 0.20 |  |
| 5 | Vehicle |  | 0.15 | 0.10 | 0.44 | 0.50 |  |
| 6 | Furniture & Fixtures |  | 0.04 | 1.00 | 0.11 | 0.12 |  |
| 7 | Office Equipment |  | 0.66 | 1.29 | 1.42 | 1.66 |  |
| 8 | Station Supplies |  | - |  |  |  |  |
| 9 | Miscellaneous |  | - |  |  |  |  |
| A | Total R&M Expenses | - | 31.04 | 113.61 | 121.43 | 131.99 |  |
| B | less: Expenses Capitalized | - | - | - | - | - |  |
| C | Total R&M Expenses chargeable to Revenue Expenses | - | 31.04 | 113.61 | 121.43 | 131.99 |  |
|  | Total |  |  |  |  |  |  |

| Form-S3: SLDC : Interest on Working capital (Rs Cr) |  |  |  |  |
| --- | --- | --- | --- | --- |
| No | Item | 2019-20 | 2020-21 | 2021-22 |
| 1 | O&M expenses (as per norms) | 0.83 | 0.98 | 1.07 |
| 2 | Maintenance Spares (as per norms) | 0.08 | 0.09 | 0.17 |
| 3 | Receivables (as per norms) | 0.90 | 1.08 | 1.24 |
| 4 | Total Working Capital | 1.81 | 2.14 | 2.48 |
| 5 | Interest Rate (as per norms) (2% + base rate as on 1-4-2019) | 10.95% | 10.95% | 10.95% |
| 6 | Interest on Working Capital | 0.20 | 0.23 | 0.27 |

| Form-S5 : Fixed Assets (2019-20) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S.No. |  |  | Assets Group (as per notification in respect of depreciation) |  |  | Rate of depreciation |  | Gross fixed assets |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | At the beginning of the year | Additions during the year |  |  | Adjustment & deductions | At the end of the year |  | Remarks |
| 1 |  |  | 2 |  |  | 3 |  | 4 | 5 |  |  | 6 | 7 |  |  |
| 1 |  |  | Land & Land rights |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  |
| 2 |  |  | Building and Civil Works |  |  |  |  | 28.89 | 10.00 |  |  | 0.00 | 38.89 |  |  |
| 3 |  |  | Hydraulic Works |  |  |  |  | 0 | 0.00 |  |  | 0.00 | 0 |  |  |
| 4 |  |  | Other Civil Works |  |  |  |  | 0 | 0.00 |  |  | 0.00 | 0 |  |  |
| 5 |  |  | Plant & Machinery@ |  |  |  |  | 47.97 | 75.72 |  |  | 0.00 | 123.69 |  |  |
| 6 |  |  | Lines Cable Network etc. |  |  |  |  | 0 | 0.00 |  |  | 0.00 | 0 |  |  |
| 7 |  |  | Vehicles |  |  |  |  | 0 | 0.00 |  |  | 0.00 | 0 |  |  |
| 8 |  |  | Furniture & fixtures |  |  |  |  | 8.27 | 0.00 |  |  | 0.00 | 8.27 |  |  |
| 9 |  |  | Office Equipment's |  |  |  |  | 6.76 | 2.79 |  |  | 0.00 | 9.55 |  |  |
| 10 |  |  | Communication equipment |  |  |  |  | 0 | 0.00 |  |  | 0.00 | 0 |  |  |
| 11 |  |  | SCADA and IT system* |  |  |  |  | 630.61 | 8.64 |  |  | 0.00 | 639.25 |  |  |
| 12 |  |  | Other equipment |  |  |  |  | 40.10 | 0.00 |  |  | 0.00 | 40.1 |  |  |
|  |  |  | Total (1) to (12) |  |  |  |  | 762.60 | 97.15 |  |  | 0.00 | 859.75 |  |  |
| Form-S5 : Fixed A Form-S5 : Fixed Assets (2019-20) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Land & Land rights |  |  | 0 |  | 0 |  |  | 0 | 0 |  |  |  |  |  |
| 2 | Building and Civil Works |  |  | 38.89 |  | 40.00 |  |  | 0.00 | 78.89 |  |  |  |  |  |
| 3 | Hydraulic Works |  |  | 0 |  | 0.00 |  |  | 0.00 | 0 |  |  |  |  |  |
| 4 | Other Civil Works |  |  | 0 |  | 0.00 |  |  | 0.00 | 0 |  |  |  |  |  |
| 5 | Plant & Machinery |  |  | 123.69 |  | 798.75 |  |  | 0.00 | 922.44 |  |  | Includes Rs. 698 lakhs for ADMS (PSDF grant Sanctioned is Rs.477 lakhs |  |  |
| 6 | Lines Cable Network etc. |  |  | 0 |  | 0.00 |  |  | 0.00 | 0 |  |  |  |  |  |
| 7 | Vehicles |  |  | 0 |  | 0.00 |  |  | 0.00 | 0 |  |  |  |  |  |
| 8 | Furniture & fixtures |  |  | 8.27 |  | 0.00 |  |  | 0.00 | 8.27 |  |  |  |  |  |
| 9 | Office Equipment's |  |  | 9.55 |  | 0.00 |  |  | 0.00 | 9.55 |  |  |  |  |  |
| 10 | Communication equipment |  |  | 0 |  | 0.00 |  |  | 0.00 | 0 |  |  |  |  |  |
| 11 | SCADA and IT system* |  |  | 639.25 |  | 1.01 |  |  | 0.00 | 640.26 |  |  |  |  |  |
| 12 | Other equipment |  |  | 40.1 |  | 0.00 |  |  | 0.00 | 40.1 |  |  |  |  |  |
|  | Total |  |  | 859.75 |  | 839.76 |  |  | 0.00 | 1699.51 |  |  |  |  |  |

| S.No. | Assets Group (as per notification in respect of depreciation) | Rate of depreciation | Gross fixed assets (2021-22) |  |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | At the beginning of the year | Additions during the year | Adjustment & deductions | At the end of the year | Cumulative upto the beginning of year |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 14 |
| 1 | Land & Land rights |  | 0 | 0 | 0 | 0 |  |  |
| 2 | Building and Civil Works |  | 78.89 | 0.00 | 0.00 | 78.89 |  |  |
| 3 | Hydraulic Works |  | 0 | 0.00 | 0.00 | 0 |  |  |
| 4 | Other Civil Works |  | 0 | 0.00 | 0.00 | 0 |  |  |
| 5 | Plant & Machinery |  | 922.44 | 17600.00 | 0.00 | 18522.44 |  |  |
| 6 | Lines Cable Network etc. |  | 0 | 0.00 | 0.00 | 0 |  |  |
| 7 | Vehicles |  | 0 | 0.00 | 0.00 | 0 |  |  |
| 8 | Furniture & fixtures |  | 8.27 | 0.00 | 0.00 | 8.27 |  |  |
| 9 | Office Equipment's |  | 9.55 | 0.00 | 0.00 | 9.55 |  |  |
| 10 | Communication equipment |  | 0 | 0.00 | 0.00 | 0 |  |  |
| 11 | SCADA and IT system* |  | 640.26 | 5300.00 | 0.00 | 5940.26 |  | ** |
| 12 | Other equipment |  | 40.1 | 0.00 | 0.00 | 40.1 |  |  |
|  | Total (1) to (12) |  | 1699.51 | 22900.00 | 0.00 | 24599.51 | 0.00 |  |

- *Includes Rs.17600 lakhs for Reliable Communication Project (PSDF grant sanctioned is Rs.7376 lakhs).  It may please be noted that this asset shall form part of the capital asset of Transmission Circles

**Rs.5300 lakhs represents the project cost of SAMAST for which DPR already been submitted before PSDF Authorities for availing Grant