KINESCO Power and Utilities Pvt. Ltd.

Details of Fixed Asset Addition during the year 2019-20

- Introduction

KPUPL had filed a separate petition on 27.10.2017 before the Hon’ble Commission for approval of the Fixed Asset addition plan for the period 2017-18. The Commission, after conducting public hearing on 21.02.2018, approved a portion of the plan vide order dated 28.05.2018 and directed KPUPL to include the remaining items along with the ARR-ERC for the MYT control period from 2018-19 to 2021-22. Accordingly, KPUPL had submitted before the Hon’ble Commission, the fresh Capital Investment plan for MYT control period for the years from 2018-19 to 2021-22 along with the revised ARR-ERC petition submitted on 15.06.2020. Hearing was conducted during the month of September 2020 on the revised ARR-ERC and the final order was kept in abeyance due to various reasons. In the meantime, certain essential capital expenditures were to be incurred by KPUPL to meet the technical necessities of the plant and to comply with the commitments given to the statutory authorities like Electricity Inspectorate and to KSEBL. Moreover, as committed to the Hon’ble Commission on various occasions on the compliance of RPO obligation, as a first step to meet the obligation, KPUPL had taken the initiative to implement solar energy plants on roof-top of our sub-stations.

- Summary of Fixed Asset Addition during the year 2019-20

The details of the Fixed Asset Additions made by the company during the year 2019-20 are tabulated below table.

| Sl. No | Description of Asset Capitalized | Unit | Qty | Amount (Rs.) | Date of Capitalization |
| --- | --- | --- | --- | --- | --- |
| 1 | Development work of sub-station road (proportionate cost transferred by KEPIP) | LS | LS | 12,17,059.00 | 31.03.2020 |
| 2 | Visitors' Chair (steel- 3 seater) | No. | 2 | 11,328.00 | 27.12.2019 |
| 3 | TOD meters | No. |  | 1,01,798.00 | 13.05.2019 |
| 4 | TOD metering panel (KIITP/MFP) | LS |  | 53,690.00 | 17.09.2019 |
| 5 | Mobile phone for Palakkad area | No | 1 | 1,400.00 | 22.10.2019 |
| 6 | HP Laptop Battery | No | 1 | 3,000.00 | 27.09.2019 |
| 7 | Procurement of PCs & peripherals | No | 2 | 1,52,012.00 | 22.10.2019 |
| 8 | Solar Generating plant at Kakkanad & Kalamassery | KWp | LS | 35,68,468.00 | 31.03.2020 |
| 9 | Supply of Lightning Arrestor | No | 1 | 5,310.00 | 22.10.2019 |
| 10 | Installation of DP structure with fuse unit at MFP | No | 1 | 58,917.00 | 16.01.2020 |
| 11 | Tools for sub-station at Kakkanad |  |  | 8,681.00 | 25.02.2020 |
| 12 | Supply & installation of RMUs at Kakkanad |  |  | 15,72,409.00 | 31.03.2020 |
| 13 | Purchase of CT/PT and GI supports |  |  | 1,85,639.00 | 01.07.2019 |
| 14 | Purchase of 11KV Cast Resin 90/5A 0.2s class CT for Kalamassery | No | 1 | 47,790.00 | 10.04.2019 |
|  | Total Amount |  |  | 69,87,501.00 |  |

The brief description and necessity of the investment are detailed below.

- Details of Capital Addition

  - Development work of sub-station road – Rs. 12,17,059/-

- Brief description and Necessity of the Investment

CEO, KINESCO requested to Civil Section, KINFRA Export Promotion Industrial Park (KEPIP) to construct a new road entry to 110KV extended yard at KINESCO 110KV Substation, Kakkanad for facilitating entry of heavy machines like Crane, JCB etc. during maintenance for easy access to equipments. Some loading cover slabs for existing trenches are also needed to be constructed for enabling entry to heavy equipments. It was suggested to take up these works by civil department of KEPIP along with similar works in order to ensure the quality of work.

The proposed work was executed by KEPIP and proportionate cost paid to KEPIP.

- Cost Estimate

As part of the major road work executed by KEPIP

- Financing of Capital Expenditure

The above capital addition was financed from the accrued surplus of KPUPL

- Supporting Documents

  - Copy of request letter to KEPIP from KPUPL- (Appendix-01)

  - Copy of bill details RAB-1 & RAB-2 (final) - (Appendix-02)

  - Visitors' Chair – Rs. 11,328/-

- Brief description and necessity of the Investment

KPUPL has been managing the licensee operations at various industrial parks from Kakkanad Office. Consumers used to visit the office for various purposes and proper seating facility needed to be arranged to engage them. 2 Nos. Three seater Steel chairs were purchased to accommodate the visitors at KPUPL Office. The item was entered in KPUPL Asset register and Capitalized as on 27.12.2019.

- Cost Estimate

The visitors chair cost Rs. 4,800/- per chair.

- Financing of Capital Expenditure

The above capital addition was financed from the accrued surplus of KPUPL

- Supporting Documents

Copy of the invoice - (Appendix-03)

  - TOD meters – Rs. 1,01,798/-

- Brief description and Necessity of the investment.

KPUPL has been sourcing the power requirement at various licensee areas from M/s. KSEB Ltd, the State Utility. As per Kerala Electricity Supply Code 2014, Chapter VI, Regulation 109 and CEA (Installation and Operation of Meters) Regulations licensee has to install check meters in addition to main meters at the interfacing points in the licensee areas. KPUPL has installed check metes only at Kakkanad licensee area. KSEBL has directed to install check meters at the licensee areas of KPUPL at KINFRA Hi Tech Park, Kalamassery, KINFRA IIT Park, Kanjikode, Palakkad and KINFRA Mega Food Park, Kozhipara, Palakkad.

Hence it was decided to purchase and calibrate 3 nos of HT ToD energy meters for the above mentioned licensee areas. Estimate was prepared based on the local enquiry and the offer received from a reputed supplier. The estimate amount came to Rs. 1,01,800/-  including GST. Quotations were invited vide quotation no. 07/KKD/2018-19 dated 22.02.2019 from suppliers for supply of HT ToD meters as per relevant IS standards. Three offers received out of which M/s. National Trading Company offered the lowest rates and hence became L1. The purchase order was awarded to M/s. National Trading Company vide PO No. 14/2018-19 dated 23.03.2019. The meters were delivered as per specifications on 27.04. 2019. The items were entered in KPUPL Asset register and Capitalized as on 13.05.2019.

- Cost Estimate

Open quotations were invited for supply of 2 nos of 3 phase 4 wire 0.2S accuracy class 22/rt3 kV/110/rt3 V, -/5A HT ToD meters and 1 no. 3 phase 4 wire 0.2S accuracy class 11/rt3 kV/110/rt3 V, -/5A HT ToD meter vide quotation no. 07/KKD/2018-19. Three firms submitted their offers with GST extra as applicable as tabulated below.

| Sl. No. | Participant | Quoted Amount (Rs.) | Status |
| --- | --- | --- | --- |
| 1. | M/s. Southern Engineering | 94,860/- | L3 |
| 2. | M/s. R. M. Electricals | 94,650/- | L2 |
| 3. | M/s. National Trading Company | 94,084/- | L1 |

M/s. National Trading Company quoted the lowest for the supply of HT ToD meters for Rs. 94,084 with GST extra as applicable. Rock bottom was requested to the company and vide offer no. 7565 dated 26.02.2019, they offered rock bottom rate as Rs. 86,270/- plus GST extra as applicable. So, the purchase order was awarded to M/s. National Trading Company for supply of HT ToD Metes vide PO No. 14/2018-19 dated 23.03.2019 for Rs. 86,270/- (Rupees Eighty-six thousand two hundred and seventy only) with GST extra as applicable.

- Financing of Capital Expenditure

The above capital addition was financed from the accrued surplus of KPUPL

- Supporting Documents

- Copy of the quotation notice-(Appendix-04)

- Copy of the purchase order - (Appendix-05)

- Copy of the contract agreement - (Appendix-06)

- Copy of the payment note - (Appendix-07)

- TOD metering panel (KIITP/MFP) – Rs. 53,690/-

- Brief description and Necessity of the Investment

KPUPL has been sourcing the power requirement at various licensee areas from M/s. KSEB Ltd, the State Utility. As per Kerala Electricity Supply Code 2014, Chapter VI, Regulation 109 and CEA (Installation and Operation of Meters) Regulations licensee has to install check meters in addition to main meters at the interfacing points in the licensee areas. KSEBL has directed to install check meters at the licensee areas of KPUPL at KINFRA Hi Tech Park, Kalamassery, KINFRA IIT Park, Kanjikode, Palakkad and KINFRA Mega Food Park, Kozhipara, Palakkad. Purchase order was awarded to M/s. National Trading Company for supply of HT ToD Metes vide PO No. 14/2018-19 dated 23.03.2019.

At KINFRA Mega Food Park, Kozhipara, Palakkad, the existing metering panel is needed to be modified for making the provision for housing 2 nos. energy meters, test terminal boxes and fuse base etc. At KIITP, Kanjikode, the existing metering panel could not be modified for making additional space for check meter installation. So it was necessary to fabricate a new metering panel with provision housing 2 nos. energy meters, test terminal blocks and fuse base etc. Local enquiry was conducted and quotations were invited for modification and fabrication of metering panels for KINFRA Mega Food Park and KIITP from contractors who are doing similar works.

An estimate for the said works at KINFRA Mega Food Park and KIITP had been prepared based on the offer received from contractor who is doing similar works. The estimate amount for modification and fabrication of metering panels was arrived to be Rs. 53,690/-. Three offers received out of which M/s. Benita Electricals offered the lowest rates and hence became L1. The work order was awarded to M/s. Benita Electricals for ‘Fabrication, Modification and Erection of ToD metering panel at KIITP and KINFRA Mega Food Park Palakkad’ vide WO No. 01/2019-20 dated 04.05.2019. The work was completed as per specifications on 26.08. 2019. The items were entered in KPUPL Asset register and Capitalized as on 17.09.2019

- Cost Estimate

Open quotations were invited for ‘Fabrication, Modification and Erection of ToD metering panel at KIITP and KINFRA Mega Food Park, Kanjikode, Palakkad’. Three firms submitted their offers with GST extra as applicable as tabulated below.

| Sl. No. | Participant | Quoted Amount (Rs.) | Status |
| --- | --- | --- | --- |
| 1. | M/s. Global Engineering | 46,275/- | L2 |
| 2. | M/s. RECON Technologies | 51,500/- | L3 |
| 3. | M/s. BENITA Electricals | 45,500/- | L1 |

M/s. BENITA Electricals offered the lowest price for the above mentioned work for Rs. 45,500/- with GST extra as applicable. Rock bottom rates were requested and they replied that they had offered least minimum rates.  Work order was awarded to M/s. BENITA Electricals for ‘Fabrication, Modification and Erection of ToD metering panel at KIITP and KINFRA Mega Food Park, Kanjikode, Palakkad’ vide WO No. 01/2019-20 dated 04.05.2020 for Rs. 45,500/- (Rupees Eighty-six thousand two hundred and seventy only) with GST extra as applicable.

- Financing of Capital Expenditure

The above capital addition was financed from the accrued surplus of KPUPL

- Supporting Documents

- Copy of the quotations received from contractors-(Appendix-08)

- Copy of the work order - (Appendix-09)

- Copy of the contract agreement - (Appendix-10)

- Copy of the payment note - (Appendix-11)

- Mobile phone for Palakkad area – Rs. 1,400/-

A dedicated contact number has been provided to the consumers of KPUPL Palakkad licensee area for communication with KPUPL control room and Section officer at KIITP, Kanjikode. For this a mobile phone has been purchased and issued to KPUPL control room at KIITP. An amount of Rs.1400/- was spent on purchasing a mobile phone for the purpose. The item was entered in KPUPL Asset register and Capitalized as on 22.10.2019.

- HP Laptop Battery – Rs. 3,000/-

The HP make laptop computer used at the office of CEO became non-operating due to battery issue. A new laptop battery made of HP suitable to the existing laptop was purchased and the laptop was made working condition. An amount of Rs.3000/- was spent on purchasing HP laptop Battery. The item was entered in KPUPL Asset register and Capitalized as on 27.09.2019.

- Procurement of PCs & peripherals – Rs. 1,52,012/-

- Brief description and Necessity of the Investment

The desktop PC used for saving the monthly energy consumption details of consumers and for preparation of monthly electricity bills had been showing troubles since ling time. A primary troubleshooting was done in the computer during the month of May 2019 with a technical expert who is doing similar works. He made some necessary modification in Operating system and networks and made the computer operative. During the trouble shooting, the technical expert informed that the hard disk and RAM of the computer has already become faulty and it needed urgent attention failing which the computer might get completely inoperative which might cause loss of back up data. The computer was of model 2010 and may hardware as well as software components of this computer were outdated and beyond upgradation. So it became necessary to purchase a computer (desktop PC) with latest configuration and replace the same at the earliest.

The desktop PC used by Finance Manager had been giving trouble since long time. The said PC was procured in the year 2010 and has outlived its useful and intended purpose. Moreover, the PC had been used as the server for Tally ERP9 and all past data of the Finance and Accounts and other important matters of financial and statutory reporting were also stored in the same PC. In the event of its going out of service would badly affect the smooth functioning of the office. The PC therefore, needed urgent replacement. The existing PC which is Tally loaded, can be used in the Audit room for the lighter use of various teams like statutory, cost and internal audits.

- Cost Estimate

A budgetary offer was invited from suppliers who are supplying similar items. The estimate was prepared for purchase and installation of 2 nos. of desktop computers and its peripherals based on the lowest offered rate. The estimated amount comes to Rs. 1,52,012/- including GST. Quotations were invited for the supply of 2 nos. of PCs and peripherals from the supplies who are doing similar works vide quotation no. 04/KKD/2019-20 dated 28.09.2019. Two suppliers were offered their rates as mentioned below.

| Sl. No. | Participant | Quoted Amount (Rs.) | Status |
| --- | --- | --- | --- |
| 1. | M/s. Cyber Park – Wow Sales Corporation | 1,28,824/- | L1 |
| 2. | M/s. Neural Networks P Ltd | 1,53,220/- | L2 |

M/s. Cyber Park – Wow Sales Corporation quoted the lowest for the supply and installation of PCs and Peripherals at KINESCO for Rs. 1,28,824/- with GST extra as applicable. Rock bottom was requested to the company and vide letter no. 134 dated 15.10.2019 and they replied that the rates quoted by them was the lowest price possible. So, the purchase order was awarded to M/s. Cyber Park – Wow Sales corporation for ‘Supply and Installation of PCs and Peripherals at KINESCO office at Kakkanad’ vide PO No. 02/2019-20 dated 17.10.2019 for Rs. 1,28,824/- (Rupees One lakh twenty-eight thousand eight hundred and twenty-four only) with GST extra as applicable. The supplier was successfully completed the supply and installation. The items were entered in KPUPL Asset register and Capitalized as on 22.10.2019.

- Financing of Capital Expenditure

The above capital addition was financed from the accrued surplus of KPUPL

- Supporting Documents

- Copy of the quotations received from suppliers -(Appendix-12)

- Copy of the purchase order - (Appendix-13)

- Copy of the contract agreement - (Appendix-14)

- Copy of the payment note - (Appendix-15)

- Supply of materials for 110KWp Grid connected PV Solar Plant & erection thereof -  Final Payment – Rs. 35,68,468/-

- Brief description and necessity of the Investment

As per the KSERC (Renewable Energy) Regulation 2015, every distribution licensee should purchase renewable energy not less than 4.50% of the total energy supplied by it to the consumers within its area of license, during the financial years commencing form 2015-16, with an increase of 0.5% per year. The renewable energy generated from solar sources or purchased from solar energy generators by the distribution licensee shall not be less than 10 % of its renewable purchase obligation. Based on the present average sale of power of 6.8 Million Units (MU) by KPUPL, the RPO obligation comes to an approximate quantity of 374000 units per month and out of this 37400 units should be from solar sources.

In this context, KPUPL obtained approval in the 36th meeting of Board of Directors of the company held on 22.12.2016 to initiate steps to proceed in consultation with ANERT, the State Government agency, to study the possibilities of setting up solar projects in KPUPL licensee areas.

We have identified three sites, viz, on the roof tops of KPUPL 110KV Substation, Kakkanad, KINFRA 110KV Substation, Hi Tech Park, Kalamassery and KPUPL 22KV Substation at KIITP, Palakkad having roof areas of 300 m2, 400 m2 and 450 m2 respectively for implementation of project on grid connected system. The major components used in this system are PV Solar panels, module mounting structure, inverter and AC distribution board.

On contacting ANERT, they have provided a list of qualified agencies for grid connected Solar Roof Top Power Plant program (Solar Connect) 2016-17.  So, it was decided to call for expression of interest from the agencies in the list.  All the listed agencies were required to conduct site visits and to give their report. The following agencies had submitted their report expressing their interest in implementing the project:

| Sl. No. | Name of Agency | Cost: Supply (Inclusive of all taxes), installation & commissioning charges) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Kakkanad |  | Kalamassery |  | Palakkad |  |  |
|  |  | Power (Kw) | Amount (Rs.) | Power (Kw) | Amount (Rs.) | Power (Kw) | Amount (Rs.) | Rate / Kw (Rs.) |
| 1. | Alternate Energy Corporation | 50 | 30,50,000 | 20 | 12,20,000 | 30 | 18,45,000 | 61,150/- |
| 2. | Swelect Energy Systems Ltd | 30 | 19,83,065 | -- | -- | 50 | 28,03,639 | 59,834/- |
| 3. | R K Tech | 30 | 30,25,500 | 40 | 40,34,000 | 50 | 50,42,500 | 100,850/- |
| 4. | Soura Natural Energy Solutions | 30 | 18,98,000 | 40 | 24,86,000 | -- | -- | 62,628/- |

The agencies offer that this PV solar panel system gives a trouble free performance for 25 years.  Based on the above budgetary offers received, the estimate for implementation of the project was arrived at the rate of Rs. 60,000/- per KWp. The total capacity of the power generation units, using Solar, was estimated to be 110KWp. Accordingly, the cost of implementing a total capacity of 110kW Solar PV power plant at the licensee areas of KPUPL at Kakkanad, Kalamassery and Palakkad was Rs. 66/- Lakhs.

- Cost Estimate

The estimate was submitted to Project Implementation Committee (PIC) of KINFRA headed by Addl. Chief Secretary, Industries Dept., Govt. of Kerala for approval in the 86th PIC meeting dated 30.10.2017. The Project Implementation Committee approved the estimate amounting to Rs.66/- Lakhs including all taxes for the ‘Supply, Installation and Commissioning of solar Project in KINFRA Parks at Kakkanad, Kalamassery and Palakkad’. The Committee authorized Chief Executive Officer, KPUPL to take necessary action for the implementation of the above system by inviting e-tenders from the approved channel partners of MNRE.

The tender for Supply, Installation, Testing, Commissioning, handing over and O&M of Grid connected Solar PV power plants at KINESCO Licensee areas at Kakkanad, Kalamassery and Palakkad was uploaded in Government of Kerala e-Procurement website on 06-01-2018. Three bidders viz M/s. Soura Natural Energy Solutions, M/s. KELTRON and M/s. Solgen Energy participated in the bid. The technical evaluation of all the tenders received were made and it is found that all of them have satisfied all the requirements and hence qualified. The estimated value of contract (PAC) was Rs. 56 Lakhs with applicable taxes extra. Based on this the price bid of the qualified bidders was opened and it is found that rates quoted by M/s. KELTRON is Rs. 60, 76, 957/-, ie. 8.52 % above PAC and the rates quoted by M/s. Soura Natural Energy Solutions is Rs. 69, 37, 780/- ie. 23.89 % above PAC and the rates quoted by M/s. Solgen Energy Pvt. Ltd is Rs. 72, 99,000/- ie 30.34 % above PAC. Thus M/s. KELTRON has become the lowest among the three bidders and hence, L1. Table below shows the details of the bidders, rate quoted and their relative position, for reference.

| Sl. No. | Name of the Bidder | PAC (Rs.) | Amount (Rs.) | (%) | Status |
| --- | --- | --- | --- | --- | --- |
| 1. | M/s. Soura Natural Energy Solutions | 56 Lakhs | 69, 37, 780 | 29.89 % (Above) | L2 |
| 2. | M/s. KELTRON Controls |  | 60, 76, 957 | 8.52 % (Above) | L1 |
| 3. | M/s. Solgen Energy Pvt. Ltd |  | 72, 99,000 | 30.34 % (Above) | L3 |

Accordingly, the work was awarded to M/s. KELTRON Controls vide work order no. 05/2018-19 dated 08.06.2018 for the Supply, Installation, Testing, Commissioning, Handover and O&M of the plant for 5 years of Grid connected Solar PV power plants to a capacity of 110KWp at KPUPL Licensee areas at Kakkanad, Kalamassery and Palakkad for an amount of Rs. 60, 76, 957/- (Rupees Sixty Lakhs Seventy-Six Thousand Nine Hundred and Fifty-Seven only) with GST extra as applicable as per standard procedure of KINFRA.

KPUPL, on 25.10.2017 had filed a petition before the Hon’ble Commission for approval of the Capital Investment / expenditure of KPUPL for the year 2017-18, in our distribution license areas at Kakkanad, Kalamassery and Palakkad. In the petition, KPUPL proposed to install 110 kWp solar plant at a total cost of Rs. 105.99 lakhs. The proposal for investment for the year 2017-18 was Rs 50.00 lakhs.

The Hon’ble Commission admitted the petition as OP No. 3/2018 and during the hearing held on 21.02.2018 observed that, the capital cost and the tariff for the electricity generated from the proposed 110 kWp solar plant was much higher than the similar solar installation by the ‘Solar Energy Corporation of India (SECI)’ and directed the KPUPL to explore the possibilities for installing the solar plant through SECI. The Hon’ble Commission did not consider the request for approval of the capital investment proposed for the installation of the 110kWp solar plant vide KSERC Order 28.05.2018.

SECI has launched a project named ‘Jyothis’, for implementing solar power plants under RESCO model and M/s. Soura Natural Energy Solutions and M/s. Keltron Controls were associated with this program in Kerala. KPUPL enquired with them whether they are ready to implement the solar plants under our license areas. M/s. Soura, in their reply, informed that they would not be able to take up individual projects of capacity less than 100 KWp as it would not be financially feasible for them. M/s. Keltron Controls have replied that they are not taking up these kind of projects due to funding issues. In light of the above, KPUPL requested to the Hon’ble Commission vide letter no. KINESCO/KSERC/RE/2018-19/139 dated 01.09.2018, to include the implementation of Solar Projects under Capital Investment plan for the year 2018-19.

Further, KPUPL filed a petition for approval of ARR & ERC and Capital Investment Plan for the control period from 2018-19 to 2021-22 on 06.12.2018. The Hon’ble Commission admitted the petition as OA No. 8/2020 and hearing was conducted on 22.06.2020 through video conference mode. Later, KSERC vide letter No. 1909/F&T/2018/KSERC dated 04.09.2020 directed KPUPL to submit further details / clarifications. The second public hearing on the petition for approval of ARR and ERC filed by KPUPL for the years from 2018-19 to 2021-22 was conducted by video conference mode on 17.09.2020. In the daily order dated 01.10.2020, the Hon’ble Commission observed that since the first two years of the control period of the Tariff Regulations 2018, ie. year 2018-19 and 2019-20 has already been elapsed, no purpose will be served by approving the ARR & ERC of this period. So, Hon’ble Commission directed KPUPL to submit the true up of accounts for the corresponding years for the consideration of the Commission.

Accordingly, KPUPL is submitting the actual capital expenditure for 2019-20 on this account for the kind consideration and approval of the Hon’ble Commission. In this respect, it may kindly be seen that the licensee had taken all reasonable financial prudence and procedural requirements before proceeding with the implementation of the project. With the regulatory requirement of implementing Solar plants to meet RPO obligation and also considering the prudent steps taken by the licensee in this respect, Hon’ble Commission may kindly approve the actual capital expenditure on this account.

- Financing of Capital Expenditure

Capital expenditure for implementation of Solar Projects amounting to Rs. 60.77 Lakhs during the financial years of the MYT control period from 2018-19 to 2021-22 is as shown in below.

| Sl. No. | Item | Qty. | Unit | Amount in Lakhs |  |  |  | Total Amount (Rs. in Lakhs) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 2018-19 | 2019-20 | 2020-21 | 2021-22 |  |
| 1. | Implementation of Solar Project | 1 | Job | 23.25 | 35.68 | 1.84 | - | 60.77 |

The expenditure towards the above capital work is proposed to be funded from internal accruals (deemed equity) of the company.

- Supporting Documents

  - Copy of minutes of 86th PIC meeting -(Appendix-16)

  - Copy of work order -(Appendix-17)

  - Copy of Payment details - (Appendix-18)

- Supply of Lightning Arrestor – Rs. 5,310/-

- Brief description and Necessity of the Investment

Power for KINFRA Integrated Industrial and Textiles Park (KIITP), Kanjikode, Palakkad is feeding through 22KV Over Head Steelmax feeder from KSEBL 220KV Substation, Kanjikode. There are two AB Switches with 22KV Lightning Arrestors are provided at HT metering yard, one set for KSEBL side and other for KPUPL. The LAs were used to get flashed due to surges.

3 nos of 22KV LAs were procured during the month of October 2019 in order to replace the faulty LAs. Local enquiry was conducted and the item was procured from M/s. Power Best Electricals for Rs. 1500/- per unit. Total expenditure incurred in purchasing the item was Rs. 5,310/-. The procurement of 22KV LAs was entered in KPUPL Asset register and Capitalized as on 22.10.2019.

- Financing of Capital Expenditure

The above capital addition was financed from the accrued surplus of KPUPL

- Supporting Documents

- Copy of the invoice - (Appendix-19)

- Installation of DP structure with fuse unit at MFP – Rs. 58,917/-

- Brief description and Necessity of the Investment

Power for KINFRA Mega Food Park, Kozhipara, Palakkad is feeding through 22KV dedicated feeder from KSEBL 110KV Substation, Walayar. There are two AB Switches provided at HT metering yard, one for KSEBL side and other for KPUPL. A drop out fuse unit (DO) is provided at KSEBL side for protection of metering equipments. During any failure of DO fuse, long duration power interruption occurs due to delay in attending the fault by KSEBL field staff.

Under this circumstance, it was decided to install one double pole structure with DO fuse unit at KPUPL side so that this DO will fail initially and KPUPL staff can attend the fault immediately and restore the supply at the earliest.

Local enquiry was conducted and invited competitive quotations from electrical contractors who are doing similar works. Three contractors offered their rates as tabulated below.

| Sl. No. | Participant | Quoted Amount (Rs.) | Status |
| --- | --- | --- | --- |
| 1. | M/s. BENITA Electricals | 50,950/- | L1 |
| 2. | Mr. Jaffer A | 56,400/- | L3 |
| 3. | M/s. Delstar Electricals | 54,100/- | L2 |

M/s. BENITA Electricals offered the lowest price for the above mentioned work for Rs. 50,950/- with GST extra as applicable. Rock bottom rates were requested and they replied that they are ready to execute the work at 2% less the offered rate.  Work order was awarded to M/s. BENITA Electricals for ‘Installation of DP structure with DO fuse unit on 22KV feeder at KINFRA Mega Food Park’ vide WO No. 09/2019-20 dated 29.11.2019 for Rs. 49,931/- (Rupees Forty-nine thousand nine hundred and thirty-one only) with GST extra as applicable. The contractor had completed the work satisfactorily as per the work order and the item was entered in KPUPL Asset register and Capitalized as on 16.01.2020.

- Financing of Capital Expenditure

The above capital addition was financed from the accrued surplus of KPUPL

- Supporting Documents

- Copy of the quotations received from contractors-(Appendix-20)

- Copy of the work order - (Appendix-21)

- Copy of the contract agreement - (Appendix-22)

- Copy of the payment note - (Appendix-23)

- Tools for sub-station at Kakkanad – Rs. 8,681/-

- Brief description and Necessity of the Investment

KPUPL has been following prepaid energy metering system since its inception. The energy consumption details of consumers can be obtained and managed from the central server located at Kakkanad office. There are some connections for which conventional energy meters are installed and there are some cases for which data communication is not healthy. In such cases, the meter reader used to collect the energy consumption data manually.

There was urgent requirement of basic tools like line tester, plier, wire stripper and measuring equipments like clamp meter and multi meter and safety helmet and torch for meter reader at Kakkanad office. Local enquiry was conducted and items were purchased from suppliers selling similar items. An amount of Rs. 8,681/- has been spent on the purchase of the above tools and equipments and safety helmet. The items were entered in KPUPL Asset register and Capitalized as on 25.02.2020.

- Financing of Capital Expenditure

The above capital addition was financed from the accrued surplus of KPUPL

- Supporting Documents

- Copy of the invoices - (Appendix-24)

- Supply, installation, testing, commissioning & handing over of 11KV RMUs – Part Payment – Rs. 15,72,409/-

- Brief description and Necessity of the Investment

- KPUPL Kanjikode Licensee Area at KIITP

KPUPL has started operations at KINFRA Integrated Industrial and Textiles Park (KIITP), Kanjikode at Palakkad on 5th August, 2016. The 11 KV distribution network at KIITP, Kanjikode was set up using 11KV feeder pillars instead of Ring Main Units (RMUs) due to lack of budget as well as time during the year 2016. But as per the control point of view as well as safety norms, feeder pillars are not allowed in the 11 KV network and hence, the Chief Electrical Inspector to Govt. (CEIG) has accorded energization approval to the 22KV substation and related 11KV distribution system subject to the condition that the feeder pillars should be replaced with RMUs within one year.  Accordingly, 8Nos of 11KV feeder pillars were to be replaced with 11KV RMUs as per the directions of CEIG.

- KPUPL Kakkanad Licensee Area

The KPUPL licensee area at Kakkanad includes KINFRA Export Promotion Industrial Park (KEPIP) and Infopark Phase-1 and both the areas are almost fully occupied by industries. KPUPL is having a well-equipped power distribution network using UG Cables and RMUs emanating from KPUPL 110 KV substation in this area. The development of power distribution network at Kakkanad licensee area was made during the year 2004 and later development was done during the year 2010.

The four existing Ring Main Units (RMUs) of Merlin Gerin – Ring Master make in the power distribution network in the Kakkanad licensee area were in deteriorated condition and almost obsolete. The year of manufacture of these RMUs were 2004. The SF6 gas leak in these RMUs were very critical and hence, operation became very risky and difficult. Being obsolete, these RMUs were beyond repair. Hence, it was proposed to replace these RMUs with new ones.

- KPUPL Licensee Area at KINFRA Hi Tech Park, Kalamassery

At present KPUPL is having only one 11KV radial system to cater the power to the consumers at KINFRA Hi Tech Park, Kalamassery, distributed around wide area in the park. As a part of strengthening of existing distribution system by providing ring formation, additional 2 nos of 11 KV RMUs have to be procured. This will make redundancy in the system and ensure uninterrupted supply in Hi Tech Park, Kalamassery.

- Cost Estimate

36th Board Meeting of KINESCO has approved the proposal for procurement of items needed for the works of 2nd phase of KIITP, Kanjikode as per the normal procedures followed in KINFRA.  Accordingly, the estimate has been put forward for the approval of KINFRA Project Implementation Committee (PIC) headed by Additional Chief Secretary, Industries dept., Govt. of Kerala. Accordingly, in the 86th meeting held on 30.10.2017, the PIC has approved an estimate amounting to Rs. 118/- Lakhs including GST @18% for the procurement, installation and commissioning of RMUs and related civil works for the licensee areas of KINESCO at Kakkanad, Kalamassery and Palakkad. The Committee authorized Chief Executive Officer, KINESCO to take necessary action for the implementation of the project as per the procedure followed in KINFRA using e-tendering.

The tender for Supply, Installation, Testing and Commissioning of 11 KV Ring Main Units (RMUs) at KINESCO Licensee areas at Kakkanad, Kalamassery and Palakkad was uploaded in Government of Kerala e-Procurement website on 13-12-2017. The three offers received from the bidders viz M/s. Electrofine, M/s. Delstar and M/s. Sterling & Wilson were scrutinized and found that M/s. Sterling & Wilson have not satisfied the conditions of tender and hence disqualified. The technical evaluation of remaining two tenders were made and it is found that both of them have satisfied all our requirements and hence qualified. Based on this the price bid of the qualified bidders was opened and it is found that rates quoted by M/s. Delstar is Rs. 86, 91, 450/-, ie. 3.43 % less than PAC and the rates quoted by M/s. Electro Fine is Rs. 58, 24, 560/- ie. 35.29 % less than PAC which is the L1.

| Sl. No. | Name of the Bidder | Make of RMU | PAC (Rs.) | Amount (Rs.) | Less (%) |
| --- | --- | --- | --- | --- | --- |
| 1. | M/s. Electro Fine | CG-Lucy | 90 Lakhs | 58.25 Lakhs | 35.29% |
| 2. | M/s. Delstar | ABB |  | 86.91 Lakhs | 3.43% |

Accordingly, the work was awarded to M/s. Electro Fine vide work order no. 02/2018-19 dated 25.04.2018 for the Supply, Installation, Testing, Commissioning and Handover of 11KV Ring Main Units (RMU) in the licensee areas of KPUPL at Kakkanad, Kalamassery and Palakkad for an amount of Rs. 58, 24, 560/- (Rupees Fifty-Eight Lakhs Twenty-Four Thousand Five Hundred and Sixty only) with GST extra as applicable as per standard procedure of KINFRA.

KPUPL, on 25.10.2017 had filed a petition before the Hon’ble Commission for approval of the Capital Investment / expenditure of KPUPL for the year 2017-18, in our distribution license areas at Kakkanad, Kalamassery and Palakkad.  In the petition, KPUPL proposed to replace 11KV feeder panels with RMUs at Palakkad and replacement of RMUs at Kakkanad and Kalamassery for a total cost of Rs. 68 lakhs. The Hon’ble Commission admitted the petition as OP No. 3/2018 and in the order dated 28.05.2018, the Commission rejected the request for granting approval for the proposed investment for want of sufficient details and documents.

Further, KPUPL filed a petition for approval of ARR & ERC and Capital Investment Plan for the control period from 2018-19 to 2021-22 on 06.12.2018. The Hon’ble Commission admitted the petition as OA No. 8/2020 and hearing was conducted on 22.06.2020 through video conference mode. Later, KSERC vide letter No. 1909/F&T/2018/KSERC dated 04.09.2020 directed KPUPL to submit further details / clarifications. The second public hearing on the petition for approval of ARR and ERC filed by KPUPL for the years from 2018-19 to 2021-22 was conducted by video conference mode on 17.09.2020. In the daily order dated 01.10.2020, the Hon’ble Commission observed that since the first two years of the control period of the Tariff Regulations 2018, ie. year 2018-19 and 2019-20 has already been elapsed, no purpose will be served by approving the ARR & ERC of this period. So Hon’ble Commission directed KPUPL to submit the true up of accounts for the corresponding years for the consideration of the Commission.

- Financing of Capital Expenditure

The expenditure towards the above capital work is proposed to be funded from internal accruals (deemed equity) of the company.

- Supporting Documents

  - Copy of CEIG sanction order - (Appendix-25)

  - Copy of minutes of 86th PIC meeting -(Appendix-26)

  - Copy of work order -(Appendix-27)

  - Copy of the Invoices - (Appendix-28)

Installation of RMUs was taken up at the instance of the Chief Electrical Inspector and also in view of the urgency of safety in distribution network. In view of this, Hon’ble Commission is requested to consider approval of the actual expenditure on this account under capital head for the year 2019 - 20.

- Purchase of CT/PT and GI supports – Rs. 1,85,639/-

- Brief description and necessity of the investment

Hon’ble Commission in Trueing Up Order dated 29.03.2021 for the truing up of accounts for the year 2017-18 have approved the asset addition for Rs. 32.66 lakhs based on the details given by KPUPL. This included purchase of supporting structure for 110KV CT, purchase of 110KV CTs and PTs as part of upgradation of 110KV metering equipments to 0.2S accuracy class. The equipments were purchased from M/s. Suman Controls (P) Ltd as per the following purchase orders shown in the table below.

| Sl. No. | KPUPL Purchase Order No. with Date | Item | Invoice No. | Invoice Amount (Rs.) |
| --- | --- | --- | --- | --- |
| 1. | 12/2016-17 dated 28.09.2016 | 110KV Outdoor Oil immersed CT with ratio 110/1A – Sl Nos.1101033-01 to 1101033-03 (3 nos.) | 000094 dated 08/02/2017 | 3,44,277.00 |
| 2. | 13/2016-17 dated 28.09.2016 | 110KV Outdoor Oil immersed PT with ratio 110kV/RT3-110V/RT3 – Sl Nos.1101034-01 to 1101034-03 (3 Nos) | 000102 dated 04/03/2017 | 3,44,277.00 |
| 3. | 14/2016-17 dated 20.10.2016 | Supporting Structure for 110KV CT (6 Nos) | 000095 dated 08/02/2017 | 1,49,700.00 |
|  | TOTAL |  |  | 8,38,254.00 |

The above capital asset addition has already been approved in Sl. No. 74 (Page No. 30 - 31) in Trueing Up Order dated 29.03.2021 for the truing up of accounts for the year 2017-18.

This is the amount paid to M/s. Suman Controls towards release of differential CST (12.5%) against purchase of 110KV Current Transformers (CTs), Potential Transformers (PTs) and GI supporting structure.

- Cost Estimate

An amount of Rs. 1,85,639/- has been paid to M/s. Suman Controls towards release of differential CST (12.5%) against purchase of 110KV Current Transformers (CTs), Potential Transformers (PTs) and GI supporting structure.

- Financing of Capital Expenditure

The above capital addition was financed from the accrued surplus of KPUPL

- Supporting Documents

  - Copy of the invoices –  - (Appendix-29)

- Purchase of 11KV Cast Resin 90/5A 0.2s class CT for Kalamassery – Rs. 47,790/-

- Brief description and Necessity of the Investment

KPUPL Kalamassery Licensee area was having power connectivity and power purchase agreement for 1000 KVA with KSEBL. During the month of January 2019, the maximum demand in the park had exceeded the contract demand. So it became necessary to enhance the power connectivity to 1500 KVA. 11KV metering CT of ratio 60/5A was in operation at Kalamassery and the same was not suitable for 1500KVA. As per the request, KSEBL suggested to replace the CT with new CT of ratio 90/5A.

Local enquiry was conducted and quotations were invited from suppliers who are supplying similar items. M/s. Intrans Electricals Pvt. Ltd and M/s. Transwaves Equipments P Ltd submitted their offers and after negotiation, purchase order was issued to M/s. Intrans Electricals P Ltd for Rs. 40,500/- with GST extra as applicable. The supplier had completed the delivery and payment had been released towards delivery.

- Financing of Capital Expenditure

The above capital addition was financed from the accrued surplus of KPUPL

- Supporting Documents

- Copy of the quotations received from suppliers -(Appendix-30)

- Copy of the purchase order - (Appendix-31)

- Copy of the payment note - (Appendix-32)

Summary

| Sl. No | Description of Asset Capitalized | Unit | Qty | Amount (Rs.) | Date of Capitalization |
| --- | --- | --- | --- | --- | --- |
| 1 | Development work of sub-station road (proportionate cost transferred by KEPIP) | LS | LS | 12,17,059.00 | 31.03.2020 |
| 2 | Visitors' Chair (steel- 3 seater) | No. | 2 | 11,328.00 | 27.12.2019 |
| 3 | TOD meters | No. |  | 1,01,798.00 | 13.05.2019 |
| 4 | TOD metering panel (KIITP/MFP) | LS |  | 53,690.00 | 17.09.2019 |
| 5 | Mobile phone for Palakkad area | No | 1 | 1,400.00 | 22.10.2019 |
| 6 | HP Laptop Battery | No | 1 | 3,000.00 | 27.09.2019 |
| 7 | Procurement of PCs & peripherals | No | 2 | 1,52,012.00 | 22.10.2019 |
| 8 | Solar Generating plant at Kakkanad & Kalamassery | KWp | LS | 35,68,468.00 | 31.03.2020 |
| 9 | Supply of Lightning Arrestor | No | 1 | 5,310.00 | 22.10.2019 |
| 10 | Installation of DP structure with fuse unit at MFP | No | 1 | 58,917.00 | 16.01.2020 |
| 11 | Tools for sub-station at Kakkanad |  |  | 8,681.00 | 25.02.2020 |
| 12 | Supply & installation of RMUs at Kakkanad |  |  | 15,72,409.00 | 31.03.2020 |
| 13 | Purchase of CT/PT and GI supports |  |  | 1,85,639.00 | 01.07.2019 |
| 14 | Purchase of 11KV Cast Resin 90/5A 0.2s class CT for Kalamassery | No | 1 | 47,790.00 | 10.04.2019 |
|  | Total Amount |  |  | 69,87,501.00 |  |

Even though approval of the Capital Expenditure Plan submitted by KPUPL is pending with Hon’ble Commission, certain essential expenditures were to be incurred by the Company on this account to meet the technical necessities of the plant and of RPO obligation.

Item No.1, development of sub-station road was part of the common developmental works undertaken by KEPIP and transferred to KPUPL, which was necessitated for better approach on emergency like flash over during lightening, to the 110 KV sub-station at Kakkanad. Item at Sl No.8 i.e. installation of solar plant in three parks was an initiative taken by KPUPL to meet the obligation under RPO as directed by the Hon’ble Commission. Item No.12 is incurred for meeting the technical requirement of Chief Electrical Inspector, Govt. of Kerala and also in view of the urgency of safety in distribution network.

All other items of asset addition are below the limit of Rs. 5 lakhs. Supporting documents for the justification for the fixed asset addition is enclosed herewith. Hon’ble Commission is requested to kindly accord approval for the additional capital expenditure of 69.86 Lakhs incurred in 2019-20.

Chief Executive Officer

List of documents attached

| Sl. No. | Particulars | Appendix No. |
| --- | --- | --- |
| I | Development work of sub-station road |  |
| 1. | Copy of request letter to KEPIP from KPUPL | Appendix -01 |
| 2. | Copy of bill details RAB-1 & RAB-2 (final) | Appendix -02 |
| II | Visitors' Chair (steel- 3 seater) |  |
| 3. | Copy of the invoice | Appendix -03 |
| III | TOD meters |  |
| 4. | Copy of the quotation notice | Appendix -04 |
| 5. | Copy of the purchase order | Appendix -05 |
| 6. | Copy of the contract agreement | Appendix -06 |
| 7. | Copy of the payment note | Appendix -07 |
| IV | TOD metering panel (KIITP/MFP) |  |
| 08. | Copy of the quotations received from contractors | Appendix -08 |
| 09. | Copy of the work order | Appendix -09 |
| 10. | Copy of the contract agreement | Appendix -10 |
| 11. | Copy of the payment note | Appendix -11 |
| V | Procurement of PCs & peripherals |  |
| 12. | Copy of the quotations received from suppliers | Appendix -12 |
| 13. | Copy of the purchase order | Appendix -13 |
| 14. | Copy of the contract agreement | Appendix -14 |
| 15. | Copy of the payment note | Appendix -15 |
| VI | Solar Generating plant at Kakkanad & Kalamassery |  |
| 16. | Copy of minutes of 86th PIC meeting | Appendix -16 |
| 17. | Copy of work order | Appendix -17 |
| 18. | Copy of Payment details | Appendix -18 |
| VII | Supply of Lightning Arrestor |  |
| 19. | Copy of the invoice | Appendix -19 |
| VIII | Installation of DP structure with fuse unit at MFP |  |
| 20. | Copy of the quotations received from contractors | Appendix -20 |
| 21. | Copy of the work order | Appendix -21 |
| 22. | Copy of the contract agreement | Appendix -22 |
| 23. | Copy of the payment note | Appendix -23 |
| IX | Tools for sub-station at Kakkanad |  |
| 24. | Copy of the invoices | Appendix -24 |
| X | Supply & installation of RMUs at Kakkanad |  |
| 25. | Copy of CEIG sanction order | Appendix -25 |
| 26. | Copy of minutes of 86th PIC meeting | Appendix -26 |
| 27. | Copy of work order | Appendix -27 |
| 28. | Copy of the Invoices | Appendix -28 |
| XI | Purchase of CT/PT and GI supports |  |
| 29. | Copy of the Invoices | Appendix -29 |
| XII | Purchase of 11KV Cast Resin 90/5A 0.2s class CT for Kalamassery |  |
| 30. | Copy of the quotations received from suppliers | Appendix -30 |
| 31. | Copy of the purchase order | Appendix -31 |
| 32. | Copy of the payment note | Appendix -32 |